**PROGRAM MANAGER LIST AND CHANGE ORDER THRESHOLDS**

**August 5, 2007**

**Office of Construction Administration**

|  |
| --- |
| **CHANGE ORDER THRESHOLDS FOR CENTRAL OFFICE FUNDED PROGRAMS**CONSULT BY E-MAIL PRIOR TOWORK OR APPROVAL |
| **Group ID** | **Program** | **Manager** | **Thresholds** |
| **SAC Codes** |  | (all 614 area code except as noted) | $ and/or % |
| MNC***4BK7, 4BD7, 7BDB, 7PE7, 729B, 727B, 4D27, 4EK5, 7287, 4EK7, 7307, 729A, 727A, 4BD74MN7, 4J27, 4R27, 4D47*** | Major New Construction | Jennifer Townley466-7493Don Fisher(614) 387-2614 | $100,000 and all CO’s after project price has increased 10% |
|  |  |  |  |
| APD***4D27, 4D37*** | Major & New ConstructionOther | Jerry Workman(614) 387-5417 | $100,000 and all CO’s after project price has increased 10% |
|  |  |  |  |
| GSP***4F27, 4F37, 4665*** | Grade Separation Program | Tony Goddard752-9005Rich Behrendt(614) 387-3097 | $50,000 and all CO’s has increased 10% |
|  |  |  |  |
| MBP***4BU7, 4BT7, 7BTB*** | Major Bridge Program | Kelly Brooker Scocco (614) 387-6225 | $100,000 and all CO’s after project price has increased 10% |
|  |  |  |  |
| MLR***4RC7, 4RA7, 7RAB, 7PM7*** | Multi-Lane Reconstruction | Scott Phinney(614) 644-9147 | $100,000 and all CO’s after project price has increased 10% |
|  |  |  |  |
| ABP***4BQ7, 4BS7*** | Amish Buggy Program | Jerry Workman(614) 387-5417 | $10,000 |
|  |  |  |  |
| ***4B47, 4BX7*** | Miscellaneous Statewide Program | Julie Ray(614) 466-2687 | $15,000 |
|  |  |  |  |
| ***4BY7, 4BE7*** | Emergency Capital | Rich Winning(614) 644-5424 | Make contact on ALL change orders |
|  |  |  |  |
| TEA***4B37*** | Trans. Enhancement Bikeways | Randy Lane(614) 644-8211 | If over Funding Cap.If no Funding Cap, then Lesser of $10,000 or 10% of original contract price |
|  |  |  |  |
| HSP***4BJ7, 4BC7, 4DP7, 4BCB, 718B, 4BJ2, 7197, 718A, 4BC2, 7BC7, 4RS7, 4HJ7, 4R67*** | Safety | Michelle May(614) 644-8309 | $50,000 and all CO's after project price has increased 10% |
|  |  |  |  |
| NWR***4BV7*** | Retrofit Noise Walls | Elvin Pinckney466-5154 | 5% of noise wall portion of project price |
|  |  |  |  |
| RAS***4BP7, 4BR7*** | Rest Areas | Mark Spagnuolo752-0388 | Lesser of $10,000 or 10% of original contract price. |
|  |  |  |  |
| LBR***4HC7*** | Local Major Bridge | Randy Lane(614) 644-8211 | If over Funding Cap.If no Funding Cap, then Lesser of $10,000 or 10% of original contract price |
|  |  |  |  |
| CBR***4R87*** | City Local Bridges | Randy Lane(614) 644-8211 | If over Funding Cap.If no Funding Cap, then Lesser of $10,000 or 10% of original contract price |
|  |  |  |  |
| STM***4B97*** | Small City's STP | Randy Lane(614) 644-8211 | If over Funding Cap.If no Funding Cap, then Lesser of $10,000 or 10% of original contract price |
|  |  |  |  |
| ***4D57*** | Discretionary | Linda Bailiff(614) 728-8062 | All funds are capped. |
|  |  |  |  |
| GSM***4SF7, 4SS7*** | Geologic Site Management (landslides) | Jerry Workman(614) 387-5417 | $50,000 and all CO's after project price has increased 10% |
|  |  |  |  |
| **CHANGE ORDER THRESHOLDS FOR CENTRAL OFFICE FUNDED PROGRAMS****WITH INTERNAL AND EXTERNAL MANAGERS**CONSULT THE EXTERNAL MANAGER BY E-MAILPRIOR TO WORK OR APPROVALAND COPY INTERNAL MANAGER |
| MTP***4BW7*** | Metro Parks | **External Manager:**Ohio Parks and Recreation Association (OPRA)Don Osborn (614) 839-6225Fax (614) 895-3050 dosborn@apraonline.org**Internal Manager:**Sharon Todd 614-752-4685 | All CO’s after project price has increased 5% |
|  |  |  |  |
| DNR***4BF7*** | ODNR | **External Manager:**Ohio Department of Natural Resources (ODNR)Gus Smithhisler (ODNR)(614) 265-6965paul.smithhisler@dnr.state.oh.us**Internal Manager:**Mike McColeman 614-644-7155 | All CO’s $25,000 or greater |
|  |  |  |  |
| LRS***4B77, 4HB7, 4RB7*** | County STP Program | External Manager:County Engineers Association of Ohio(CEAO)Michele Risko (614) 221-0707 X15Internal Manager:Randy Lane 644-8211 | All CO’s after project price has increased by: 10% for project under $1 million5% for projects of $1 million and over |
|  |  |  |  |
| LBR***4B87*** | County Local Bridge | External Manager:County Engineers Association of Ohio(CEAO)Michele Risko (614) 221-0707 X15Internal Manager:Randy Lane (614) 644-8211 | All CO’s after project price has increased by: 10% for project under $1 million5% for projects of $1 million and over |
|  |  |  |  |
| LOM***4TA7, 4TB7, 4TC7, 4AQ7, 4AM7*** | Local MPO | External Manager:Local MPO contact personInternal Manager:Dave Moore (614) 466-0754 | All CO’s after project price exceeds funding CAP are 100% local participating agency (city, village, county, or township) not the MPO, inform the appropriate agency when this occurs. |
|  |  |  |  |
| **SPECIAL FUNDS MANAGED BY****ROD RICKABAUGH**(614) 752-2179 |
| **4BG6** | OPWC Local Government Projects | There is no need to contact the Program Manager, Rod Rickabaugh (614) 752-2179, if the Memorandum of Funds for the project gives a funding CAP. Any change order increasing the project above this CAP is 100% District or locally funded. You should advise the District Planning and Programming Administrator or local agency when this occurs and inform them that they must fund the change order from another source. |
| **4BG7** | Local Government Projects |
| **4D47** | Major and New Construction (Discretionary) |
| **4J27** | Major and New Construction (Demo) |
| **4J37** | District Demonstration |
| **4J47** | Local Government Demonstration |
| **4J57** | Other Demonstration |
| **4RD7** | High Priority Projects |
| **4R27** | Major and New Construction (High Priority) |
| **4R37** | District High Priority |
| **4R47** | Local Government High Priority |
| **4R57** | Other High Priority |