CHECKLIST

Proposal Note 107

Critical Path Method Progress Schedule (01-16-04)

Project:__________		Contractor:_______________________________		Date:___________

Proposal Note 107 Requirements (Contract Requirements)

General:

- Contractor has a designated Schedule Representative.  Name:______________________

Baseline Requirements:

- Contractor submitted an interim project schedule within 30 days after the execution of the Contract or prior to start of work, whichever came first.

- Contractor submitted a detailed CPM schedule within 60 days of the execution of the Contract or prior to start of work.

Schedule Requirements:

- Schedule included the following Administrative Identifier Information:

- Project Number

- County

- Route Number

- FHWA Number

- PID Number

- Contract Signed Date

- Completion Date

- Contractor’s Name

- Contractor’s Dated Signature

- ODOT’s Dated Approval Signature

- Schedule included activity requirements

  - Activity ID

  - Activity Description

  - Activity Original Duration

  - Relationships all FS or

SS (w/lag < pred duration)

- All activities except first have

a predecessor

- All activities except last have

a successor

- Constraints used sparingly

- Only Early Constraints or

Late Constraints used

- Non-work or seasonal shutdowns

shown in calendars

- Project electronic file not

linked to another project

- Activity codes, minimum three

- Schedule Options - schedule

calculated using retained logic

- Schedule Options - open ends

shown as non-critical

- Schedule Options – durations

are contiguous

- Schedule Options – total

float calc. as finish float

Submission Requirements:

- Schedule submitted in electronic file format

- CPM schedule in bar chart format

  - Bar chart shows activity ID, activity description, original duration, remaining duration, early start date, early finish date, total float and calendar ID

  - critical path in red

- Six week look ahead schedule

- Scheduling Statistics Report

Schedule reviewed and;

- Approved

- Approved as noted						ODOT Reviewer:

- Rejected

Name:_________________________

COMMENTS

Proposal Note 107

Critical Path Method Progress Schedule (01-16-04)

Critical Path Method Schedule Comments (Non-Contractual Requirements)

Proposal Note 107 addresses the contract requirements for the contractor’s baseline schedule.  Proposal Note 107 will ensure the project receives a technically acceptable schedule without being an overly prescriptive specification.  The reviewer still needs use common sense to evaluate the schedule in sufficient detail to accept it as a reasonable and workable plan to complete the project by the original contract completion date.

If the reviewer has additional comments, the reviewer can add the comments to the acceptance letter to the contractor below the Contractual Requirements.  The reviewer will fashion a paragraph to describe the comments as follows:

“We have the following additional comments based on our initial review of the schedule.  While these comments do not constitute reasons to reject the schedule, we request that the Contractor review the comments and provide a narrative response to each comment and/or revise the schedule as appropriate.”

Additional comments may include, but not be limited to, the following items:

1. Are the activity codes organized into a useful format?

2. Are Hammocks preferable to track durations of road closures or other plan work?  Hammocks are not activities and do not drive the work in the schedule.  Hammocks are acceptable with a SS relationship on predecessor and a FF on the successor.

3. Are there long periods of shutdown?  Are shutdown periods shown in the calendars?  Do all the calendars make sense?  Are activities assigned to the correct calendar?

3. Review the critical path.  Does the project finish on time?  How many activities are in the longest path?  Are there many unique critical paths or branches to the critical paths?  Do you thing the critical path is reasonable, based on what you know about this project?

Observations

- On bridge projects, bridges are usually critical, review bridge component durations.

- On paving projects, review paving durations.

4.  Review non-critical paths.  Do durations make sense?  Are there activities with excessive float?

5. First activities.  Start construction should be the contract execution date (contract signed).  Is there a need for mobilization, field office, submittals, ODOT review times, fabrication times.

6. Last activities.  Project complete should be before or on the contract completion date.  Is there a need for punchlist or demobilization activities?