## Instructions
Instructions for Construction Duration Determination Tool
I. Purpose and Background
Determination of an accurate construction contract duration is vital to the overall success of a project. Allowing more time than necessary may increase road user delay, increase ODOT contract administration costs, and may have a negative influence on public opinion when work does not appear to progress within a work zone. Specifying a small timeframe to complete the work may unnecessarily increase projects costs by requiring the contractor to mobilize extra forces and work overtime on projects that may not necessarily need expedited timelines. This tool serves as guidance for project engineers and designers developing construction project timelines. This guide should be used as a supplement to “hands-on” knowledge and experience. If preparing a construction timeline for a particular aspect of a project that you are unfamiliar with, the project engineer/designer should consult with experts in this field of construction. The project engineer/designer should use sound engineering judgment necessary to determine the sequencing of operations and identify construction overlap to ascertain the appropriate project timelines.
II. Instructions for Contract Time Determination
A. Determination of Adjustment Factors: The project engineer or desginer should determine which adjustment factors apply to the project. These factors will be used to adjust production rates for items of work entered in the next step. Use the pull down menu in each cell to select the most appropriate adjustment factors for the project in the Production Rates tab.
| Location |  | Traffic |  | Complexity |  | Soil Conditions |  | Quantity
| Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1
| Small City | 0.85 | Moderate | 0.88 | Medium | 0.85 | Fair | 0.85 | Medium | 0.88
| Large City | 0.75 | Heavy | 0.7 | High | 0.7 | Poor | 0.65 | Small | 0.75
B. Enter Items of Work in the Bar Chart tab. Click on the first cell under the Description column and a pull down menu appears. Scroll down the pull down menu to find the first tiem of work. Next to each item of work enter a contract quantity. Repeat for each item of work in the plan. To enter an item of work not on the pull down menu, turn off data validation for that cell. Go to Data -> Data Validation -> Clear All.
C. Enter a Preceeding Activity ID and Percent Complete for each item of work in the Bar Chart tab. Scroll down to visually verify that the activities are in the correct sequence in the bar chart.
D. From the Bar Chart Tab, determine the Total Working Days for the project.
E. In the Completion Date tab, enter the Total Working Days and select a starting month for the project. The first cell in the first column contains a pull down menu to select the month and year for the project start. The spreadsheet will provide an estimated number of work days available in the upcoming months. The second column takes into account weekends, holidays and anticipated weather days. The Conditional Formatting will indicated which month(s) to set a completion date to accomplish the items of work entered into the Bar Chart.
F. Projects with multiple phases or areas may require the user to create additional Bar Chart tabs to determine Total Working Days.

## Bar Chart
Contstruction Duration Determination Worksheet
Bar Chart Method
ODOT Project Number:
| Project Information | [6 empty] | FHWA Project Number:
Description: | [7 empty] | PID Number:
Date:
County: |  |  | Distict: |  |  |  |  | Scheduler:
Route No.: |  |  | Designer: |  |  |  |  | Email :
| ID No. | Description | Contract Quantity | Units | Base Production Rate | Units | Adjusted Production Rate | Units | Working Day Duration | Preceeding Activity |  | Start Day | Finish Day
[10 empty] | ID | Percent Complete
| 1 | [5 empty] | 0 |  | 0 |  |  | 1 | 0
| 2 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 3 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 4 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 5 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 6 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 7 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 8 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 9 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 10 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 11 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 12 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 13 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 14 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 15 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 16 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 17 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 18 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 19 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 20 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 21 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 22 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 23 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 24 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| 25 | [5 empty] | 0 |  | 0 |  |  | #N/A | 0
| Comments: | [9 empty] | Total Working Days |  | 0

## Production Rates
ID No. | Description | Base Production Rate | Units | Adjustment Factors | [9 empty] | Adjusted Production Rate | Units
|  |  |  | Location |  | Traffic |  | Complexity |  | Soil Conditions |  | Quantity
1 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
2 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
3 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
4 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
5 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
6 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
7 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
8 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
9 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
10 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
11 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
12 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
13 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
14 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
15 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
16 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
17 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
18 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
19 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
20 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
21 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
22 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
23 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
24 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0
25 | 0 | #N/A |  | Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1 | 0

## Adjustment Factors
Location |  | Traffic |  | Complexity |  | Soil Conditions |  | Quantity
Rural | 1 | Light | 1 | Low | 1 | Good | 1 | Large | 1
Small City | 0.85 | Moderate | 0.88 | Medium | 0.85 | Fair | 0.85 | Medium | 0.88
Large City | 0.75 | Heavy | 0.7 | High | 0.7 | Poor | 0.65 | Small | 0.75

## Items of Work
Major Worktype | Sub Worktype - Description | Unit | Low | High
Bridge | Bridge - Bearing Assembly | each | 5 | 10
Bridge | Bridge - Bridge Deck Concrete Overlay | square yard | 200 | 500
Bridge | Bridge - Bridge Deck Grooving | square yard | 500 | 800
Bridge | Bridge - Bridge Deck Scarification (Cold Milling) | square yard | 350 | 1000
Bridge | Bridge - Bridge Deck Scarification (Hydroblasting) | square yard | 175 | 500
Bridge | Bridge - Concrete Structures | cubic yard | 10 | 25
Bridge | Bridge - Concrete Superstructure | cubic yard | 10 | 30
Bridge | Bridge - Clean & Paint Steel Bridge - SP 10 | square foot | 1000 | 2100
Bridge | Bridge - Clean & Paint Steel Bridge - SP 6 | square foot | 800 | 1600
Bridge | Bridge - Clean & Paint Steel Bridge - SP 3 | square foot | 250 | 550
Bridge | Bridge - Cofferdam (Doesn’t apply for major river bridges) | each | 0.2 | 0.5
Bridge | Bridge - Concrete Removal | cubic yard | 5 | 20
Bridge | Bridge - Deck Slab Repair (Full Depth) | square yard | 10 | 25
Bridge | Bridge - Deck Slab Repair (Partial Depth) | square yard | 25 | 50
Bridge | Bridge - Driving Piles | foot | 250 | 500
Bridge | Bridge - Cofferdam Excavation | cubic yard | 75 | 150
Bridge | Bridge - Formed Concrete Repair | square foot | 50 | 100
Bridge | Bridge - Jacking & Cribbing (per beam) | each | 5 | 10
Bridge | Bridge - Precast Concrete Beam Erection | foot | 150 | 325
Bridge | Bridge - Precast Concrete Beams (Fabricate & Furnish) | calendar day | 30 | 120
Bridge | Bridge - Precast Concrete Bridge Deck | square foot | 500 | 800
Bridge | Bridge - Precast Deck Beams | square foot | 1000 | 3000
Bridge | Bridge - Protective Shield | square yard | 160 | 250
Bridge | Bridge - Reinforcement Bars (Substructure) | pounds | 4000 | 6000
Bridge | Bridge - Reinforcement Bars (Superstructure) | pounds | 10000 | 15000
Bridge | Bridge - Removal of Existing Concrete Deck | square yard | 150 | 300
Bridge | Bridge - Removal of Existing Substructure | cubic yard | 20 | 40
Bridge | Bridge - Removal of Existing Superstructure | square yard | 100 | 250
Bridge | Bridge - Slope Wall | square yard | 25 | 75
Bridge | Bridge - Structural Steel Erection | foot | 150 | 250
Bridge | Bridge - Structural Steel (Fabricate & Furnish) | calendar day | 60 | 270
Bridge | Bridge - Stud Shear Connectors | each | 1000 | 2500
Bridge | Bridge - Temporary Sheet Piling | square foot | 300 | 1000
Bridge | Bridge - Test Pile | Each | 0.5 | 1
Bridge | Bridge - Waterproofing Membrane System | square yard | 100 | 250
Electrical | Electrical - Conduit in Trench | foot | 75 | 325
Electrical | Electrical - Conduit (Pushed) | foot | 30 | 75
Electrical | Electrical - Controller | each | 0.5 | 1
Electrical | Electrical - Detector Loop | foot | 150 | 300
Electrical | Electrical - Electric Cable | foot | 1500 | 3000
Electrical | Electrical - Electrical Conductors in Conduit | foot | 750 | 1300
Electrical | Electrical - Foundations - Controller, Signal | foot | 2 | 5
Electrical | Electrical - Foundations - Light Poles | foot | 10 | 20
Electrical | Electrical - Foundations - Light Towers | foot | 20 | 25
Electrical | Electrical - Handholes | each | 2 | 4
Electrical | Electrical - Junction Box | each | 2 | 5
Electrical | Electrical - Light Pole | each | 4 | 6
Electrical | Electrical - Light Tower | each | 1 | 2
Electrical | Electrical - Luminaire | each | 5 | 10
Electrical | Electrical - Mast Arm Assembly & Pole | each | 2 | 4
Electrical | Electrical - Raceway for Magnetic Detectors | foot | 100 | 200
Electrical | Electrical - Relocate Existing Traffic Signal Posts | each | 2 | 4
Electrical | Electrical - Service Installation | each | 0.5 | 1
Electrical | Electrical - Signal Head | each | 5 | 10
Electrical | Electrical - Signal Post (wood or metal) | each | 4 | 8
Electrical | Electrical - Trench & Backfill | foot | 75 | 350
Electrical | Electrical - Unit Duct | foot | 550 | 700
Electrical | Electrical - Unit Duct/without Cable | foot | 150 | 350
Landscape | Landscape - Evergreens | each | 20 | 40
Landscape | Landscape - Excelsior Blanket | square yard | 1000 | 4000
Landscape | Landscape - Intermediate Trees | each | 20 | 40
Landscape | Landscape - Seeding | acre | 5 | 10
Landscape | Landscape - Seedling Trees | each | 2000 | 3000
Landscape | Landscape - Shade Trees | each | 20 | 40
Landscape | Landscape - Shrubs | each | 200 | 400
Landscape | Landscape - Sodding | square yard | 1000 | 1500
Landscape | Landscape - Straw Mulch | ton | 10 | 20
Landscape | Landscape - Vines | each | 1000 | 2000
Landscape | Landscape - Weed Control Spraying | acre | 50 | 100
Roadway | Aggregate - Granular Backfill | cubic yard | 300 | 600
Roadway | Aggregate - Granular Embankment Special | ton | 800 | 1500
Roadway | Aggregate - Gravel or Crushed Stone Base Course | ton | 700 | 1200
Roadway | Aggregate - Gravel or Crushed Stone Shoulders | ton | 500 | 1200
Roadway | Aggregate - Gravel or Crushed Stone Surface Course | ton | 700 | 1200
Roadway | Aggregate - Porous Granular Embankment | cubic yard | 400 | 1000
Roadway | Aggregate - Subbase Granular Materials | ton | 700 | 2000
Roadway | Drainage - Adjust Frames & Grates | each | 5 | 10
Roadway | Drainage - Catch Basins | each | 2 | 5
Roadway | Drainage - Concrete Box Culverts | cubic yard | 8 | 15
Roadway | Drainage - Concrete Headwalls | cubic yard | 3 | 8
Roadway | Drainage - Concrete Gutter | foot | 400 | 1400
Roadway | Drainage - Curb & Gutter | foot | 300 | 1200
Roadway | Drainage - End Sections (Pipe Culvert & Storm Sewer) | each | 5 | 10
Roadway | Drainage - Inlets | each | 2 | 5
Roadway | Drainage - Manholes | each | 2 | 4
Roadway | Drainage - Paved Ditch | foot | 200 | 400
Roadway | Drainage - Pipe Culverts (Depending on size and depth) | foot | 100 | 300
Roadway | Drainage - Pipe Underdrains | foot | 1500 | 7500
Roadway | Drainage - Precast Box Culverts | foot | 75 | 250
Roadway | Drainage - Reinforcement Bars (Culverts) | pound | 3000 | 5000
Roadway | Drainage - Riprap | square yard | 100 | 200
Roadway | Drainage - Storm Sewers (Dependent on size and depth) | foot | 75 | 300
Roadway | Drainage - Trench Backfill | cubic yard | 100 | 200
Roadway | Drainage - Exploration Trench | foot | 250 | 1000
Roadway | Excavation - Embankment | cubic yard | 500 | 10000
Roadway | Excavation - Borrow Excavation | cubic yard | 1000 | 10000
Roadway | Excavation - Channel Excavation | cubic yard | 200 | 500
Roadway | Excavation - Earth Excavation (Shoulders & Widening) | cubic yard | 500 | 1000
Roadway | Excavation - Earth Excavation | cubic yard | 750 | 10000
Roadway | Excavation - Rock Excavation (Ripping or Blasting) | cubic yard | 500 | 2000
Roadway | Excavation - Excavation (Special) | cubic yard | 500 | 1000
Roadway | Excavation - Excavation (Topsoil) | cubic yard | 500 | 1000
Roadway | Excavation - Grading and Shaping Roadway | unit | 10 | 50
Roadway | Excavation - Process Lime Modified Soil | square yard | 2000 | 6500
Roadway | Excavation - Process Lime Stabilized Soil | square yard | 2000 | 6500
Roadway | Excavation - Topsoil Placement | square yard | 5000 | 25000
Roadway | Miscellaneous - Chain Link Fence | foot | 300 | 500
Roadway | Miscellaneous - Concrete Barrier | foot | 200 | 400
Roadway | Miscellaneous - Delineators | each | 75 | 150
Roadway | Miscellaneous - Furnishing and Erecting Row Markers | each | 10 | 30
Roadway | Miscellaneous - Noise Abatement Wall | square foot | 800 | 1000
Roadway | Miscellaneous - Steel Plate Beam Guardrail | foot | 300 | 600
Roadway | Miscellaneous - Steel Plate Beam Guardrail Removal | foot | 500 | 800
Roadway | Miscellaneous - Temporary Concrete Barrier Wall | foot | 500 | 1500
Roadway | Miscellaneous - Woven Wire Fence | foot | 500 | 1000
Roadway | Paving - Pavement Rem/Rep Reinforced Concrete | square yard | 50 | 100
Roadway | Paving - Pavement Rem/Rep Concrete w/Dowel Bars | square yard | 50 | 100
Roadway | Paving - Pavement Rem/Rep Concrete or Asphalt | square yard | 100 | 150
Roadway | Paving - Partial Depth Patches | square yard | 200 | 400
Roadway | Paving - Bituminous Concrete Base Course Widening | square yard | 500 | 2000
Roadway | Paving - Bituminous Concrete Binder & Surface Course | ton | 500 | 1600
Roadway | Paving - Bituminous Materials | gallon | 3000 | 10000
Roadway | Paving - Bituminous Pavement Removal & Replacement | square yard | 50 | 100
Roadway | Paving - Bituminous Shoulders | square yard | 1500 | 4500
Roadway | Paving - Bridge Approach Pavement | square yard | 50 | 100
Roadway | Paving - Continuously Reinforced Concrete Pavement | square yard | 2000 | 7000
Roadway | Paving - Bituminous Concrete Pavement (Full depth) | square yard | 1000 | 3500
Roadway | Paving - Bituminous Concrete Surface Removal (1.5 in) | square yard | 10000 | 60000
Roadway | Paving - Cracking and Sealing Pavement | square yard | 5000 | 15000
Roadway | Paving - Level Binder | ton | 50 | 1600
Roadway | Paving - Median Surface (Concrete) | square foot | 750 | 2000
Roadway | Paving - Micro-Surfacing/Lane | mile | 1 | 3
Roadway | Paving - Pavement Fabric | square yard | 1200 | 6000
Roadway | Paving - Pavement Reinforcement | square yard | 1500 | 5000
Roadway | Paving - PC Concrete Base Course | square yard | 1500 | 6000
Roadway | Paving - PC Concrete Base Course Widening | square yard | 750 | 2500
Roadway | Paving - PC Concrete Driveways | square yard | 100 | 150
Roadway | Paving - PC Concrete Pavement | square yard | 1500 | 6000
Roadway | Paving - PC Concrete Pavement (Hinge Joint) | square foot | 1500 | 6000
Roadway | Paving - PC Concrete Sidewalks | square yard | 1000 | 1500
Roadway | Paving - PCC Shoulders | square yard | 1200 | 6000
Roadway | Paving - Protective Coat | square yard | 3000 | 7000
Roadway | Paving - Stabilized Subbase 4 | square yard | 3000 | 10000
Roadway | Paving - Strip Reflective Crack Control | foot | 10000 | 20000
Roadway | Pvt Mk - Paint Pavement Marking (Hand) | foot | 500 | 1000
Roadway | Pvt Mk - Paint Pavement Marking (Truck) | foot | 10000 | 20000
Roadway | Pvt Mk - Raised Reflective Pavement Markers | each | 100 | 200
Roadway | Pvt Mk - Thermoplastic Pavement Marking Symbol | square foot | 450 | 900
Roadway | Pvt Mk - Thermoplastic Pavement Marking (Hand) | foot | 500 | 1000
Roadway | Pvt Mk - Thermoplastic Pavement Marking (Truck) | foot | 60000 | 180000
Roadway | Removal - Bituminous Surface Removal | square yard | 2000 | 10000
Roadway | Removal - Curb & Gutter Removal | foot | 600 | 1400
Roadway | Removal - Pavement Grinding | square yard | 1000 | 2000
Roadway | Removal - Pavement Removal | square yard | 1000 | 2000
Roadway | Removal - Sidewalk Removal | square foot | 1500 | 2500
Roadway | Removal - Tree Removal | acre | 2 | 4
Roadway | Removal - Tree Removal (6 to 15 Units Diameter) | units | 150 | 400
Roadway | Removal - Tree Removal (Over 15 Units Diameter) | units | 100 | 300
Signing | Signing - Metal Post | foot | 250 | 400
Signing | Signing - Overhead Sign Foundation | cubic yard | 5 | 16
Signing | Signing - Overhead Sign Structure | foot | 25 | 50
Signing | Signing - Sign Panel | square foot | 500 | 2000
Signing | Signing - Structural Steel Sign Support Non-Breakaway | pound | 1000 | 15000

## Monthly Data
Data for Each Month
January 2012 to Aug 2025
MONTH/YEAR | CALENDAR DAYS PER MONTH | SATURDAYS | SUNDAYS | HOLIDAYS | WEATHER DAYS | WORK DAYS PER MONTH (NO WEATHER) | WORK DAYS PER MONTH (WEATHER)
2012-01-01 | 31 | 4 | 5 | 1 | 8 | 21 | 13
2012-02-01 | 29 | 4 | 4 | 0 | 8 | 21 | 13
2012-03-01 | 31 | 5 | 4 | 0 | 7 | 22 | 15
2012-04-01 | 30 | 4 | 5 | 0 | 6 | 21 | 15
2012-05-01 | 31 | 4 | 4 | 1 | 5 | 22 | 17
2012-06-01 | 30 | 5 | 4 | 0 | 5 | 21 | 16
2012-07-01 | 31 | 4 | 5 | 1 | 4 | 21 | 17
2012-08-01 | 31 | 4 | 4 | 0 | 4 | 23 | 19
2012-09-01 | 30 | 5 | 5 | 1 | 5 | 19 | 14
2012-10-01 | 31 | 4 | 4 | 0 | 6 | 23 | 17
2012-11-01 | 30 | 4 | 4 | 1 | 6 | 21 | 15
2012-12-01 | 31 | 5 | 5 | 1 | 6 | 20 | 14
2013-01-01 | 31 | 4 | 4 | 1 | 8 | 22 | 14
2013-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2013-03-01 | 31 | 5 | 5 | 0 | 7 | 21 | 14
2013-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2013-05-01 | 31 | 4 | 4 | 1 | 5 | 22 | 17
2013-06-01 | 30 | 5 | 5 | 0 | 5 | 20 | 15
2013-07-01 | 31 | 4 | 4 | 1 | 4 | 22 | 18
2013-08-01 | 31 | 5 | 4 | 0 | 4 | 22 | 18
2013-09-01 | 30 | 4 | 5 | 1 | 5 | 20 | 15
2013-10-01 | 31 | 4 | 4 | 0 | 6 | 23 | 17
2013-11-01 | 30 | 5 | 4 | 1 | 6 | 20 | 14
2013-12-01 | 31 | 4 | 5 | 1 | 6 | 21 | 15
2014-01-01 | 31 | 4 | 4 | 1 | 8 | 22 | 14
2014-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2014-03-01 | 31 | 5 | 5 | 0 | 7 | 21 | 14
2014-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2014-05-01 | 31 | 5 | 4 | 1 | 5 | 21 | 16
2014-06-01 | 30 | 4 | 5 | 0 | 5 | 21 | 16
2014-07-01 | 31 | 4 | 4 | 1 | 4 | 22 | 18
2014-08-01 | 31 | 5 | 5 | 0 | 4 | 21 | 17
2014-09-01 | 30 | 4 | 4 | 1 | 5 | 21 | 16
2014-10-01 | 31 | 4 | 4 | 0 | 6 | 23 | 17
2014-11-01 | 30 | 5 | 5 | 1 | 6 | 19 | 13
2014-12-01 | 31 | 4 | 4 | 1 | 6 | 22 | 16
2015-01-01 | 31 | 5 | 4 | 1 | 8 | 21 | 13
2015-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2015-03-01 | 31 | 4 | 5 | 0 | 7 | 22 | 15
2015-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2015-05-01 | 31 | 5 | 5 | 1 | 5 | 20 | 15
2015-06-01 | 30 | 4 | 4 | 0 | 5 | 22 | 17
2015-07-01 | 31 | 4 | 4 | 1 | 4 | 22 | 18
2015-08-01 | 31 | 5 | 5 | 0 | 4 | 21 | 17
2015-09-01 | 30 | 4 | 4 | 1 | 5 | 21 | 16
2015-10-01 | 31 | 5 | 4 | 0 | 6 | 22 | 16
2015-11-01 | 30 | 4 | 5 | 1 | 6 | 20 | 14
2015-12-01 | 31 | 4 | 4 | 1 | 6 | 22 | 16
2016-01-01 | 31 | 5 | 5 | 1 | 8 | 20 | 12
2016-02-01 | 29 | 4 | 4 | 0 | 8 | 21 | 13
2016-03-01 | 31 | 4 | 4 | 0 | 7 | 23 | 16
2016-04-01 | 30 | 5 | 4 | 0 | 6 | 21 | 15
2016-05-01 | 31 | 4 | 5 | 1 | 5 | 21 | 16
2016-06-01 | 30 | 4 | 4 | 0 | 5 | 22 | 17
2016-07-01 | 31 | 5 | 5 | 1 | 4 | 20 | 16
2016-08-01 | 31 | 4 | 4 | 0 | 4 | 23 | 19
2016-09-01 | 30 | 4 | 4 | 1 | 5 | 21 | 16
2016-10-01 | 31 | 5 | 5 | 0 | 6 | 21 | 15
2016-11-01 | 30 | 4 | 4 | 1 | 6 | 21 | 15
2016-12-01 | 31 | 5 | 4 | 1 | 6 | 21 | 15
2017-01-01 | 31 | 4 | 5 | 1 | 8 | 21 | 13
2017-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2017-03-01 | 31 | 4 | 4 | 0 | 7 | 23 | 16
2017-04-01 | 30 | 5 | 5 | 0 | 6 | 20 | 14
2017-05-01 | 31 | 4 | 4 | 1 | 5 | 22 | 17
2017-06-01 | 30 | 4 | 4 | 0 | 5 | 22 | 17
2017-07-01 | 31 | 5 | 5 | 1 | 4 | 20 | 16
2017-08-01 | 31 | 4 | 4 | 0 | 4 | 23 | 19
2017-09-01 | 30 | 5 | 4 | 1 | 5 | 20 | 15
2017-10-01 | 31 | 4 | 5 | 0 | 6 | 22 | 16
2017-11-01 | 30 | 4 | 4 | 1 | 6 | 21 | 15
2017-12-01 | 31 | 5 | 5 | 1 | 6 | 20 | 14
2018-01-01 | 31 | 4 | 4 | 1 | 8 | 22 | 14
2018-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2018-03-01 | 31 | 5 | 4 | 0 | 7 | 22 | 15
2018-04-01 | 30 | 4 | 5 | 0 | 6 | 21 | 15
2018-05-01 | 31 | 4 | 4 | 1 | 5 | 22 | 17
2018-06-01 | 30 | 5 | 4 | 0 | 5 | 21 | 16
2018-07-01 | 31 | 4 | 5 | 1 | 4 | 21 | 17
2018-08-01 | 31 | 4 | 4 | 0 | 4 | 23 | 19
2018-09-01 | 30 | 5 | 5 | 1 | 5 | 19 | 14
2018-10-01 | 31 | 4 | 4 | 0 | 6 | 23 | 17
2018-11-01 | 30 | 4 | 4 | 1 | 6 | 21 | 15
2018-12-01 | 31 | 5 | 5 | 1 | 6 | 20 | 14
2019-01-01 | 31 | 4 | 4 | 1 | 8 | 22 | 14
2019-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2019-03-01 | 31 | 5 | 5 | 0 | 7 | 21 | 14
2019-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2019-05-01 | 31 | 4 | 4 | 1 | 5 | 22 | 17
2019-06-01 | 30 | 5 | 5 | 0 | 5 | 20 | 15
2019-07-01 | 31 | 4 | 4 | 1 | 4 | 22 | 18
2019-08-01 | 31 | 5 | 4 | 0 | 4 | 22 | 18
2019-09-01 | 30 | 4 | 5 | 1 | 5 | 20 | 15
2019-10-01 | 31 | 4 | 4 | 0 | 6 | 23 | 17
2019-11-01 | 30 | 5 | 4 | 1 | 6 | 20 | 14
2019-12-01 | 31 | 4 | 5 | 1 | 6 | 21 | 15
2020-01-01 | 31 | 4 | 4 | 1 | 8 | 22 | 14
2020-02-01 | 29 | 5 | 4 | 0 | 8 | 20 | 12
2020-03-01 | 31 | 4 | 5 | 0 | 7 | 22 | 15
2020-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2020-05-01 | 31 | 5 | 5 | 1 | 5 | 20 | 15
2020-06-01 | 30 | 4 | 4 | 0 | 5 | 22 | 17
2020-07-01 | 31 | 4 | 4 | 1 | 4 | 22 | 18
2020-08-01 | 31 | 5 | 5 | 0 | 4 | 21 | 17
2020-09-01 | 30 | 4 | 4 | 1 | 5 | 21 | 16
2020-10-01 | 31 | 5 | 4 | 0 | 6 | 22 | 16
2020-11-01 | 30 | 4 | 5 | 1 | 6 | 20 | 14
2020-12-01 | 31 | 4 | 4 | 1 | 6 | 22 | 16
2021-01-01 | 31 | 5 | 5 | 1 | 8 | 20 | 12
2021-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2021-03-01 | 31 | 4 | 4 | 0 | 7 | 23 | 16
2021-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2021-05-01 | 31 | 5 | 5 | 1 | 5 | 20 | 15
2021-06-01 | 30 | 4 | 4 | 0 | 5 | 22 | 17
2021-07-01 | 31 | 5 | 4 | 1 | 4 | 21 | 17
2021-08-01 | 31 | 4 | 5 | 0 | 4 | 22 | 18
2021-09-01 | 30 | 4 | 4 | 1 | 5 | 21 | 16
2021-10-01 | 31 | 5 | 5 | 0 | 6 | 21 | 15
2021-11-01 | 30 | 4 | 4 | 1 | 6 | 21 | 15
2021-12-01 | 31 | 4 | 4 | 1 | 6 | 22 | 16
2022-01-01 | 31 | 5 | 5 | 1 | 8 | 20 | 12
2022-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2022-03-01 | 31 | 4 | 4 | 0 | 7 | 23 | 16
2022-04-01 | 30 | 5 | 4 | 0 | 6 | 21 | 15
2022-05-01 | 31 | 4 | 5 | 1 | 5 | 21 | 16
2022-06-01 | 30 | 4 | 4 | 0 | 5 | 22 | 17
2022-07-01 | 31 | 5 | 5 | 1 | 4 | 20 | 16
2022-08-01 | 31 | 4 | 4 | 0 | 4 | 23 | 19
2022-09-01 | 30 | 4 | 4 | 1 | 5 | 21 | 16
2022-10-01 | 31 | 5 | 5 | 0 | 6 | 21 | 15
2022-11-01 | 30 | 4 | 4 | 1 | 6 | 21 | 15
2022-12-01 | 31 | 5 | 4 | 1 | 6 | 21 | 15
2023-01-01 | 31 | 4 | 5 | 1 | 8 | 21 | 13
2023-02-01 | 28 | 4 | 4 | 0 | 8 | 20 | 12
2023-03-01 | 31 | 4 | 4 | 0 | 7 | 23 | 16
2023-04-01 | 30 | 5 | 5 | 0 | 6 | 20 | 14
2023-05-01 | 31 | 4 | 4 | 1 | 5 | 22 | 17
2023-06-01 | 30 | 4 | 4 | 0 | 5 | 22 | 17
2023-07-01 | 31 | 5 | 5 | 1 | 4 | 20 | 16
2023-08-01 | 31 | 4 | 4 | 0 | 4 | 23 | 19
2023-09-01 | 30 | 5 | 4 | 1 | 5 | 20 | 15
2023-10-01 | 31 | 4 | 5 | 0 | 6 | 22 | 16
2023-11-01 | 30 | 4 | 4 | 1 | 6 | 21 | 15
2023-12-01 | 31 | 5 | 5 | 1 | 6 | 20 | 14
2024-01-01 | 31 | 4 | 4 | 1 | 8 | 22 | 14
2024-02-01 | 29 | 4 | 4 | 0 | 8 | 21 | 13
2024-03-01 | 31 | 5 | 5 | 0 | 7 | 21 | 14
2024-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2024-05-01 | 31 | 4 | 4 | 1 | 5 | 22 | 17
2024-06-01 | 30 | 5 | 5 | 0 | 5 | 20 | 15
2024-07-01 | 31 | 4 | 4 | 1 | 4 | 22 | 18
2024-08-01 | 31 | 5 | 4 | 0 | 4 | 22 | 18
2024-09-01 | 30 | 4 | 5 | 1 | 5 | 20 | 15
2024-10-01 | 31 | 4 | 4 | 0 | 6 | 23 | 17
2024-11-01 | 30 | 5 | 4 | 1 | 6 | 20 | 14
2024-12-01 | 31 | 4 | 5 | 1 | 6 | 21 | 15
2025-01-01 | 31 | 4 | 4 | 1 | 8 | 22 | 14
2025-02-01 | 29 | 4 | 4 | 0 | 8 | 21 | 13
2025-03-01 | 31 | 5 | 5 | 0 | 7 | 21 | 14
2025-04-01 | 30 | 4 | 4 | 0 | 6 | 22 | 16
2025-05-01 | 31 | 5 | 4 | 1 | 5 | 21 | 16
2025-06-01 | 30 | 4 | 5 | 0 | 5 | 21 | 16
2025-07-01 | 31 | 4 | 4 | 1 | 4 | 22 | 18
2025-08-01 | 31 | 5 | 5 | 0 | 4 | 21 | 17

## Completion Date
ENTER TOTAL WORKING DAYS
ENTER MONTH START | CUMMULATIVE WORK DAYS (WITH WEATHER DAYS) | CUMMULATIVE CALANDER DAYS (WITH WEATHER DAYS)
2012-08-01 | 19 | 31 |  | PROJECTED FINISH MONTH (+ 10% working days)
2012-09-01 12:14 | 33 | 61
2012-10-03 00:29 | 50 | 92
2012-11-03 12:43 | 65 | 122 | Weather Sensitive Months and Work Types
2012-12-05 00:58 | 79 | 153 | November | asphalt (polymer modified)
2013-01-05 13:12 | 93 | 184 | December | asphalt, traffic markings, concrete sealing, bridge painting
2013-02-06 01:26 | 105 | 212 | January | asphalt, concrete pavement, earthwork, traffic markings, concrete sealing, bridge painting
2013-03-09 13:41 | 119 | 243 | February | asphalt, concrete pavement, earthwork, traffic markings, concrete sealing, bridge painting
2013-04-10 01:55 | 135 | 273 | March | asphalt, concrete pavement,traffic markings, concrete sealing, bridge painting
2013-05-11 14:10 | 152 | 304 | April | asphalt, traffic markings, concrete sealing, bridge painting
2013-06-12 02:24 | 167 | 334
2013-07-13 14:38 | 185 | 365 | Work Types during these months will push completion date
2013-08-14 02:53 | 203 | 396
2013-09-14 15:07 | 218 | 426
2013-10-16 03:22 | 235 | 457 | Incidental Work
2013-11-16 15:36 | 249 | 487 | Add one month for projects that contain significant incidental work not entered into bar chart
2013-12-18 03:50 | 264 | 518
2014-01-18 16:05 | 278 | 549
2014-02-19 04:19 | 290 | 577
2014-03-22 16:34 | 304 | 608
2014-04-23 04:48 | 320 | 638
2014-05-24 17:02 | 336 | 669
2014-06-25 05:17 | 352 | 699
2014-07-26 17:31 | 370 | 730
2014-08-27 05:46 | 387 | 761
2014-09-27 18:00 | 403 | 791
2014-10-29 06:14 | 420 | 822
2014-11-29 18:29 | 433 | 852
2014-12-31 06:43 | 449 | 883
2015-01-31 18:58 | 462 | 914