## No Lanes Closed
Work Zone User cost calculations
2010-04-29
Project Number:
CRS:
No lane closure cost calculation procedure
|  | Passenger Car | B/C Truck
| Cost per hour: | 19.22 | 51.88
| Length of Work zone in miles: | 4.2 | 4.2
| Free flow speed (normal 85% speed) in mph: | 72 | 72
| Work zone speed (85%) in mph: | 62 | 62
| Average AADT of full section: | 45000 | 15000
| Duration of Closure in days | 300 | 300
Calculated values:
| Travel time in free flow (secs): | 210 | 210
| Travel Time in work zone (secs): | 243.871 | 243.871
| Delay (secs): | 33.871 | 33.871
| Delay (hours): | 0.0094086 | 0.0094086
| Cost per Vehicle: | 0.18083 | 0.48812
| Cost per day per closure: | 8137.5 | 7321.7742
| Total Cost for closure duration: | 2441250 | 2196532.2581
| Total Cost for all vehicles: | 4637782.2581
| Average cost per day | 15459.2742
The Average cost per day is the MAXIMUM that may be used as incentive / disincentive
Spreadsheet protection password: CONSTRUCTION
See Contact Reynaldo Stargell in the Office of Traffic Engineering for the latest adjustment factor based on the CPI : ftp://ftp.bls.gov/pub/special.requests/cpi/cpiai.txt

## Detour (using distance & speed)
Work Zone User cost calculations
2010-04-29
Project Number:
CRS:
Detour cost calculation procedure
|  | Passenger Car | B/C Truck
| Cost per hour: | 19.22 | 51.88
| Length of work zone in miles: | 4.2 | 4.2
| Length of Detour in miles: | 12.3 | 12.3
| Free flow speed (normal 85% speed) in mph: | 72 | 72
| Detour zone speed (85%) in mph: | 52 | 52
| Average AADT of full section: | 500 | 20
| Duration of Closure in days | 20 | 20
Calculated values:
| Travel time in free flow (secs): | 210 | 210
| Travel Time in detour (secs): | 851.5385 | 851.5385
| Delay (secs): | 641.5385 | 641.5385
| Delay (hours): | 0.17821 | 0.17821
| Cost per Vehicle: | 3.4251 | 9.2453
| Cost per day per closure: | 1712.5513 | 184.9056
| Total Cost for closure duration: | 34251.0256 | 3698.1128
| Total Cost for all vehicles: | 37949.1385
| Average cost per day | 1897.4569
The Average cost per day is the MAXIMUM that may be used as incentive / disincentive
Spreadsheet protection password: CONSTRUCTION
See Contact Reynaldo Stargell in the Office of Traffic Engineering for the latest adjustment factor based on the CPI : ftp://ftp.bls.gov/pub/special.requests/cpi/cpiai.txt

## Detour (using time driven)
Work Zone User cost calculations
2010-04-29
Project Number:
CRS:
Detour cost calculation procedure
|  | Passenger Car | B/C Truck
| Cost per hour: | 19.22 | 51.88
| Time to drive existing route at free-flow speed in minutes: | 4 | 4
| Time to drive detour route in minutes: | 15 | 15
| Average AADT of full section: | 500 | 20
| Duration of Closure in days | 20 | 20
Calculated values:
| Delay (minutes): | 11 | 11
| Delay (hours): | 0.18333 | 0.18333
| Cost per Vehicle: | 3.5237 | 9.5113
| Cost per day per closure: | 1761.8333 | 190.2267
| Total Cost for closure duration: | 35236.6667 | 3804.5333
| Total Cost for all vehicles: | 39041.2
| Average cost per day | 1952.06
The Average cost per day is the MAXIMUM that may be used as incentive / disincentive
Spreadsheet protection password: CONSTRUCTION
See Contact Reynaldo Stargell in the Office of Traffic Engineering for the latest adjustment factor based on the CPI : ftp://ftp.bls.gov/pub/special.requests/cpi/cpiai.txt