Ohio Department of Transportation

Office of Construction Management

Time Extension Policy and Standard Procedure

Quality Assurance Review

(QAR)

MONITORING PLAN

CY2007

Ohio Department of Transportation – Office of Construction Management

QAR Monitoring Plan

QAR Category

Change Order Policy and Standard Procedure

Criteria

1.  CFR 635

2.  Ohio Revised Code Section 5514

3.  Construction & Material Specification Sections 108.06, 108.07

4.  Standard Procedure 519-012(SP) and Policy 27-012(P)

Review Method

1.  Interview with District Construction Engineer and Project Engineer

2.  Document Review

Frequency

All Districts will be reviewed every other year

Follow Up Method

Written status report from district and/or phone call or visit

QAR Team

Team Leader:

Clint Bishop, Office of Construction Management

CY 2007 QAR Schedule

| District | QAR Scheduling Deadline | Date of QAR Visit | Report Issue Deadline |
| --- | --- | --- | --- |
| 1 | 3/19/2007 | 4/2/2002 | 4/16/2007 |
| 2 | 4/2/2007 | 4/16/2007 | 4/30/2007 |
| 3 | 4/16/2007 | 4/30/2007 | 5/14/2007 |
| 4 | 4/30/2007 | 5/14/2007 | 5/29/2007 |
| 5 | 5/21/2007 | 6/4/2007 | 6/18/2007 |
| 6 | 6/4/2007 | 6/18/2007 | 7/2/2007 |
| 7 | 6/18/2007 | 7/2/2007 | 7/16/2007 |
| 8 | 7/2/2007 | 7/16/2007 | 7/30/2007 |
| 9 | 7/23/2007 | 8/6/2007 | 8/20/2007 |
| 10 | 8/6/2007 | 8/20/2007 | 9/4/2007 |
| 11 | 8/27/2007 | 9/10/2007 | 9/24/2007 |
| 12 | 9/10/2007 | 9/24/2007 | 10/9/2007 |

The Office of Construction Management conducts one QAR per District per calendar year.

Ohio Department of Transportation

Office of Construction Management

Time Extension Policy and Standard Procedure

QAR Checklists

CY2007

QAR

Time Extension Policy and Standard Procedure

District:				Contractor:						Date:

Project:				Project Engineer:					C/R/S:

Preparation and Approval of a Time Extension:

Request for a postponement of a contract completion date is received from the Contractor.

The District evaluated and processed the request within 30 days.

A review of the request for time extension from the Contractor was made to determine if the time 	extension is justified.

Non CPM Schedule Project

    - Contractor Requested _____ days

    - District completes Form C-122 if time extension is justified

    - Reason Code(s) on Form C-122

    - Explanation(s) on Form C-122 ________________________________________________________________________________________________________________________________________________________________________________________________________________________

________________________________________________________________________

CPM Schedule Project

    - Contractor Requested _____ days

    - District used CPM Progress Schedule to evaluate request

    - District completes Form C-122 if time extension is justified

    - Reason Code(s) on Form C-122

    - Explanation(s) on Form C-122 ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Form C-122:

Work Day time extension converted to Calendar Day time extension (if applicable)

Contract Time Extension Completion Date ________________________________

District Signature and Date on Time Extension

Approval entered into CMS on the “LIQID” screen by District

District furnished approved Form C-122 to Contractor

District furnished approved Form to FHWA (if project has Federal oversight)

Records Retention – see attached Records Retention Schedule applicable to Change Orders

Yes	 No	Does the office utilize the attached records retention schedule?

Yes	 No	Are any record retention schedules or procedures are being followed other than or in 					addition to the approved records retention schedules

Attachment A

Department of Administrative Services

State of Ohio Records Management

Records Retention Schedule

Department of Transportation

Construction Management

Construction Administration

Project Record Series

| Series Authorization No: 770-1764 | Agency: DOT | Division: 0027 | Section: 0519 | Revision: 0 |
| --- | --- | --- | --- | --- |
| Agency Series No.: CA-01 | Record Series Title: Project Record Series |
| Record Series Description: This includes all records and reports compiled during the course of a construction project. This series includes, but not limited to: contract, project proposal, general correspondence, test lab reports, construction plans, field measurements. Forms: Estimates-CMS generated, Daily Diaries, change orders, payroll correspondence, earthwork drawings, cross-section calculations, survey notes, aerial engineering data, pile test load reports, tickets, EEO reports and records, computation sheets, railroad invoice transmittals, affidavit as to non-spec material, piling records, extra work contract estimates, final report, request to sublet, progress schedule and supplement, daily construction record bituminous concrete pavement, change order flow record, recommendation for postponement of contract completion date, request to waive liquidated damages, request for additional i-encumbrance, report of compaction, in-place density using nuclear method, validation of final pay quantities, field note sheet, compliance data reports. |

Agency Web Link: http://www.dot.state.oh.us

| Confidential Description | Vital Description |
| --- | --- |
|  | Documents to be retained for future reference on construction projects as determined by ODOT Chief Legal Counsel and FHWA. For projects that have warranty items, all records shall be maintained in-house until warranty period has expired. |  |  |
| Media | Retention Period | Retention Justification | Method of Disposal |
| Paper | retain paper documents for a period of three years after submission of final voucher, then Microfilm. Destroy paper documents after microfilm has been checked for quality and completeness. |  | Recycle |
| Micro-film | Retain microfilm until determined to be obsolete or for the life of the completed construction project. | Microfilm needs to be retained for future reference on construction projects as determined by ODOT''s Chief Legal Counsel and FHWA. NOTE: Projects that have warranty items shall be maintained in-house until warranty period has expired. | Recycle |

| Approvals: |
| --- |
| Created |  | Date: 6/27/2005 |
| Approved | Christina Hines, Records Coordinator | Date: 6/27/2005 |
| Approved | Dwight Neely, Records Officer | Date: 6/27/2005 |
| Approved | Michael Hardenbrook, Record Administrator | Date: 7/6/2005 |
| Approved | Martin Meeks, State Auditor | Date: 7/7/2005 |
| Approved | Steve Gutgesell, State Archivist | Date: 7/14/2005 |
| Notes: |  |  |
| Note Date | Note Description | User |