Ohio Department of Transportation

Division of Construction Management

Change Order Policy and Standard Procedure

Quality Assurance Review

(QAR)

MONITORING PLAN

CY2008

Ohio Department of Transportation – Division of Construction Management

QAR Monitoring Plan

QAR Category

Change Order Policy and Standard Procedure

Criteria

1.  23 CFR 635

2.  Ohio Revised Code Section 126.30, 127.16, 5517.20, 5525.11, 5525.14 and 5525.99

3.  Construction & Material Specification Sections 109.04, 109.05

4.  Interim Standard Procedure 510-010(SP) and Policy 27-010(P)

Monitoring Method

Select at least one Project(s) selected for size, Federal participation, and 50 to 95% complete

Review Method

1.  Interview with District Construction Engineer and Project Engineer

2.  Document Review

Frequency

All Districts will be reviewed every year

Follow Up Method

Written status report from district and/or phone call or visit

QAR Team

Team Leader:

Clint Bishop, Division of Construction Management

CY 2008 QAR Schedule

| District | QAR Scheduling Deadline | Date of QAR Visit | Report Issue Deadline |
| --- | --- | --- | --- |
| 1 | 3/24/2008 | 4/7/2008 | 4/21/2008 |
| 2 | 4/7/2006 | 4/21/2008 | 5/5/2008 |
| 3 | 4/21/2008 | 5/5/2008 | 5/19/2008 |
| 4 | 5/5/2008 | 5/19/2008 | 6/2/2008 |
| 5 | 5/29/2008 | 6/9/2008 | 6/23/2008 |
| 6 | 6/9/2008 | 6/23/2008 | 7/7/2008 |
| 7 | 6/23/2008 | 7/7/2008 | 7/21/2008 |
| 8 | 7/10/2008 | 7/21/2008 | 8/4/2008 |
| 9 | 7/21/2008 | 8/4/2008 | 8/18/2008 |
| 10 | 8/4/2008 | 8/18/2008 | 9/8/2008 |
| 11 | 8/18/2008 | 9/8/2008 | 9/22/2008 |
| 12 | 9/8/2008 | 9/22/2008 | 10/6/2008 |

The Division of Construction Management conducts one QAR per District per calendar year.

Ohio Department of Transportation

Division of Construction Management

Change Order Policy and Standard Procedure

QAR Checklists

CY2008

| District: | Date: | C/R/S: |
| --- | --- | --- |
| Project: | Contractor: |
| Change Order: | Contact(s): |

Section #1 Regular Work Change Order

High Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | A RWCO shall only be used for the following: |  | Interview |  |
|  | 1. Contract quantity adjustment |  |  |  |
|  | 2. Adjustment of contract specified payments or deductions |  |  |  |
|  | 3. Changes in contract documents or specifications |  |  |  |
|  | 4. Changes in material requirements |  |  |  |
|  | 5. Revise an interim or contract completion date |  |  |  |
|  | 6. Implement non-performances of a VECP |  |  |  |
|  | 7. Other reasons authorized by Administrative Rulings |  |  |  |

Section #2 Extra Work Change Order

High Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | An EWCO shall only be used for the following: |  | Interview |  |
|  | 1. Increase in contract quantities beyond contract limits |  |  |  |
|  | 2. Addition of new items of work |  |  |  |
|  | 3. Increase in quantities previously established by and EWCO |  |  |  |
|  | 4. Project termination costs |  |  |  |
|  | 5. Force Account |  |  |  |
|  | 6. Implement VECP |  |  |  |
|  | 7. Payments that differ from fixed amounts established in the Proposal |  |  |  |
|  | 8. Final Payment for an item that differs from the lump sum amount bid by the contractor |  |  |  |
|  | 9. Payment for allowable delay costs |  |  |  |
|  | 10. Payment for interest on delays in processing payments |  |  |  |
|  | 11. Compensate the Contractor for damages associated with claims in accordance with the Dispute Resolution and Administrative Claims Process or Ohio Court of Claims |  |  |  |
|  | The EWCO shall include a “Description of Work” and when necessary a “Supplemental Description” |  |  |  |
|  | The EWCO “Explanation of Necessity” shall include, at a minimum, the information required in the Standard Procedure |  |  |  |
|  | All supporting documentation, including complete cost analysis shall be attached to the EWCO on file in the District |  |  |  |

Section #3 Force Account

Medium Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | An EWCO for ECFA shall be processed if the amount of the force account work > $100,000 and duration > two weeks |  | Records Check |  |
|  | ECFA |  |  |  |
|  | 1. All ECFA shall be paid by an EWCO |  |  |  |
|  | 2. The ECFA shall state the estimated costs as determined by a cost analysis or estimate based upon similar bid items according to the C&MS and MOP |  |  |  |
|  | 3. An original affidavit per Standard Procedure shall be attached to the change order by the Contractor |  |  |  |

Section #4 FHWA Consultation and Concurrence

High Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | The District shall consult with FHWA Transportation Engineer when a major change is first contemplated on a Federal Oversight Project: |  | Records Check |  |
|  | 1. This consultation may be by email or by telephone with a follow up email. The results of this consultation shall be documented in the project file and the change order “Explanation of Necessity” |  |  |  |
|  | 2. The email shall have the Project Number, PID and County-Route-Section in the subject line and have adequate information to determine the nature and extent of the proposed change |  |  |  |
|  | FHWA considers a change order to be major if it: |  | Records Check |  |
|  | 1. Project cost > $250,000 or 5% of the award amount |  |  |  |
|  | 2. Alters the planned access controls, highway operations or work limits |  |  |  |
|  | 3. Results in new environmental impacts |  |  |  |

Section #5 Program Manager Consultation and Concurrence

High Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | District Program Manager Change orders on district funded projects must be approved by the appropriate district manager in accordance with processes established by the DDD |  | Records Check |  |
|  | Central Office Program Manager Change orders funded by a Central Office Program must be approved by the Program Manager if the change order amount exceeds the specified threshold for the program |  | Records Check |  |

Section #6 Controlling Board

High Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | An EWCO with a pay item in excess of Contract Limits, regardless of funding source, and not covered by Section VII.B of the procedure, must be submitted to the Controlling Board for approval prior to performance and payment |  | Interview and Records Check |  |
|  | An EWCO shall not be divided into inappropriate pay items or participation codes for the purpose of avoiding Controlling Board review |  |  |  |
|  | The District shall recommend the EWCO, obtain the Program Manager’s signature, and obtain the Contractor’s signature in accordance with Section IX.B of this procedure |  |  |  |
|  | The District shall forward to DCM the signed copy of the EWCO and a draft explanation appropriate for Controlling Board request |  |  |  |
|  | The DCM will process the Controlling Board request and, if approved, send the District the executed Controlling Board approval of the EWCO. This approval shall be attached to the EWCO on file |  |  |  |
|  | An EWCO with a pay item in excess of Contract Limits, regardless of funding source, must be reported to the Controlling Board quarterly in accordance with ORC 5525.14(b), but does not have to be approved by the Controlling Board: |  | Interview and Records Check |  |
|  | 1. An increase of a plan quantity determined during the final measurement |  |  |  |
|  | 2. Added work necessitated by federally mandated requirements |  |  |  |
|  | 3. Added work for which the Director has granted emergency permission |  |  |  |

Section #7 Approval Authority

High Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | All change orders for the extension of an existing contract item of work or for the addition of a new item of work beyond the Contract Limits shall be approved by the Director |  | Interview and Records Check |  |
|  | All change orders for additional work which consist of multiple related items (existing or new) the sum of which exceeds the lesser of $100,000 or 25% of the original contract value shall also be approved by the Director |  |  |  |
|  | The District shall have authority to approve all change orders that do not require approval by the Director as set forth in Section VIII.A of the standard procedure |  |  |  |
|  | Change orders requiring approval by the Director: |  |  |  |
|  | Emergency: The District Construction Office shall obtain declaration of emergency as set forth in Section X.A of the standard procedure |  |  |  |
|  | Emergency: The District Construction Office shall then prepare the change order as set forth in Section IX of this procedure |  |  |  |
|  | Final Measurement: The District Construction Office shall prepare and submit “Request for Estimated Final Measurement Approval” or “Request for Actual Final Measurement Approval” form to the DCM for approval by the Director |  |  |  |
|  | Change orders not emergency or Final Measurement: The District Construction Office shall prepare and submit “Request for Preliminary Change Order Approval” form to DCM for approval by the Director |  |  |  |
|  | The DCE shall have authority to recommend change orders requiring approval by the Director |  |  |  |
|  | Change orders requiring approval by the District: |  | Interview and Records Check |  |
|  | The District shall establish a change order approval process whereby two different signatures are required |  |  |  |
|  | The people selected to sign change orders shall be knowledgeable with this procedure 510-010(SP) and policy 27-010(P) and familiar with the project involved and the circumstances of the proposed change. One signature on the change order shall be from a person within the Construction Department while the other signature shall be from a person not within the Construction Department |  |  |  |
|  | A person will be granted authority to recommend the change order |  |  |  |
|  | A person who is a Professional Engineer registered with the Ohio State Board of Registration for Professional Engineers and Surveyors will be granted approval authority |  |  |  |
|  | Several people may be authorized for each of the two signature levels on a project |  |  |  |

Section #8 Execution and Distribution

Medium Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | In all cases, the District Construction Offices shall coordinate and obtain all necessary approvals (e.g. FHWA, Director, Program Managers, Controlling Board) prior to execution |  | Records Check |  |
|  | A person with recommended authority signs and dates on the “Recommended by” line indicating their title as appropriate. This person shall enter this action into CMS |  |  |  |
|  | The District shall indicate any required Program Manager approval on the change order. If approval is required, the Central Office Program Manager signs and dates on the “Program Manager” line |  |  |  |
|  | The Contractor signs and dates on the “By Contractor” line indicating their title as appropriate. At the discretion of the District, contractor signature can occur before or after signature by the person by the person recommending the change order |  |  |  |
|  | Reservation of Rights The District shall not execute change orders which contain any sort of reservation of rights language included by the Contractor except as set forth in IX.B.3.a.(2) below. |  |  |  |
|  | Under limited circumstances there may be a few instances where it is not feasible for the Contractor and Department to reach full agreement on all the costs and/or time damages arising from a specific circumstance. However, these instances should be rare. In such cases, it is expected that the Contractor notify the Engineer of its specific need, and justification for such need, to reserve its rights to claim specific time or costs at a later date. The Engineer may, only with the approval of the Division of Construction Management, permit a Contractor to reserve its rights. In all cases when a reservation of rights is permitted the details of the reservation of rights shall be documented in the “Explanation of Necessity” section of the change order |  |  |  |
|  | For change orders approved by the Director: The District Construction Office shall then submit the change order to the Division of Construction Management |  | Records Check |  |
|  | The Division of Construction Management will obtain the Director’s signature and notify the District Construction Office of this action by e-mail and return to them the fully executed document |  |  |  |
|  | A person assigned approval authority for District level change orders for the project shall enter this action into CMS |  |  |  |
|  | For change orders approved by the District: A person with approval authority signs their own name as a Professional Engineer with the initials P.E. next to their signature on the “Approved by” line and enters the date. This person shall enter this action into CMS |  | Records Check |  |
|  | Do not approve a RWCO that is for the increase in the quantity of an original bid item to the Contract Limits that is in companion with an EWCO for the further addition of quantities to that same original bid item until the Declaration of Emergency or other preliminary authorization for the EWCO has been granted by the Director |  |  |  |
|  | RWCO’s: District sends the original signed copy of all RWCOs including attached documents to the Office of Accounting for filing with the original contract |  | Records Check |  |
|  | A copy of the signed RWCO shall be kept in the District project file |  |  |  |
|  | Copies of the signed RWCOs shall be distributed to the Contractor and project engineer on all projects |  |  |  |
|  | Copies of all executed RWCOs including backup documentation shall be provided to the FHWA on federal oversight projects |  |  |  |
|  | EWCO’s: District sends the original signed copy of all EWCOs including attached documents to the Office of Accounting for filing with the original contract |  | Records Check |  |
|  | A copy of the signed EWCO shall be kept in the District project file |  |  |  |
|  | Copies of the signed EWCOs shall be distributed to the Contractor and project engineer on all projects |  |  |  |
|  | Copies of all executed EWCOs including backup documentation shall be provided to the FHWA on federal oversight projects |  |  |  |
|  | Copies of signed EWCOs for additions due to Final Measurements and work added due to Federal mandates shall be sent to the Division of Construction Management for inclusion on the quarterly report to the Controlling Board |  |  |  |

Section #9 Emergency Permission

High Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | The Director may grant emergency permission under ORC Section 5525.14, to proceed with added work that exceeds the Contract Limits, prior to processing a change order. |  | Interview and Records Check |  |
|  | This permission shall be in writing and granted to add work that is necessary to eliminate emergency circumstances that would: a. create a life, safety, or health threatening situation, or b. unduly delay the completion of a project and increase its costs |  |  |  |
|  | Added work in these circumstances may include the following: a. construction needed to complete a project, b. adjustments needed to meet changed conditions, c. alterations in original plans, d. unforeseen contingencies, and e. payments necessitated by contract terminations or suspensions |  |  |  |
|  | The declaration of emergency and permission to proceed with work shall be fully documented using only the “Declaration of Emergency and Permission to Proceed with Work” form |  |  |  |
|  | The District Construction Office shall complete the “Declaration of Emergency and Permission to Proceed with Work” form including all Supporting documentation, obtain signature of the DDD and submit to the Division of Construction Management for approval by the Director |  |  |  |
|  | The DCM will obtain the Director’s approval and signature on the “Declaration of Emergency and Permission to Proceed with Work” form, promptly notify the District Construction Office of the Director’s action by e-mail and return to them the fully executed document |  |  |  |
|  | The original signed “Declaration of Emergency and Permission to Proceed with Work” form with supporting documentation shall be kept in the District project file |  |  |  |
|  | Copies of the signed “Declaration of Emergency and Permission to Proceed with Work” form shall be sent to: a. the Contractor, as the Department’s written commitment to pay for the work. The Contractor may proceed with the proposed work, however, it is not legally required to perform the proposed work until the change order is approved, b. the Project Engineer |  |  |  |
|  | Attach a copy of the emergency permission to the subsequent EWCO |  |  |  |
|  | The EWCO shall be designated “Emergency” in CMS |  |  |  |

Section #10 Change Orders for Payment of Claims

Low Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | When such payments exceed the Contract Limits a Controlling Board request and approval are required before payment is made |  | Records Check |  |
|  | Payments for damages associated with claims do not qualify as an emergency |  | Records Check |  |

Section #11 Change Orders for Projects Under Litigation

Medium Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | Change orders on projects under litigation shall be coordinated with the Office of Chief Legal Counsel prior to submitting to the Contractor for signature. Monthly, the Office of Chief Legal Counsel will supply each District with a list of projects that have pending litigation. For each listed project, the District shall inform the Office of Chief Legal Counsel, Court of Claims Section, of the following: |  | Records Check |  |
|  | 1. Pending disputes on each listed project that could result in a change order. |  |  |  |
|  | 2. Change orders currently in process on each listed project |  |  |  |
|  | 3. All change orders approved on each listed project. |  |  |  |

Section #12 Extension of Project Limits

Medium Priority

| Reviewed “(” | Conformance Statement |  | Measurements | Conformance Comments |
| --- | --- | --- | --- | --- |
|  | The DDD may extend project limits on a project under contract for the purpose of adding work outside of the original project only to accomplish the following: |  | Records Check |  |
|  | 1. Complete the project as intended by the original plan or |  |  |  |
|  | 2. Eliminate circumstances arising from the project that would create a life, safety, or health threatening situation |  |  |  |
|  | Procedure: The extension of project limits shall be fully documented on the “Extension of Project Limits” form |  |  |  |
|  | The original signed “Extension of Project Limits” form with supporting documentation shall be kept in the District project file |  |  |  |
|  | A copy of the signed “Extension of Project Limits” form shall be sent to the Project Engineer |  |  |  |

Section #13 Records Retention

Low Priority

| Reviewed “(” | Conformance Statement |  | YES | NO |
| --- | --- | --- | --- | --- |
|  | Does the office utilize the attached records retention schedules? |  |  |  |
|  | Are any records retention schedules or procedures being followed other than or in addition to the approved records retention schedules? |  |  |  |

Attachment A

Department of Administrative Services

State of Ohio Records Management

Records Retention Schedule

Department of Transportation

Construction Management

Construction Administration

Project Record Series

| for Contractors/Vendors | for Government Entities | for State Employees | for the Public Top of Form Bottom of Form |
| --- | --- | --- | --- |

|  | View Schedule |
| --- | --- |
| Return to Welcome Schedule General Schedule List Search Agency/Divison/ Section List Login Help Site Map Search DAS Home State Home Agency Contacts | Series Authorization No: 770-2473 Agency: DOT Division: 0027 Section: 0519 Revision: 1 Agency Series No.: CA-01 Record Series Title: Project Record Series Record Series Description: This includes all records and reports compiled during the course of a construction project. This series includes, but is not limited to: contract, project proposal, general correspondence, test lab reports, construction plans, field measurements. Forms: Estimates-(Construction Management System generated), daily diaries, change orders, payroll correspondence, earthwork drawings, cross section calculations, survey notes, aerial engineering data, pile test load reports, tickets, EEO reports and records, computation sheets, railroad invoice transmittals, affidavit as to non-spec materials, piling records, extra work contract estimates, final report, request to sublet, progress schedule and supplement, daily construction record bituminous concrete pavement, change order flow record, recommendation for postponement of contract completion date, request to waive liquidated damages, request for additional i-encumbrance, report on compaction, in-place density using nuclear method, validation of final pay quantities, field notes, compliance data report. Agency Web Link: http://www.dot.state.oh.us Confidential Description Vital Description Media Retention Period Retention Justification Method of Disposal Paper Retain paper documents for a period of three years after submission of final voucher, then microfilm or scan to CD/DVD. Destroy paper documents after microfilm or CD/DVD has been check for quality and completeness. Recycle Microform Retain microfilm until determined to be obsolete or for the life of the completed construction project. Microfilm or CD/DVD needs to be retained for future reference on construction projects as determined by ODOT's Chief Legal Counsel and the FHWA. NOTE: Projects that have warranty items shall be retained in-house until warranty period has expired. Recycle Machine Readable Retain CD/DVD until determined to be obsolete or for the life of the completed construction project. CD/DVD needs to be retained for future reference on construction projects as determined by ODOT's Chief Legal Counsel and the FHWA. NOTE: Projects that have warranty items shall be retained in-house until warranty period has expired. Recycle Approvals: Created Date: 9/27/2007 Approved Christina Hines, Records Coordinator Date: 9/27/2007 Approved Dwight Neely, Records Officer Date: 9/28/2007 Approved Michael Hardenbrook, Record Administrator Date: 9/28/2007 Approved Martin Meeks, State Auditor Date: 10/1/2007 Approved Steve Gutgesell, State Archivist Date: 10/23/2007 Notes: Note Date Note Description User |

Bottom of Form