## Slide 1: Additive Alternates on ODOT let Projects
-A discussion-
Joe Anthony
Supervisor, Construction Cost Section
Office of Estimating

## Slide 2: New language is being drafted for Additive Alternates on ODOT-let Contracts
Today, a discussion on our progress to date
  Why have Additive alternates
  How they are set up
  How do we award today
  What is our direction for the future
  How does a contractor bid them

## Slide 3: Why Additive Alternates?
All projects must be completely funded
  If bids are over estimate and the owner has no additional money, bids are rejected
Additive alternates afford the owner an opportunity to add additional work to the funded work if the bids come in under (the funded) estimate and/or if the local can produce additional money over the funded amount

## Slide 4: How are Additive Alternates set up?
An additive alternate can be one single item of work or a number of items of work
  If there is more than one item of work in the alternate, all items within that alternate must be performed
Additive alternates are only performed in the order they are bid
  The owner determines the order in which the additive alternates are performed
    There can be no deviation in the order after bids are opened
The total estimated cost of all alternates cannot exceed 25% of the estimated cost of the funded work

## Slide 5: How are we awarding our projects today?
Today on ODOT-let projects the low bidder on the funded work is always the low bidder
If there is one (or more) additive alternates, the low bidder on the funded amount is the only contractor who can perform the additional alternate(s)
This can be problematic for the owner if the “low bidder” bids exorbitantly high (non-competitively) for the alternate(s)

## Slide 6: Considerations for awarding additive alternate projects in the future?
Low bidder for the funded amount identified as the low bidder at bid opening
  Awarded Bidder could change with each additive alternate in the project
Award to the lowest bidder who can perform the funded amount of the project plus most additive alternates the owner has money to fund
The “owner” who contributes additional money to fund the additive alternates will not know who the low bidder for the alternate(s) is until they commit to funding the alternate(s)
Incidental costs of doing additive work should be included in the cost of the alternate items
If the Department determines a bidder is ineligible to be awarded the funded work, the bidder is also ineligible to perform any of the work

## Slide 7: How should a contractor bid Additive Alternate Proposals?
Follow all ODOT rules of bidding
ODOT understands that the cost of an additive alternate may be higher than its cost if it were bid within the funded work
When an owner determines what money may be available to fund additive alternates, they will know the cost of funding each alternate, but not the bidder who would be awarded the project
  This information will be available after the owner determines what alternate(s) they will perform

## Slide 8: Questions?