## Slide 2: Partnering
AGENDA
Partnering Process
Specifications
  108.02: Self-Facilitated Partnering
  Proposal Note 111: Facilitated Partnering
Facilitated Partnering vs DRB / DRA

## Slide 3: Partnering

## Slide 4: Partnering
Misconceptions about Partnering…
“Horse-trading”
Trust Falls & Hand Holding
Sacrifice
Expecting extra work for free
Relaxing specifications
A replacement to the Contract

## Slide 5: Partnering
“Partnering is the formal process of creating a cooperative team by resolving issues in a timely manner. The Partnering Process facilitates an environment that enables all stakeholders to develop a relationship based on communication, trust, and respect.”
- ODOT Partnering Homepage

## Slide 6: Partnering
Partnering is the Process of Preventing Disputes
Collaborative Process
  CMS 108.02 – Self Facilitated Partnering
    Part A: Preconstruction Meeting
    Part B: Initial Partnering Session
    Part C: Progress Meeting
    Part D: Post-Milestone Meetings
    Part E: Partnering Monitoring
    Part F: Mitigation & Notice
Notes: Standard for all Projects
Does not affect terms and conditions of Contract
All costs are incidental to contract
ODOT Project Engineer and Contractor will be the Facilitators

## Slide 7: Partnering
Statewide Partnering Goals
  Safety
  On Time & On Budget
  Timely Issue Resolution
  Respect the Environment
  Partner with Stakeholders
  Trust & Respect
  Mitigation
  Transparency
  Quality
  Open Effective Communication
  Project First Focus
Notes: Standard for all Projects
Does not affect terms and conditions of Contract
All costs are incidental to contract
ODOT Project Engineer and Contractor will be the Facilitators

## Slide 8: Partnering
PN 111 – Facilitated Partnering
Neutral Facilitator
  Who, What, When, Where, & How…
  List of 41 Approved Facilitators
  ODOT Facilitators Standard & Expectation Manual
  Mutually agreed upon by ODOT & Contractor
  Max: $3500 for Initial, $1500 for Re-connects
  Approximately 25 Projects since 2012

## Slide 9: Partnering
PN 111 – Facilitated Partnering
Project Type?
  Project Value
  Funding Sources
  Project Duration
  Project Complexity
  Utility & Railroad Involvement
  Project Location & Visibility
  Public/Stakeholders and their Goals
Notes: Details for consideration:
  Project value (greater than $5 million);
  Multiple funding sources for the project;
  Project duration (multiple year);
  Project complexity (complex maintenance of traffic/ phasing/ environmental/technical issues);
  Extent of utility & railroad involvement (significant relocations/crossings);
  Project location and its visibility (urban high profile);
  Number and diversity of the stakeholders and their goals (multiple diverse goals);
  Stakeholders’ experience with Partnering (some stakeholders have no experience);
  Coordination issues (major milestone dates/adjacent projects); and
  Public involvement (multiple interest groups)

## Slide 10: Partnering
Project value guidelines
Minimum requirements for all projects

## Slide 11: Partnering
Partnering vs. DRA/DRB
DRB/DRA process is distinct from, but complementary to, the partnering process (PN 108 and 109).
DRB/DRA process focuses primarily on dispute resolution, with some dispute prevention aspects.
Partnering focuses more on day-to-day project management issues, problems, and communications.

## Slide 12: Partnering

## Slide 13
Disputes and Claims
2015

## Slide 14
Claims Process
C&MS 108.02(G)

## Slide 15
Claims Process
1 – Project level
2 – District Level (DDRC)
3 – Central Office (DCB)

## Slide 17
Engineer to Provide Step 2 Docs
Step 3 Documents - Time Extensions
Increasing the DCB’s Control of the Hearing
Step 3 Presentation By Employee
ADR By Agreement
C&MS Changes for 2016

## Slide 18
Step Two (DDRC)
Dispute | County/Route/Section | Contractor | Step 2 Meeting Date | Dispute
01-148010-03 | HAN-75-3.22 | Becdir Construction Co. | 1/18/15 | MOT/Project Suspension
02-130027-01/8 | OTT-2-25.05 | The Beaver Construction Co. | 11/3/15 | #8 Barrier Grout Mix Design
02-130395-03 | LUC-65-5.35 | Atsalis Bros. Painting | 1/6/15 | Winter Bridge Painting
02-140032-01 | WOO-475-0214 | Gerken Paving, Inc. | 4/14/15 | Temporary overhang falsework
02-140170-01 | WOO-75-10.61 | Kokosing Construction Co. |  | Blended Unit Prices
02-140268-01 | WOO-75-2.75 | Kokosing Construction Co. |  | Tack Coat Base Course
02-143000-01 | HAN/WOO-75-18.92/0.00 | Miller Brothers Const. | 9/4/15 | 48” Conduit
03-130001-01 | LOR-58-7.36 | The Beaver Construction Co. | 8/17/15 | Distorted Deck Plates
04-143005-01 | SUM-271-12.47/SUM-82-3.93 | Great Lakes Construction Co. | withdrawn | Payment for SWPPP
04-143005-02 | SUM-271-12.47/SUM-82-3.93 | Great Lakes Construction Co. | Settled | Railroad Steel Erection Redesign/Delay - Settled for $136,907
04-138033-01 | SUM-271-2.33 | Anthony Allega | 11/30/15 | Girder Line
06-120541-02 | PIC-762-11.18 | Fechko Excavating | 2/24/15 | Delay Claim/Liquidated Damages
06-130402-01 | FRA-23-22.23 | Ruhlin/Igel JV | 1/30/15 | Over Break on Shale Excavation
06-133006-02 | FRA-270-52.72 | Complete General | 4/27/15 | Asphalt Pavement mill steps
08-120599-01 | HAM-75-2.30 | Kokosing Construction Co. | 3/3/15 | Delay/Constructability
09-143018-01 | HIG-County Bridge 9 | E.L. Robinson |  | Bridge Footing Design
09-110628-01 | LAW- Ironton Russell Bridge | Brayman Const. | 1/21/15 | Anchor Box Distortion
09-140078-01 | LAW- -75.46 | Complete General Construction Co. | 1/12/16 | 
10-130508-01 | WAS-Training Annex Bldg. | 21st Century Concrete Construction, Inc. | 7/28/15 | Liquidated Damg/Extra Work
10-140113-01 | HOC-664-16.18/16.30 | Cross Roads Construction | 3/3/15 | Changed subsurface cond.
12-130151-01 | CUY-87-4.24, Parts 1-2 | Great Lakes Construction | 6/29/15 | NonPerf Cofferdam/Bracing
12-145003-01 | CUY-237-8.24 | Perk Company | 2/9/15 | Water & Monument Box $ Adj.
12-15000-01 | CUY- Chagrin Falls | Anthony Allega Cement Contractors | 6/11/15 | Underdrain Fill
12-140473-01 | CUY-Canal Rd | Great Lakes Construction Co. |  | Micropile differing site cond.
12-110499-01 | CUY-90 | Anthony Allega Cement Contractors | 10/29/15 | Repair to Parapet Epoxy sealer
12-140540-01 | CUY-IR71-12.45 | Cosmos Industrial Services, Inc. |  | Interpret 511.14 curing/loading
Step Two Meetings (DDRC) - 2015

## Slide 19
12 New Claims Filed (5 from 2014)
8 DCB Hearings
3 Mediations
4 Dropped/Settled
2 Pending
2 Filed in 2016
Step Three Hearings (DCB)

## Slide 20
Step Three Hearings (DCB)
Claim | Contractor | Resolution Type | Demand
06-133006-01 | Complete General | Claim's Board | $ 24,102.93
04-130613-01 | A.P. O’Horo | Withdrawn | $ 36,386.31
06-130402-01 | Ruhlin/Igel JV | Settled by District | $ 1,044,128.00
01-148010-03 | BECDIR Const. | Withdrawn | $ -
04-101078-01 | Anthony Allega | Claim's Board | $ 692,287.40
10-140113-01 | Cross Roads Construction | Mediation | $ 151,985.00
08-133025-01 | Great Lakes | Claim's Board | $ 30,444.75
06-133006-02 | Complete General | Settled by District | $ 74,218.00
12-140062-02 | 360 Construction | Claim's Board | $ 265,857.00
08-130086-01 | Sunesis Construction | Mediation | $ 378,475.63
02-130395-01 | Atsalis Bros. | Claim's Board | $ 2,085,133.00
02-130395-02 |  |  | 
06-120541-02 | Fechko Excavating, Inc. | Claim's Board | $ 213,002.46
02-130027-02 | The Beaver Excavating Co. | Mediation | $ 2,447,426.63
02-130027-03 |  |  | 
09-143018-01 | J&J Schlaegel | Claim's Board | $ 74,937.75
08-120599-06 | Kokosing Construction | Claim's Board | $ 2,203,203.00
03-130001-01 | The Beaver Excavating Co. | Claim's Board | $ 38,562.82
09-110628-01 | Brayman Construction | Mediation | $ 6,984,480.73

## Slide 21
Claims Process – Alt.
DRB Proposal Note 108
DRA Proposal Note 109

## Slide 22
IPS v. Univ. of Toledo
  2016-Ohio-361, 10th Dist. Ct. App.
  Must strictly adhere to the dispute resolution procedure
  Contractor waived its Claims by missing deadline for sending notice of dispute
Boone Coleman Const. v. Piketon
  2016-Ohio-628, Ohio Sp. Ct.
  Liquidated Damages are enforceable
  “Consistent with public policy”
  Specifically analyzed ODOT’s LD’s
  Per Diem rate is reviewed, not total
Recent Case Law

## Slide 23
Ironton – Russell Bridge

## Slide 24
Ironton – Russell Bridge

## Slide 26
Ironton – Russell Bridge

## Slide 27
Ironton – Russell Bridge

## Slide 31
Ironton – Russell Bridge
ODOT Construction and Material Specifications (C&MS) 711.02
ASTM A123: Standard Specification for Hot-Dipped Galvanized Coatings on Iron and Steel Products
ASTM A384: Standard Practices for Safeguarding against Warpage and Distortion During Hot-Dip Galvanization on Steel Assemblies

## Slide 32
Ironton – Russell Bridge
ASTM A384

## Slide 33
Ironton – Russell Bridge
Bridge Design Manual
302.4.2.1 GALVANIZED BEAM STRUCTURES If a galvanized bridge structure is the selected structure type, the following problems should be recognized and dealt with by the designer. Galvanizing tanks are shallow and normally not longer than 45 feet [13.7 meters] in length. Therefore, beam lengths should not be longer than 60 feet [18.5 meters]. Before a design is BDM SECTION 300 DETAIL DESIGN July 2007 3-27 completed, the designer should confirm with local galvanizers if a local plant can galvanize the structural members detailed.

## Slide 34
Ironton – Russell Bridge
ASTM A123

## Slide 35
Ironton – Russell Bridge
Pre-Galvanization Meeting

## Slide 38
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor

## Slide 39
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor
Fabricator
Galvanizer

## Slide 40
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor
Fabricator
Galvanizer

## Slide 41
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor
Fabricator
Galvanizer

## Slide 42
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor
Fabricator
Galvanizer

## Slide 43
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor
Fabricator
Galvanizer

## Slide 44
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor
Fabricator
Galvanizer

## Slide 45
Ironton – Russell Bridge
ODOT
DESIGNER
Contractor
Fabricator
Galvanizer
DRB
Consultant
Consultant

## Slide 49
204.1 FOOTING ELEVATIONS Substructure footing elevations should be shown on the Final Structure Site Plan. The top of footing should be a minimum of one foot [0.3 meters] below the finished ground line. The top of footing should be at least one foot [0.3 meters] below the bottom of any adjacent drainage ditch. The bottom of footing shall not be less than four feet [1.2 meters] below and measured normal to the finished groundline. BDM SECTION 200 PRELIMINARY DESIGN April 2010 2-24.3
Where footings are founded on bedrock (note that undisturbed shale is bedrock) the minimum depth of the bottom of the footing below the stream bed, D, in feet [meters], shall be as computed by the following: D = T + 0.50Y Where: T = Thickness of footing in feet [meters] Y = distance from bottom of stream bed to surface of bedrock in feet [meters] The footing depth from the above formula shall place the footing not less than 3 inches [75 mm] into the bedrock.

## Slide 50
204.1 FOOTING ELEVATIONS Substructure footing elevations should be shown on the Final Structure Site Plan. The top of footing should be a minimum of one foot [0.3 meters] below the finished ground line. The top of footing should be at least one foot [0.3 meters] below the bottom of any adjacent drainage ditch. The bottom of footing shall not be less than four feet [1.2 meters] below and measured normal to the finished groundline. BDM SECTION 200 PRELIMINARY DESIGN April 2010 2-24.3
Where footings are founded on bedrock (note that undisturbed shale is bedrock) the minimum depth of the bottom of the footing below the stream bed, D, in feet [meters], shall be as computed by the following: D = T + 0.50Y Where: T = Thickness of footing in feet [meters] Y = distance from bottom of stream bed to surface of bedrock in feet [meters] The footing depth from the above formula shall place the footing not less than 3 inches [75 mm] into the bedrock.

## Slide 51
204.1 FOOTING ELEVATIONS Substructure footing elevations should be shown on the Final Structure Site Plan. The top of footing should be a minimum of one foot [0.3 meters] below the finished ground line. The top of footing should be at least one foot [0.3 meters] below the bottom of any adjacent drainage ditch. The bottom of footing shall not be less than four feet [1.2 meters] below and measured normal to the finished groundline. BDM SECTION 200 PRELIMINARY DESIGN April 2010 2-24.3
Where footings are founded on bedrock (note that undisturbed shale is bedrock) the minimum depth of the bottom of the footing below the stream bed, D, in feet [meters], shall be as computed by the following: D = T + 0.50Y Where: T = Thickness of footing in feet [meters] Y = distance from bottom of stream bed to surface of bedrock in feet [meters] The footing depth from the above formula shall place the footing not less than 3 inches [75 mm] into the bedrock.

## Slide 52
BDM 204.1 Footing Elevation has Three Requirements:
Minimum Depth for Top of Footing Footing @ 933.0’
Minimum Depth for Bottom of Footing Footing @ 934.0’
No less than 3” into bedrock Footing @ 938.0’

## Slide 53
DCB  Entitled to Compensation for .5’ extra footing depth

## Slide 54
Questions?
Nathan.Fling@dot.ohio.gov
(614) 466-2140