## Vendors
STATE OF OHIO
Director of Transportation
|  |  |  | Award Date | 2021-08-31
| Invitation | 553-22 | Single
| Opened | 2021-08-24
| Location | Statewide
| Commodity | Consultant Selection for Grade Crossing Action Plan
Threshold
553-22
| Vendor Information | Remit to Address | Link to Bid
HDR Engineering, Inc. | HDR Engineering, Inc. | Included on Pricing Tab
9987 CARVER RD STE 200 | 9987 CARVER RD STE 200
Cincinnati, OH 45242 | Cincinnati, OH 45242
Kevin Keller | Kevin Keller
614-839-5770 | 614-839-5770
OAKS ID: 0000080903
Kevin.Keller@hdrinc.com; Matt.Selhorst@hdrinc.com
HDR Engineering, Inc.

## Worksheet
Loaded Billing Rates
| 258.72 | 157.92 | 286.72 | 73.64 | 224.56 | 204.4 | 131.04 | 168 | 85.4
| Principal | Project Manager | Senior Advisor | Data Collection & Analysis | Railroad Planning | Grade Crossing Engineering | Public & Agency Stakeholder Outreach | QAQC | Admin | Hours | Cost
Task 1: Project Management | 2 | 20 | 4 | 20 |  |  |  |  | 20 | 66 | 8003.52
Task 2: SAP Kickoff Meeting | 2 | 4 | 2 | 8 | 8 | 2 | 16 | 2 |  | 44 | 6949.6
Task 3: SAP Development | 4 | 40 | 12 | 160 | 24 | 40 |  |  |  | 280 | 36140.16
Task 4: Stakeholder Engagement | 4 | 16 | 12 | 24 | 24 | 12 | 60 | 2 |  | 154 | 24810.24
Task 5: Final and Revised Final SAP Update Documentation | 4 | 16 | 8 | 40 | 24 | 16 | 4 | 4 |  | 116 | 18656.96
| 4 | 24 | 16 | 16 | 24 | 16 | 12 |  |  | 112 | 20823.04
[9 empty] | Expenses | 1 | 1000
[9 empty] | Total | 772 | 116383.52
Assumptions: - All stakeholder and project meetings assumed to occur virtually via Cisco Webex or similar platform. - Expenses include minimal costs associated with printing of materials, social media postings, and other related items. - Stakeholder Engagement Task assumes one virtual stakeholder meeting with railroads, local roadway authorities and other stakeholders. The scope of this task can be adusted during negotiation to increase or decrease the extent of outreach activities.

## Rates
project Start | Project End
2021-09-01 | 2022-06-01
2021 | 2022
4 | 3 | months | 7
1 | 1.035 | fee growth
| 1.015 | % increase
Name | Role | Rate (2021) | Growth Adjusted
Kevin Keller/Keith Bucklew | Senior Advisor | 100.885 | 102.4
Matt Selhorst | Principal | 91 | 92.4
Chris Ryan | Project Manager | 55.54 | 56.4
David Montoya | Data Collection & Analysis | 25.92 | 26.3
Tony Klaumann | QAQC | 59.08 | 60
Catherine Dobbs | Railroad Planning | 79 | 80.2
Jennifer Crumbliss | Grade Crossing Engineering | 71.89 | 73
Ameerah Palacios | Public & Agency Stakeholder Outreach | 46.1 | 46.8
Chris Ryan | Safety Analysis | 55.54 | 56.4
Generic | Admin | 30 | 30.5
| Multiplier | 2.8