## Master List
| ODOT Warranty Projects |  |  |  | Last Updated: |  | 2016-08-15
Project Type | Spec Num | PID | Project | Project Year | Project Number | Dist | C-R-S | Item Description | Warranty Start (C-85) | Warranty Length | 1st Insp | 2nd Insp | 3rd Insp | 4th Insp | 5th Insp | 6th Insp | Final Insp | Distress Type | Corrective Work Required | Structure File Number 1 | Structure File Number 2 | Structure File Number 3 | Structure File Number 4 | Structure File Number 5 | Structure File Number 6 | Structure File Number 7 | Structure File Number 8 | Structure File Number 9 | Structure File Number 10 | Structure File Number 11 | Structure File Number 12 | Structure File Number 13 | Structure File Number 14 | Comments | End of warranty date | Under Warranty?
Bridge | 530 | 20411 | 3008 | 2000 | 2000-3008 | 4 | STA-IR77-011.59 | SPECIAL - STRUCTURE, MISC.: | Assumed Expired | 3 | [25 empty] | Expired
Other | 632 | 9941 | 3000 | 1997 | 1997-3000 | 6 | FRA-IR71-015.26 | SIGNALIZATION, MISC.: - 2 YR SYSTEM WARRANTY (SPECIAL) | Non performed | 2 | [23 empty] | NONPERFORMED |  | Expired
Other | 690 | 23261 | 185 | 2008 | 2008-0185 | 4 | SUM-SR82-004.14 | SPECIAL - MISC.: | Assumed Expired | 2 | [25 empty] | Expired
Asphalt | 854 | 22754 | 340 | 2002 | 2002-0340 | 2 | LUC IR-475 008.97 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B | 2003-11-21 | 3 | 2004-07-14 | 2005-04-11 | 2006-03-04 |  |  |  |  | Surface deteriorations not covered by warranty | None | [15 empty] | 2006-11-21 | Expired
Asphalt | 854 | 78418 | 273 | 2005 | 2005-0273 | 2 | WIL-20-12.03 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B | 2005-10-19 | 3 | 2006-03-04 | 2007-04-02 | [22 empty] | 2008-10-19 | Expired
Asphalt | 854 | 76818 | 376 | 2004 | 2004-0376 | 3 | LOR-US20-013.57 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 874 | 76817 | 380 | 2004 | 2004-0380 | 3 | WAY-US30-023.16 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 874 | 76686 | 364 | 2004 | 2004-0364 | 7 | MOT-IR75-003.77 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 880 | 15866 | 219 | 1997 | 1997-0219 | 1 | VAN-US30-25.971 | SPECIAL - ASPHALT CONCRETE MISC.: - ASPHALT CONCRETE WITH WARRANTY | 1997-11-18 | 5 | [23 empty] | Technical services review | 2002-11-18 | Expired
Asphalt | 880 | 15283 | 15 | 1998 | 1998-0015 | 1 | VAN-US30-06.618 | SPECIAL - ASPHALT CONCRETE, MISC.: - ASPHALT CONCRETE WITH WARRANTY | 1998-12-10 | 5 | [6 empty] | 2002-06-30 | [17 empty] | 2003-12-10 | Expired
Asphalt | 880 | 16044 | 172 | 2000 | 2000-0172 | 1 | ALL-US30-013.27 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2000-11-28 | 5 | 2001-04-23 | 2002-05-20 | 2003-04-17 | 2004-04-18 |  |  | 2005-08-30 |  | Some work to be performed prior to 8/30/2005 | [15 empty] | 2005-11-28 | Expired
Asphalt | 880 | 16055 | 39 | 2001 | 2001-0039 | 1 | VAN-US30-021.18 | ASPHALT CONCRETE (5 YEAR WARRANTY) - (T=16-1/4") | 2002-06-07 | 5 | 2003-05-21 | 2003-04-18 | 2006-04-04 | [21 empty] | 2007-06-07 | Expired
Asphalt | 880 | 16055 | 39 | 2001 | 2001-0039 | 1 | VAN-US30-021.18 | ASPHALT CONCRETE (5 YEAR WARRANTY) - (T=3-1/2") | 2002-06-07 | 5 | 2002-05-21 | 2003-04-18 | 2004-04-18 | 2006-04-04 | [20 empty] | 2007-06-07 | Expired
Asphalt | 880 | 18922 | 83 | 2001 | 2001-0083 | 1 | HAN-SR15-021.52 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-06-14 | 7 | 2002-05-13 | 2003-04-21 | 2004-04-18 | 2006-04-17 | [20 empty] | 2009-06-14 | Expired
Asphalt | 880 | 77302 | 3 | 2005 | 2005-0003 | 1 | HAN-US30-04.828 (Mainline) | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) | 2007-11-09 | 7 |  | 2009-05-29 | 2010-07-16 | 2011-04-20 | 2012-04-10 | [18 empty] | sealing in various locations | 2014-11-09 | Expired
Asphalt | 880 | 77302 | 3 | 2005 | 2005-0003 | 1 | HAN-US30-04.828 (Ramps) | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) | 2008-10-14 | 7 | 2009-05-29 | 2010-07-16 | 2011-04-20 | 2012-04-10 | [19 empty] | sealing in various locations | 2015-10-14 | Expired
Asphalt | 880 | 24337 | 87 | 2006 | 2006-0087 | 1 | DEF-US24-007.96 (East) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-11-07 | 7 |  |  |  | 2012-04-16 | [19 empty] | there was some minor sealing both lanes and they used a polymer modified surface sealer for an area that was disintegrated | 2015-11-07 | Expired
Asphalt | 880 | 24337 | 87 | 2006 | 2006-0087 | 1 | DEF-US24-007.96 (West) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-08-21 | 7 |  |  | Waived | 2011-05-18 | 2012-04-16 | [18 empty] | there was some minor sealing both lanes and they used a polymer modified surface sealer for an area that was disintegrated | 2014-08-21 | Expired
Asphalt | 880 | 19047 | 433 | 2006 | 2006-0433 | 1 | DEF-US24-012.03 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-12-06 | 7 |  | 2010-07-15 | 2011-04-26 | 2012-04-17 | [19 empty] | some longitudinal cracking that they routed and sealed | 2015-12-06 | Expired
Asphalt | 880 | 82497 | 214 | 2008 | 2008-0214 | 1 | DEF-US24-010.73 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-12-14 | 7 |  | 2010-07-22 | 2011-04-26 | 2012-04-17 | [19 empty] | there was some longitudinal cracking that they routed and sealed | 2015-12-14 | Expired
Asphalt | 880 | 19338 | 206 | 2000 | 2000-0206 | 2 | SAN-US20-026.53 | ASPHALT CONCRETE (5 YEAR WARRANTY) - , 3-1/4" | 2000-11-06 | 5 | 2001-08-06 | 2002-04-12 | 2003-04-09 | 2004-04-08 | 2005-04-06 |  | 2005-04-06 | Cracking | Crack Sealing as per SS 825 | [15 empty] | 2005-11-06 | Expired
Asphalt | 880 | 19767 | 569 | 2000 | 2000-0569 | 2 | WOO-IR75-019.92 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2001-11-19 | 5 | 2002-04-11 | 2003-04-17 | 2004-04-07 | 2005-04-11 | 2006-03-04 |  |  | Crackings | Crack Sealing as per SS 825 | [15 empty] | 2006-11-19 | Expired
Asphalt | 880 | 19768 | 291 | 2001 | 2001-0291 | 2 | WOO-IR475-000.00 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2002-01-17 | 5 | 2002-04-11 | 2003-04-17 | 2004-04-07 | 2005-04-11 | 2006-03-04 |  | 2007-01-17 | Crackings | Crack Sealing as per SS 825 | [15 empty] | 2007-01-17 | Expired
Asphalt | 880 | 23312 | 167 | 2007 | 2007-0167 | 2 | WOO-20-11.37 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2009-12-21 | 5 | 2010-03-15 | 2011-04-27 | [5 empty] | Longitudinal Joint Openings | Routing and Sealing | [14 empty] | (4/27/2011): Remedial action to be performed by 9/30/2011, with sealing by 11/15/2011. Coordination between contractor and district required. Submit action plan to district prior to work. | 2014-12-21 | Expired
Asphalt | 880 | 11376 | 23 | 2000 | 2000-0023 | 3 | ERI-SR2-12.558 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2001-11-14 | 7 | 2002-04-01 | 2003-04-01 | 2005-04-18 | 2006-04-26 |  |  |  | Some cracking / Disintegration | [16 empty] | 2008-11-14 | Expired
Asphalt | 880 | 11366 | 37 | 2000 | 2000-0037 | 3 | ASD-IR71-14.383 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2001-11-28 | 7 | 2002-04-01 | 2003-04-28 | 2005-04-19 | 2006-04-25 |  |  |  | Flushing / Disintegrated areas | R & R distressed area | [15 empty] | 2008-11-28 | Expired
Asphalt | 880 | 11365 | 151 | 2000 | 2000-0151 | 3 | RIC-IR71-20.220 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-11-26 | 7 | 2003-04-01 | 2005-04-20 | 2006-04-25 | [21 empty] | 2009-11-26 | Expired
Asphalt | 880 | 7885 | 239 | 2000 | 2000-0239 | 3 | MED-IR71-015.78 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-12-02 | 7 | 2003-04-01 | 2005-04-20 | 2006-04-18 |  |  |  |  | Cracking / Flushing / Disintegration | [16 empty] | 2009-12-02 | Expired
Asphalt | 880 | 18286 | 302 | 2000 | 2000-0302 | 3 | ASD-US30-09.484 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2001-11-28 | 5 | 2002-04-01 | 2003-04-28 | 2005-04-29 | 2006-04-24 |  |  |  | Cracking / Disintegration | R & R distressed area | [15 empty] | 2006-11-28 | Expired
Asphalt | 880 | 18200 | 3002 | 2000 | 2000-3002 | 3 | MED-IR271-000.00 | SPECIAL - MISC.: - PAVEMENT WITH FIVE YEAR WARRANTY | 2001-11-16 | 5 | 2002-04-01 | [23 empty] | 2006-11-16 | Expired
Asphalt | 880 | 18200 | 3002 | 2000 | 2000-3002 | 3 | MED-IR271-000.00 | SPECIAL - MISC.: - PAVEMENT WITH SEVEN YEAR WARRANTY | 2001-11-16 | 7 | 2002-04-01 | 2005-04-21 | 2006-04-18 |  |  |  |  | Cracks / Flushing | [16 empty] | 2008-11-16 | Expired
Asphalt | 880 | 17891 | 3015 | 2000 | 2000-3015 | 3 | LOR-IR90-010.76 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) - | 2003-02-12 | 7 | 2006-04-19 | [23 empty] | 2010-02-12 | Expired
Asphalt | 880 | 11378 | 116 | 2001 | 2001-0116 | 3 | RIC-IR71-013.66 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-12-13 | 7 | 2003-04-01 | 2005-04-19 | 2006-04-24 |  |  |  |  | Cracking / Flushing / Disintegration | [16 empty] | 2009-12-13 | Expired
Asphalt | 880 | 16281 | 141 | 2001 | 2001-0141 | 3 | ERI-US250-08.763 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-10-31 | 7 | 2003-04-01 | 2005-04-18 | 2006-04-19 |  |  |  |  | Disintegration | [16 empty] | 2009-10-31 | Expired
Asphalt | 880 | 20229 | 282 | 2001 | 2001-0282 | 3 | MED US-42 001.89 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-11-19 | 5 | 2005-04-20 | 2006-04-20 | [5 empty] | Cracking/Disintegration / Flushing | [16 empty] | 2007-11-19 | Expired
Asphalt | 880 | 14016 | 517 | 2001 | 2001-0517 | 3 | WAY-IR71-000.28 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-11-22 | 7 | 2003-04-01 | 2005-04-21 | 2006-04-21 | [21 empty] | 2009-11-22 | Expired
Asphalt | 880 | 16284 | 33 | 2002 | 2002-0033 | 3 | CRA-US30-33.500 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-08-04 | 7 | 2006-04-17 | [23 empty] | 2012-08-04 | Expired
Asphalt | 880 | 16283 | 36 | 2002 | 2002-0036 | 3 | CRA-US30-24.000 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-08-04 | 7 | [24 empty] | 2012-08-04 | Expired
Asphalt | 880 | 16282 | 509 | 2002 | 2002-0509 | 3 | CRA-US30-15.865 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-08-04 | 7 | 2006-04-17 | [23 empty] | 2012-08-04 | Expired
Asphalt | 880 | 18632 | 465 | 2003 | 2003-0465 | 3 | RIC-IR71-6.73 (slm 164.47 - 165.66) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2004-11-15 | 7 | [24 empty] | 2011-11-15 | Expired
Asphalt | 880 | 18632 | 465 | 2003 | 2003-0465 | 3 | RIC-IR71-6.73 (slm 165.66 - 169.52) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-05-26 | 7 | [24 empty] | 2012-05-26 | Expired
Asphalt | 880 | 18632 | 465 | 2003 | 2003-0465 | 3 | RIC-IR71-6.73 (slm 169.52 - 171.53) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-12-14 | 7 | [24 empty] | 2012-12-14 | Expired
Asphalt | 880 | 18631 | 82 | 2004 | 2004-0082 | 3 | WAY-SR30-9.26 10.42EB to 11.63EB | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2004-11-24 | 7 | [24 empty] | 2011-11-24 | Expired
Asphalt | 880 | 18631 | 82 | 2004 | 2004-0082 | 3 | WAY-SR30-9.26 11.43WB to 11.3WB | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2004-12-17 | 7 | [24 empty] | 2011-12-17 | Expired
Asphalt | 880 | 18631 | 82 | 2004 | 2004-0082 | 3 | WAY-SR30-9.26 9.18EB to 10.42EB | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2006-05-25 | 7 | [24 empty] | 2013-05-25 | Expired
Asphalt | 880 | 18631 | 82 | 2004 | 2004-0082 | 3 | WAY-SR30-9.26 9.18WB to 10.47WB | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2006-05-25 | 7 | [24 empty] | 2013-05-25 | Expired
Asphalt | 880 | 19956 | 583 | 2004 | 2004-0583 | 3 | MRW-IR71-019.54 (slm 157.7 - 160.67) | ASPHALT CONCRETE WITH WARRANTY (7 YEARS) | 2006-11-12 | 7 | 2007-04-20 | [6 empty] | Some rutting, deterioration | [16 empty] | 2013-11-12 | Expired
Asphalt | 880 | 19956 | 583 | 2004 | 2004-0583 | 3 | MRW-IR71-019.54 (slm 160.67 - 164.47) | ASPHALT CONCRETE WITH WARRANTY (7 YEARS) | 2005-12-17 | 7 | 2007-04-20 | [6 empty] | Some rutting, deterioration | [16 empty] | 2012-12-17 | Expired
Asphalt | 880 | 14017 | 48 | 2005 | 2005-0048 | 3 | WAY IR-0071 007.04 (slm 201-89 - 204-05) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-12-16 | 7 | [23 empty] | Some cracking / piting | 2013-12-16 | Expired
Asphalt | 880 | 14017 | 48 | 2005 | 2005-0048 | 3 | WAY IR-0071 007.04 (slm 204.05 - 208.31) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-12-17 | 7 | [23 empty] | Some cracking / piting | 2012-12-17 | Expired
Asphalt | 880 | 24355 | 77 | 2005 | 2005-0077 | 3 | ASD-US250-012.56 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-12-01 | 7 | [24 empty] | 2012-12-01 | Expired
Asphalt | 880 | 4082 | 312 | 2005 | 2005-0312 | 3 | MED-SR18-016.03 | ASPHALT CONCRETE (7 YEAR WARRANTY) | Non performed | 7 | [25 empty] | Expired
Asphalt | 880 | 14018 | 343 | 2005 | 2005-0343 | 3 | MED-IR71-009.56 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-12-14 | 7 | [24 empty] | 2013-12-14 | Expired
Asphalt | 880 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 Ramp EN | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-12-14 | 7 | [24 empty] | 2014-12-14 | Expired
Asphalt | 880 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 Ramp SE | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-08-08 | 7 | [24 empty] | 2015-08-08 | Expired
Concrete | 884 | 24336 | 78 | 2007 | 2007-0078 | 1 | PAU-US24-012.30 | 12.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-10-29 | 10 |  |  | 2012-04-26 | [20 empty] | Settlement agreement that created an additional 3 years of warranty | 2019-10-29 | Under Warranty
Concrete | 884 | 24334 | 110 | 2007 | 2007-0110 | 1 | PAU-US24-000.00 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-10-29 | 7 | 2010-07-21 | 2011-04-27 | 2012-04-24 | [20 empty] | there was some repairs on the exit and entrance ramps to SR 49.This consited of remove and replace,spall repair,stitch and seal joints. | 2016-10-29 | Under Warranty
Chip Seal | 882 | 95788 | 1065 | 2014 | 2014-1065 | 2 | WIL SR 107 0.00 Resurf | SINGLE CHIP SEAL WITH TWO YEAR WARR, APP | 2014-09-19 | 2 | [24 empty] | 2016-09-19 | Under Warranty
Concrete | 896 | 80444 | 8015 | 2009 | 2009-8015 | 2 | LUC-24-6.19 | PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK (7 YEAR WARRANTY) | 2012-09-28 | 7 | [6 empty] | 2012-12-12 | [17 empty] | 2019-09-28 | Under Warranty
Concrete | 896 | 80446 | 201 | 2009 | 2009-0201 | 2 | HEN/LUC-24-15.85/0.00 PART 1; HEN-24-10.42 (LUC) PART 2 | PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK (7 YEAR WARRANTY) | 2012-09-28 | 7 | [6 empty] | 2013-05-23 | [17 empty] | 2019-09-28 | Under Warranty
Asphalt | 880 | 16367 | 454 | 2001 | 2001-0454 | 4 | STA-IR77-17.61 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-10-07 | 7 | 2006-08-16 | 2007-04-30 | [21 empty] | Mainline pavement warranty from Station 440+06 to Station 73+86 Rt., I-77started on October 18, 2002; Mainline pavement warranty from Station 440+06 to Station 73+86 Lt. I-77started on October 7, 2003 Ref 124 | 2010-10-07 | Expired
Asphalt | 880 | 18721 | 70 | 2002 | 2002-0070 | 4 | ATB IR-90 19.56 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-11-03 | 7 | 2006-08-01 | 2007-05-03 | [21 empty] | Mainline pavement warranty from station 357+00 to 492+00 RT., I-90 started on October 31, 2002; Mainline pavement warranty from station 357+00 to 492+00 LT., I-90 started on November 3, 2003 Ref 93 | 2010-11-03 | Expired
Asphalt | 880 | 21609 | 467 | 2002 | 2002-0467 | 4 | STA IR-77 12.76 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-10-31 | 7 | 2006-08-16 | 2007-04-25 | [21 empty] | NB mainline pavement from Station 184+42 to 290+00 RT., I-77 10/31/2003 Ref 112 | 2010-10-31 | Expired
Asphalt | 880 | 22261 | 4 | 2003 | 2003-0004 | 4 | ATB IR-90 0.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2004-10-25 | 7 | 2006-08-01 | 2007-05-03 | [21 empty] | Mainline pavement warranty from Station 0+45 to Station 162+21 Lt., I-90 started on November 10, 2003 per SS880. Mainline pavement warranty from Station 162+21 to Station 196+00 Lt. (Passing lane + shoulder), I-90 started on November 10, 2003 per SS880. Mainline pavement warranty from Station 162+21 to Station 196+00 Lt. (Driving lane + shoulder), I-90 started on June 4, 2004 per SS880. Mainline pavement warranty from Station 0+45 to Station 196+00 Rt., I-90 started on Oct. 25, 2004 Ref 82 | 2011-10-25 | Expired
Asphalt | 880 | 20410 | 333 | 2003 | 2003-0333 | 4 | STA IR-77 9.46 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-11-16 | 7 | 2005-11-16 | 2007-04-27 |  |  |  |  | 2006-08-24 | [16 empty] | Ref 161 | 2012-11-16 | Expired
Asphalt | 880 | 23482 | 350 | 2004 | 2004-0350 | 4 | STA IR 77 17.93 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2007-09-06 | 7 | 2007-12-05 |  |  |  | 2012-04-03 |  |  | Cracking | [15 empty] | Ref 168: Distresses noted (cracking)- corrective actions requested 4/4/12. | 2014-09-06 | Expired
Asphalt | 880 | 21610 | 532 | 2004 | 2004-0532 | 4 | STA IR 77 14.80 (NB) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-12-13 | 7 | [6 empty] | 2012-04-10 | Cracking (Longitudinal joints - project length) Disintegrating (Portage St Onramp) Disintegrating - Dry Distresses Cinter lane near 109.75. Disintegrating - Surface Distresses Everhard on-ramp. Disintegrating - Cenerlane before Hall of Fame Bridge. Disintegrated - Off ramp at Portage. | [15 empty] | Refs 116, 442 | 2012-12-13 | Expired
Asphalt | 880 | 21610 | 532 | 2004 | 2004-0532 | 4 | STA IR 77 14.80 (SB) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2006-11-05 | 7 | [5 empty] | 2012-04-10 |  | Cracking (Longitudinal joints - project length) Disintegrating - near Portage offramp. Disintegrating - Boney near Mile 110. |  | 1504 L SFN 7604440 | 1516 L SFN 7604505 | 1668 L SFN 7604653 | 1597 SFN 7604629 | [10 empty] | Refs 116, 442 | 2013-11-05 | Expired
Asphalt | 880 | 16372 | 582 | 2004 | 2004-0582 | 4 | SUM IR 77 1.40 RT:1.40-4.06 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-10-11 | 7 | 2005-12-14 |  |  |  |  | 2012-04-12 |  | Cracking - Longitudinal Joints Disintegrated Areas - Various Locations | [15 empty] | Ref 110 | 2012-10-11 | Expired
Asphalt | 880 | 16372 | 582 | 2004 | 2004-0582 | 4 | SUM IR 77 1.40 LT 1.40-4.06 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2006-09-29 | 7 | 2007-01-17 |  |  |  |  | 2012-04-12 |  | Cracking - Longitudinal Joints Disintegrated Areas - Various Locations | [15 empty] | Ref 110 | 2013-09-29 | Expired
Asphalt | 880 | 24591 | 108 | 2005 | 2005-0108 | 4 | ATB IR 90 3.70 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | Voided | 7 | N/A | [22 empty] | Ref 150 Non-Performed |  | Expired
Asphalt | 880 | 20412 | 583 | 2005 | 2005-0583 | 4 | STA IR 77 10.33 (SB) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2006-12-13 | 7 |  |  |  |  | 2012-04-17 |  |  | Cracking - Longitudinal Joints & Misc locations. Disintegrated - North construction joint. Middle lane sout of 13th bridge. Middle lane bewn Tusc & Duber structures. | [15 empty] | Comp Date 6/30/08 Ref 199 | 2013-12-13 | Expired
Asphalt | 880 | 20412 | 583 | 2005 | 2005-0583 | 4 | STA IR 77 10.33 (NB) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2007-11-19 | 7 | [5 empty] | 2012-04-17 |  | Cracking - Longitudinal Joints & Misc locations. | [15 empty] | Comp Date 6/30/08 Ref 199 | 2014-11-19 | Expired
Asphalt | 880 | 16514 | 151 | 2006 | 2006-0151 | 4 | SUM IR 77 21.79 (SLM 18.97-21.70 NB) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2008-11-06 | 7 |  |  |  | 2012-04-24 | 2013-04-18 | 2014-07-16 |  | 2012/2013, Cracking & Disintegrated Areas 2014 - Crack Sealing Needed | [15 empty] | Completion Date 9-30-08 Ref 166 | 2015-11-06 | Expired
Asphalt | 880 | 16514 | 151 | 2006 | 2006-0151 | 4 | SUM IR 77 21.79 (SLM 18.97-22.34 SB) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2008-11-06 | 7 |  |  |  | 2012-04-24 | 2013-04-18 | 2014-07-16 |  | 2012/2013, Cracking & Disintegrated Areas 2014 - Crack Sealing Needed | [15 empty] | Completion Date 9-30-08 Ref 166 | 2015-11-06 | Expired
Asphalt | 880 | 16514 | 151 | 2006 | 2006-0151 | 4 | SUM IR 77 21.79 (SLM 17.20-18.97) | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2008-06-06 | 7 |  |  |  | 2012-04-24 | 2013-04-18 | 2014-07-16 |  | 2012/2013, Cracking & Disintegrated Areas 2014 - Crack Sealing Needed | [15 empty] | Held review 4/22/15 - Contractor will crack seal NB & SB I-77 within project limits. Crack Sealing Completed in May of 2015 | 2015-06-06 | Expired
Asphalt | 880 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 Ramp ES | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-05-22 | 7 | [24 empty] | 2016-05-22 | Expired
Asphalt | 880 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 Mainline | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-11-15 | 7 | [24 empty] | 2016-11-15 | Under Warranty
Asphalt | 880 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 Ramp WS | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2010-04-26 | 7 | [24 empty] | 2017-04-26 | Under Warranty
Asphalt | 880 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 Ramp WNS | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2010-04-26 | 7 | [24 empty] | 2017-04-26 | Under Warranty
Asphalt | 880 | 16299 | 136 | 2000 | 2000-0136 | 5 | MUS-SR16-007.16 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-11-13 | 7 | 2006-04-12 | 2007-04-27 | 2008-04-24 | 2009-04-23 |  |  |  | Minor distress | Some cracking | [14 empty] | Flushing at Eastbound 8.10-8.20 (driving and passing lane); Eastbound 10.0-10.10 (passing lane); Eastbound 10.30-10.40; Eastbound 10.70-10.80 (passing lane). | 2009-11-13 | Expired
Asphalt | 880 | 16293 | 136 | 2001 | 2001-0136 | 5 | FAI-US33-007.31 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-11-14 | 7 | 2006-03-30 | 2007-04-19 | 2009-04-23 |  |  |  |  | Minor cracking | [15 empty] | Contractor applied crack sealing | 2010-11-14 | Expired
Asphalt | 880 | 16294 | 110 | 2002 | 2002-0110 | 5 | FAI-US33-013.25 | ASPHALT CONCRETE (7 YEAR WARRANTY) - , 11.25" | 2004-11-22 | 7 | 2006-03-30 | 2007-04-19 | 2008-04-24 | 2009-04-23 |  | 2011-04-13 |  | Minor cracking, Flushing | [15 empty] | Initial flushing at Eastbound 15.40-15.50 (passing lane); Eastbound 15.70-16.00 (passing and driving lanes); Eastbound 16.20-16.30 (driving lane) (4/13/11): Flushing at 15.40-16.30 passing and driving lanes. | 2011-11-22 | Expired
Asphalt | 880 | 16295 | 446 | 2002 | 2002-0446 | 5 | FAI-US33-017.44 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-04-07 | 7 | 2006-03-30 | 2007-04-19 | 2008-04-24 | 2009-04-23 |  | 2011-04-13 |  | None | None | [14 empty] | Some contractor applied crack sealing | 2012-04-07 | Expired
Asphalt | 880 | 8314 | 1 | 2003 | 2003-0001 | 5 | LIC-SR79-006.66 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-08-23 | 7 | 2006-04-20 | 2007-04-27 | 2008-04-24 | 2009-04-23 |  | 2011-04-13 | 2012-04-17 | Cracking and Potholes | [15 empty] | 4/13/11: Cracking throughout, potholes at 8.40-8.50 both drive & passing lanes. | 2012-08-23 | Expired
Asphalt | 880 | 23057 | 46 | 2003 | 2003-0046 | 5 | FAI-US33-019.79 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-10-26 | 7 | 2006-01-04 | 2007-04-19 | 2008-04-24 | 2009-04-23 |  | 2011-04-13 | 2012-04-17 | None | [15 empty] | 4/13/11: Cracking from 20.00-20.30. 4/17/12: Cracking 20.5-21.00 & 22.00, Disent 21.250-21.30, Rutting 21.20-21.80 | 2012-10-26 | Expired
Asphalt | 880 | 24486 | 150 | 2006 | 2006-0150 | 5 | FRA/LIC-161-23.20/0.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2008-10-21 | 7 |  |  | 2011-04-13 | 2012-04-17 |  | 2014-05-27 |  | Cracking | [15 empty] | Cracking at variious locations in east and westbound lanes. | 2015-10-21 | Expired
Asphalt | 880 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 Ramp NSW | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2010-04-26 | 7 | [24 empty] | 2017-04-26 | Under Warranty
Asphalt | 880 | 25199 | 460 | 2009 | 2009-0460 | 4 | ATB-IR90-014.25 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2012-06-28 | 7 | 2013-04-30 | 2014-07-15 | 2015-04-22 |  |  |  |  | 7/15/2014 - Intermittent Cracking in excess of 500' | [15 empty] | Held review 4/22/15 - Remedial action needed, letter sent to contractor 4/29/15 | 2019-06-28 | Under Warranty
Asphalt | 880 | 25199 | 460 | 2009 | 2009-0460 | 4 | ATB-90-14.25 PART 1; ATB-84-20.50 PART 2 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2012-06-26 | 7 | 2013-04-30 | 2014-07-15 | 2015-04-22 |  |  |  |  | 7/15/2014 - Intermittent Cracking in excess of 500' | [16 empty] | 2019-06-26 | Under Warranty
Asphalt | 880 | 7278 | 722 | 1999 | 1999-0722 | 6 | FRA-IR71-025.60 | ASPHALT CONCRETE (5 YEAR WARRANTY) - PHASE 1 | 2000-11-17 | 5 | N/A | 2002-04-29 | 2003-03-14 | 2004-04-17 | 2005-06-04 | [18 empty] | OUT OF WARRANTY | 2005-11-17 | Expired
Asphalt | 880 | 7278 | 722 | 1999 | 1999-0722 | 6 | FRA-IR71-025.60 | ASPHALT CONCRETE (5 YEAR WARRANTY) - PHASE 2 | 2001-10-01 | 5 | 2002-04-29 | 2002-04-29 | 2003-03-14 | 2004-04-17 | 2005-06-04 | 2006-04-09 | 2006-08-24 | out of warranty | [15 empty] | OUT OF WARRANTY | 2006-10-01 | Expired
Asphalt | 880 | 16967 | 5028 | 1999 | 1999-5028 | 6 | FRA-IR670-005.61 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 1999-11-01 | 5 | [5 empty] | 2004-11-01 | [17 empty] | OUT OF WARRANTY | 2004-11-01 | Expired
Asphalt | 880 | 5881 | 4 | 2000 | 2000-0004 | 6 | FRA-IR70-014.69 | ASPHALT CONCRETE (7 YEAR WARRANTY) - PHASE A EAST BOUND | 2001-11-11 | 7 |  | 2003-03-27 | 2004-04-24 | 2005-08-04 | 2006-05-06 | 2007-05-05 | Oct. 08' | cracking | seal Oct. 06 | [14 empty] | 3/20/2006--no defieciencies foundprevious patched potholes at James exit okay indepth review 5/6/06-cracking -contractor to seal after October 1, 2006 as a prevention Cracksealing performed by contractor 10/21/06 and 10/28/06 5/5/07 reviewed cracking, sporadic throughout all lanes. 6/11/07 reminder letter sent to KOKO. 6/18/07 koko response will fix in late august of 07 22.7mm nb ramp to 270 heading westbound Looked at 3/14/2008 some new cracks but within threshold limit. Will drive in October 08 for final inspection Out of warranty letters sent to Kokosing and their bonding company Nov. 12, 2008 OUT OF WARRANTY SIGN REMOVAL LETTER SENT 11/13/08 | 2008-11-11 | Expired
Asphalt | 880 | 5881 | 4 | 2000 | 2000-0004 | 6 | FRA-IR70-014.69 | ASPHALT CONCRETE (7 YEAR WARRANTY) - PHASE A WEST BOUND | 2001-07-26 | 7 |  | 2003-03-27 | 2004-04-24 | 2005-08-04 | 2006-05-06 | 2007-05-05 | June 08' | cracking | seal Oct. 06 | [14 empty] | 3/20/2006--no defieciencies found 5/6/06-indepth review contractor to seal after Oct 1, 2006 as a prevention Cracksealing performed by contractor 10/21/06 and 10/28/06 5/5/07 reviewed cracking, sporadic throughout all lanes. 6/11/07 reminder letter sent to KOKO. Looked at on 3/14/2008 some new cracks but within threshold limit. Will look at in June 08 for final inspection. OUT OF WARRANTY 7/26/08. | 2008-07-26 | Expired
Asphalt | 880 | 5881 | 4 | 2000 | 2000-0004 | 6 | FRA-IR70-014.69 | ASPHALT CONCRETE (7 YEAR WARRANTY) - PHASE B EAST BOUND | 2000-11-15 | 7 | 2001-06-20 | Review Waived 2002 | 2003-03-27 | 2004-04-24 | 2005-08-04 | 2006-05-06 | 2007-05-05 | cracking | seal Oct. 06 | [14 empty] | 3/20/2006--no defieciencies found5/6/06-indepth review contractor to scrack seal ofter 10/2/06 as a prevention as a prevention Cracksealing performed by contractor 10/21/06 and 10/28/06 5/5/07 review--popouts at James cracking throughtout all lanes, none 500' but some wide--letter to koko on 5/14/07. 6/11/07 reminder letter sent to KOKO. Out of warranty letter sent to Koko and bonding company on 11/27/07 OUT OF WARRANTY | 2007-11-15 | Expired
Asphalt | 880 | 5881 | 4 | 2000 | 2000-0004 | 6 | FRA-IR70-014.69 | ASPHALT CONCRETE (7 YEAR WARRANTY) - PHASE B WEST BOUND | 2000-07-25 | 7 | 2001-06-20 | Review Waived 2002 | 2003-03-27 | 2004-04-24 | 2005-08-04 | 2006-05-06 | 2007-05-05 | cracking | seal Oct. 06 | [14 empty] | 3/20/2006--no defieciencies found 5/6/060in depth review contractor to crack seal after 10/2/06 as a prevention Cracksealing performed by contractor 10/21/06 and 10/28/06 Warranty review scheduled for 5/5/07 reviewed 5/5/07 letter to koko on 5/14/07--cracking previously patched area under 270 coming out though cracking not 500' some wide. 6/11/07 reminder letter sent to KOKO. Repairs set up for 9/8/07 cancelled due to rain reset for 9/15/07-remove 1.5" and replace.repairs made on 9/15/2007 to satisfaction of area engineer Brian Hupp. This portion of project out of warranty 7/25/2007--letter sent to contractor 10/2/07(recognizing repairs). Out of warranty letters sent to Koko and bonding company on 11/27/07 OUT OF WARRANTY | 2007-07-25 | Expired
Asphalt | 880 | 20943 | 17 | 2000 | 2000-0017 | 6 | FRA-IR670-005.61 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2000-08-09 | 5 | Warranty Waived 2001 | Review Waived 2002 | 2003-03-24 | 2004-04-21 | 2005-05-31 | xxxxxx | 2005-08-04 | [16 empty] | OUT OF WARRANTYLetter sent for sign removal, to contractor and bonding company | 2005-08-09 | Expired
Asphalt | 880 | 4388 | 91 | 2000 | 2000-0091 | 6 | GRE-US35-026.20 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-07-20 | 7 | 2003-03-21 | 2004-04-22 | 2005-08-06 | see comments | 4/12/2007 see comments | 2008-02-21 | 2009-04-28 | [16 empty] | Begin/end expiration signs ordered, as none were on site. cracking occuring in pavment sending letter to contractor after I hear from Kerry Yoakum at C.O. 4/25/06 53106 letter to bonding company sent Craksealing performed by Jurgensen for bonding company on 11/13/06. 4/12/07-crackseal material gone , more cracking-letter being sent to bonding company 4/25/07. 6/11/07 reminder letter to Surety company. 8/16/07--received phone call from Paul Cain of Jurgensen Co.- faxing him copy of findings--he insinuated repairs will be done in OCTOBER 07. 11/02/07--warranty repairs(cracksealing performed on 10/31/07 and 10/29/07) made by J. R. Jurgenson Contractor. 02/21/08--previous cracksealing holding up . No new cracking. Small holes from missing rpm's thus ODOT's to fix04/28/09 met with paul cain of jurgenson, representing bonding company, cracking in pavement 5/4/09 letter sent to bonding company of findings waiting on response. 6/8/09 received letter from J. R. Jurgensen will be doing repairs for St Paul Travelers. 6/11/09 sent out approval to proceed with repairs to J. R. Jurgensen and St Pual Travelers 09/03/09 TALKED WITH PAUL CAIN OF JURGENSEN WILL BE IN LATE SEPT OR EARLY OCT TO CRACKSEAL.. 10-23-09 out of warranty cracksealing on project completed weeks of 10/19/09 and 10/26/09. OUT OF WARRANTY LETTERS SENT TO BONDING COMPANY. | 2009-07-20 | Expired
Asphalt | 880 | 9078 | 577 | 2000 | 2000-0577 | 6 | FAY-US35-002.57 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-08-01 | 7 | 2004-04-22 | 2005-08-06 | see comments | 4/3/2007 see comments | 2008-02-21 | 2009-04-28 | [17 empty] | distress types found sending letter to contractor after I hear from Kerry Yoakum at C.O. 4/25/06 5/31/06 letter to bonding company 11/13/06 CRACKSEALING PERFORMED BY JURGENSEN FOR BONDING COMPANY 4/3/07--cracking, previous crackseal gone, loss of material letter being sent to bonding company . Reminder letter sent to surety on 6/11/07. 8/16/07--Paul Cain of Jurgenson called- faxed him infor on review and areas needing attention. He insinuated they would be fixing areas in October 07'. 11/2/07--warranty repairs completed by J. R. Jurgenson Co. (10/29 and 10/31 2007, cracksealing) 02/21/08 review--rpm's missing ODOT responsibility to repair. previous placed cracksealing in good shape. 04/28/09 met with bonding company representative paul cain of jurgensen, cracking throughout, 5/4/09 sent letter to bonding company of findings waiting on response. 09/03/09 TALKED WITH PAUL CAIN OF JURGENSEN WILL BE IN LATE SEPT OR EARLY OCT TO CRACKSEAL. week of 10/19/09 jr jurgenson company, bagan cracksealing of warranty pavement, odot inspector wilbur anders. CRACKSEALING COMPLETED 11 12 2009 03/2010--prelim inspection by county found no warranty issues. Goes out of warranty in August 2010 will look at in July. | 2010-08-01 | Expired
Asphalt | 880 | 6912 | 142 | 2001 | 2001-0142 | 6 | FAY-US35-007.51 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-08-01 | 7 | 2004-04-22 | 2005-08-06 | see comments | 2007-04-03 | 2008-02-21 | 2009-04-28 | [17 empty] | sending letter to contractor on problem areas after I hear from Kerry Yoakum at C.O> 4/25/06 5/31/06 letter to bonding company sent 11/13/06 jurgensen contractor performed cracksealing for contractor 4/3/07--some cracking letter being sent to bonding company--cracking not over threshold limits . 6/11/07 reminder letter to surety company sent. No repairs needed at this time. 02/21/08 at this time everyting looking good cracking still not over threshold limits. 04/28/09 met with bonding company representative paul cain of jurgenson cracking in pavement 5/4/09 sent letter of findings to bonding company waiting on response. 09/03/09 TALKED WITH PAUL CAIN OF JURGENSEN WILL BE IN LATE SEPT EARLY OCT. TO CRACKSEAL. week of 10/19/09 j. rl. jurgenson on project cracksealing warranty asphalt, odot inspector wilbur anders on site. CRACKSEALING COMPLETED 11 10 2009. 03/2010--prelim by county no warranty issues at this time will drive in July as out of warranty in August 2010. | 2010-08-01 | Expired
Asphalt | 880 | 4666 | 69 | 2002 | 2002-0069 | 6 | FRA-IR670-003.17 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-09-19 | 7 | 2004-04-21 | 2005-05-31 | 2006-03-22 | 2007-02-21 | 2008-03-12 | 2009-03-30 | [17 empty] | 3/22/06-drt review no deficencies found. 2/27/07--preliminary review says lots of cracking will look at. 7/12/07 J. Dersoon looked at, cracking not at threshold as yet, deterioration/separation at c/l joint , should look at in-depth spring 08 with drt team 3/12/08 --cracking but within threshold limits. Hole was a rpm that had come out ODOT's to fix. 03/30/09eastbound okay, westbound some cracking will look at again in April to see if review is needed. letter to contractor on 5/4/09 with findings on cracking waiting on response. 09/03/09 CALLED AND LEFT MESSAGE WITH JIM GEORGE OF COMPLETE GENERAL TO SEE WHEN REPAIRS WILL TAKE PLACE. STILL 1 YEAR LEFT ON WARRANTY 10/07/09---Brian Hupp ODOT P.E. met with Bruce St.Claire of Shelly Co. cracking is at the 3.93 to 4.06 westbound between 3rd and 4th streets can wait till next year on final review to be repaired.(cracksealing ). 2010 review set for may 4, 2010 May 4, 2010--Warranty review with Shelly Co(subcontractor in attendnance ) Longitudinal cracking meeting thresholds. Letter sent to Prime contractor of findings along with pictures 5/11/10. | 2010-09-19 | Expired
Asphalt | 880 | 16992 | 8005 | 2002 | 2002-8005 | 6 | FRA-IR670-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) -inside lanes | 2003-10-22 | 7 | 2004-04-21 | 2005-08-04 | 2006-03-22 | 2007-02-21 | 2008-03-12 | 2009-03-30 | [17 empty] | 3/22/2006-drt team pavement looks good.2/21/07--some horizontal cracking noted with tolerance 7/12/07--J dersoon looked at and suggest that though not at threshold level now would warrant an in-depth review in spring of 08' 03/12/08 reviewed cracking measured not at distress threshold. 03/30/09 no warranty issues found at this time. 8/31/09--Shelly and Sands crew in and cracksealed centerline joint using 3402 polymer blend from R.W. Meadows on Roadway A from .62 to US 33. May 4, 2010--warranty review crack longitudinal cracking e.b. and w.b. lanes Contractor notified by letter . | 2010-10-22 | Expired
Asphalt | 880 | 16992 | 8005 | 2002 | 2002-8005 | 6 | FRA-IR670-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) -inside lanes | 2003-10-22 | 7 | 2004-04-21 | 2005-08-04 | 2006-03-22 | 2007-02-21 | 2008-03-12 | 2009-03-30 | [17 empty] | 3/22/2006-drt team pavement looks good.2/21/07--some horizontal cracking noted with tolerance 7/12/07--J dersoon looked at and suggest that though not at threshold level now would warrant an in-depth review in spring of 08' 03/12/08 reviewed cracking measured not at distress threshold. 03/30/09 no warranty issues found at this time. | 2010-10-22 | Expired
Asphalt | 880 | 16992 | 8005 | 2002 | 2002-8005 | 6 | FRA-IR670-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) -outside and ramps | 2002-10-20 | 7 | 2004-04-21 | 2005-08-04 | 2006-03-22 | 2007-02-21 | 2008-03-12 | 2009-03-30 | 2009-08-31 | [16 empty] | 3/22/06-drt team pavement looks good. 2/21/07--some horizontal cracking noted with tolerance --7/12/07 J. Dersoon looked at, cracking withing tolerance/threshold suggest drt team review in spring of 08' 03/12/08 reviewed cracking measured and not at distress threshold 03/30/09 cracking roading a and roadway b letter to shelly and sands on 3/13/09 with findings .waiting on response. June 16, 2009 letter from Shelly and Sands repair to cracks by sealing okay on repairs sent out 6/25/09 8/31/09-Shelly and Sands crew in and crack sealed centerline joint using 340s polymer compound by r.w. meadows and applying in crack after blowing out using air hose on Roadway B from US 33 to gore area. and roadway a westbound from .62 to us 33. out of warranty letter sent 10/9/09 | 2009-10-20 | Expired
Asphalt | 880 | 6225 | 134 | 2003 | 2003-0134 | 6 | FAY-IR71-000.00 | ASPHALT CONCRETE NORTHBOUND INT. | 2004-07-21 | 7 | 2005-08-06 | 2006-04-08 | 2007-03-01 | 2008-04-30 | 2009-04-28 | 2010-03-01 |  | CRACKING | [15 empty] | 04/08/06 no distress types found 3/1/07--over all good condition 9.35 transvers crack within threshold tolerances 2008 warranty review inside lane at shoulder between 0.00 and .28 cracking occuring over 1/4" average in one 528 foot segment measured over 500' in cracking. There is spurodic cracking throughout project limits, mainly on inside lane at shoulder as a preventive measure contractor will be made aware as this has three more years on warranty. There is disintegration at the approach slab and asphalt pavement joints at the following: .28 rear, .47 rear, 3.01 rear and forward, 3.85 forward, 7.1 forward and 7.3 rear and forward. 10/16/08 J. R Jurgenson (Paul Cain) called wil be sending letter on when they will do repairs. jUERGENSON IN CRACKING SEALING 11/03/08. JEFF HOLBROOK ODOT NOTIFIED WILL ANDERS WATCHING. 04/28/09 met with jurgenson, paul cain, cracking discovered 5/4/09 sent out letter on findings waiting on response. week of 10/19/09 began cracksealing on warranty pavement j.r. jurgenson co., odot inpsector wilbur anders. 03/2010 no inspection required this year contractor to be back in to finish cracksealing started fall of 2009 | 2011-07-21 | Expired
Asphalt | 880 | 6225 | 134 | 2003 | 2003-0134 | 6 | FAY-IR71-000.00 | ASPHALT CONCRETE SOUTHBOUND | 2005-06-23 | 7 | 2006-04-08 | 2007-03-01 | 2008-04-30 | 2009-04-28 | 2010-03-01 | [18 empty] | 04/08/06 no distress types found 3/1/07--good condition 2008 warranty review-- no show by contracotr-- spurodic cracking mainly inside lane at shoulder area but not at distress threshold limit-- contractor should watch and maintain as a preventive measure. Letter to contractor 5/5/08 4/28/09 met with paul cain of jurgenson for review, cracking in pavement various areas 5/4/09 sent out letter to contractor of findings waiting on response.week of 10/19/09 began cracksealing on warranty pavement j.r. jurgenson co., odot inpsector wilbur anders.03/2010 no inspection required this year contractor to be back in to finish cracksealing started fall of 2009 | 2012-06-23 | Expired
Asphalt | 880 | 77118 | 294 | 2004 | 2004-0294 | 6 | MAD-70-0.00 | Asphalt Conc Pvmnt EB Intermediate all 3 lanes | Voided | 7 | 2006-03-20 | Review waived 2007 | this is incorportated with all EB pavement | [20 empty] | see comments above |  | Expired
Asphalt | 880 | 77118 | 294 | 2004 | 2004-0294 | 6 | MAD-70-0.00 | ASPHALT CONCRETE EASTBOUND INSIDE | 2005-07-22 | 7 | 2006-03-20 | Review waived 2007 | 2008-04-14 | 2009-02-24 | 2010-04-22 | [18 empty] | 3/20/2006--no defieciencies foundsee comments above 03/14/08 review- pot hole at beginning of proj and one approximately 1000 feet in inside line west of structure6.29 nb--contractor to fix for right know county manager said they would fill with cold mix. Kokosing called inquiring on repair to barrier wall holes in structure and potholes 8/21/08. 09/03/09 TALKD WITH ROB VANGORDER OF KOKOSING. REPAIR WORK COMPLETED ON POTHOLE EB AND STRUCTURE 1.88 EB BOLT HOLES IN DECK ON 9/2/09 03/15/2010--prelim inspection by county manager pot holes discovered will set up DRT review for April 2010. REVIEW SET UP FOR APRIL 22, 2010. 04/22/10 contractor will be in later this year to repair potholes. | 2012-07-22 | Expired
Asphalt | 880 | 77118 | 294 | 2004 | 2004-0294 | 6 | MAD-70-0.00 | ASPHALT CONCRETE(7 YEAR WARRANTY) westbound lanes 0.00 to 8.91 | 2006-11-29 | 7 | Review waived 2007 | 2008-04-14 | 2009-02-24 | 2010-04-22 | [19 empty] | 2/26/07--preliminary review of intermediate asphalt and all structures performed by project engr. Very minute scaling found on structures and core holes small potholes in asphalt will be fixed prior to surface course placement final c-85 issued 12/10/07 final work 11-19-07. 04/14/08 review asphalt cracking small amount of cracking but well under threshold limits. 09/14/09 county manager called and verified that mudflap hole was sealed by contractor using an a/c sealant. 03/15/2010--prelim inspection by county manager pot holes discovered will set up DRT review for April 2010. 04/22/10 contractor will be in later this year to repair potholes. | 2013-11-29 | Expired
Asphalt | 880 | 18249 | 560 | 2001 | 2001-0560 | 7 | MOT-IR75-29.305 (Stop Eight Rd to Sta 7+660) | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN - | 2005-07-18 | 7 | [24 empty] | 2012-07-18 | Expired
Asphalt | 880 | 17067 | 36 | 2006 | 2006-0036 | 7 | MOT-US35-015.07 (WB Sta 397+00 to 477+00) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-12-14 | 7 | [24 empty] | 2013-12-14 | Expired
Asphalt | 880 | 17067 | 36 | 2006 | 2006-0036 | 7 | MOT-US35-015.07 (WB 3000+10.34 to 3162+44.88, All WB pavement, Ramp I-75/35 WB Sta 3+13.59to4+13.59) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-12-14 | 7 | [24 empty] | 2013-12-14 | Expired
Asphalt | 880 | 17067 | 36 | 2006 | 2006-0036 | 7 | MOT-US35-015.07 (EB Sta2000+10.34to2162+62.67, EB ramps on sheets 199 221-224, Stave Wahalen Blvd) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-11-14 | 7 | [24 empty] | 2014-11-14 | Expired
Asphalt | 880 | 75927 | 387 | 2007 | 2007-0387 | 7 | MOT-IR75-013.11 (SB75 46ft lt to 86ft lt of CL Sta366+50 to 431+50) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-12-19 | 7 | [24 empty] | 2015-12-19 | Expired
Asphalt | 880 | 25869 | 1078 | 2010 | 2010-1078 | 4 | ATB-IR90-022.06 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2013-08-29 | 7 | 2014-07-15 | 2015-04-22 | [21 empty] | Held review 4/22/15 - Remedial action needed, letter sent to contractor 4/29/15 | 2020-08-29 | Under Warranty
Asphalt | 880 | 25869 | 1078 | 2010 | 2010-1078 | 4 | ATB-90-22.06 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2013-08-29 | 7 | 2014-07-15 | 2015-04-22 | [21 empty] | Held review 4/22/15 - Remedial action needed, letter sent to contractor 4/29/15 | 2020-08-29 | Under Warranty
Concrete | 884 | 6080 | 2 | 2006 | 2006-0002 | 4 | MAH IR 80 0097 (80 WB) | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | 2009-09-15 | 7 |  |  | 2012-04-18 | 2013-04-25 |  |  |  | 4/25/2013 - Cracking and Disintegrated Areas | [15 empty] | Completion Date 8/31/2009 Ref 136 | 2016-09-15 | Under Warranty
Asphalt | 880 | 18899 | 3003 | 2000 | 2000-3003 | 8 | PRE-IR70-000.00 | SPECIAL - MISC.: - PAVEMENT WITH 5 YEAR WARRANTY | 2001-12-19 | 5 | 04/23/03 review waived |  | 2005-04-27 | [5 empty] | Cracks were sealed | [15 empty] | 2006-12-19 | Expired
Asphalt | 880 | 19394 | 3004 | 2000 | 2000-3004 | 8 | GRE-US35-000.00 | SPECIAL - MISC.: - ASPHALT PAVEMENT WITH 7 YEAR WARRANTY | 2001-11-26 | 7 | 4/22/2003 review waived |  | 2005-04-28 |  | 2007-04-17 | 2008-04-28 |  |  | Seal Transverse Joints and cracking in wheel tracks | [14 empty] | Distresses encountered, contractor notified to submit plan for remedial action. | 2008-11-26 | Expired
Asphalt | 880 | 19786 | 3012 | 2000 | 2000-3012 | 8 | HAM-IR275-032.27 | SPECIAL - ASPHALT PAVEMENT (5 YEAR WARRANTY) - | 2003-07-31 | 5 |  |  |  | 2007-04-10 | 2008-04-22 |  |  | Cracks | None | [14 empty] | Transverse cracks noted, but not covered under the 5-year warranty of this project. | 2008-07-31 | Expired
Asphalt | 880 | 19705 | 3009 | 2001 | 2001-3009 | 8 | HAM-IR71-011.08 | SPECIAL - ASPHALT PAVEMENT (5 YEAR WARRANTY) - | 2002-03-14 | 5 | 4/16/2003 review waived |  | 2005-04-30 |  | 2007-03-07 |  |  |  | Patching at Structure Back walls | [15 empty] | 2007-03-14 | Expired
Asphalt | 880 | 78569 | 413 | 2006 | 2006-0413 | 8 | CLI-SR73-012.03 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-11-12 | 7 | [24 empty] | 2014-11-12 | Expired
Asphalt | 880 | 22386 | 414 | 2006 | 2006-0414 | 8 | HAM-IR275-021.52 | ASPHALT CONCRETE (7 YEAR WARRANTY) | Non performed | 7 | [25 empty] | Expired
Asphalt | 880 | 22386 | 414 | 2006 | 2006-0414 | 8 | HAM-IR275-021.52 | ASPHALT CONCRETE (5 YEAR WARRANTY) | Non performed | 5 | [25 empty] | Expired
Asphalt | 880 | 77221 | 138 | 2007 | 2007-0138 | 5 | LIC-161/37-6.65/10.25 Sta 356+00-654+00 | ASPHALT CONCRETE (7 YEAR WARRANTY) - Eastbound | 2009-07-31 | 7 |  | 2011-04-13 | 2012-04-17 |  | 2014-05-27 |  |  | 5/27/2014 - Cracking/Raveling | [16 empty] | 2016-07-31 | Expired
Asphalt | 880 | 77221 | 138 | 2007 | 2007-0138 | 5 | LIC-161/37-6.65/10.25 356+00-576+00 | ASPHALT CONCRETE (7 YEAR WARRANTY) - Westbound | 2010-05-04 | 7 | 2011-04-13 | 2012-04-17 |  | 2014-05-27 |  |  |  | 5/27/2014 - Cracking/Raveling | [16 empty] | 2017-05-04 | Under Warranty
Asphalt | 880 | 77221 | 138 | 2007 | 2007-0138 | 5 | LIC-161/37-6.65/10.25 576+00-654+00 | ASPHALT CONCRETE (7 YEAR WARRANTY) - Westbound | 2009-09-15 | 7 |  | 2011-04-13 | 2012-04-17 |  | 2014-05-27 |  |  | 5/27/2014 - Cracking/Raveling | [15 empty] | Cracking 7.15-7.35 | 2016-09-15 | Under Warranty
Asphalt | 880 | 75927 | 387 | 2007 | 2007-0387 | 7 | MOT-IR75-013.11 (SB Full Width Sta345+53to366+50, Remaining Sta 366+50to431+50 not completed 2008) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-11-23 | 7 | [24 empty] | 2016-11-23 | Under Warranty
Asphalt | 880 | 17045 | 114 | 2000 | 2000-0114 | 9 | ROS-US23-000.00 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2000-12-12 | 5 | 2001-04-23 | 2002-05-21 | 2003-04-23 | 2004-04-08 | 2005-04-11 |  | 2005-12-12 | [17 empty] | 2005-12-12 | Expired
Asphalt | 880 | 10904 | 304 | 2000 | 2000-0304 | 9 | BRO-US62-31.640 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2001-12-12 | 7 | Review Waived | Review Waived | Review Waived | Review Waived | Review Waived | Review Waived | 2009-12-09 |  | None | [14 empty] | No major problem areas. DRT recommends this project be released from warranty. | 2008-12-12 | Expired
Asphalt | 880 | 19146 | 563 | 2000 | 2000-0563 | 9 | SCI-US23-5.51 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2002-02-05 | 5 | 2003-05-28 | 2004-04-28 | 2005-04-25 | 2006-04-13 | 2007-02-28 |  | 2007-02-28 | minor cracking | None | [15 empty] | 2007-02-05 | Expired
Asphalt | 880 | 4804 | 154 | 2003 | 2003-0154 | 9 | SCI-SR335-003.78 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2005-05-27 | 7 | Review Waived | Review Waived |  |  |  |  | 2012-04-27 | [16 empty] | Released 4/30/12 - no distresses. | 2012-05-27 | Expired
Asphalt | 880 | 19642 | 285 | 2003 | 2003-0285 | 9 | LAW-SR7-7.25 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-11-21 | 7 |  | 2009-04-24 |  | 2011-04-07 |  | 2013-04-24 | 2014-11-13 | Cracking | Crack Sealing as per SS 825 | [14 empty] | Several cracks observed in the first .5 to .75 miles of the project in both directions. Contractor may consider crack sealing in this area. If the cracks open up or the pavement starts to disintegrate than this area will become a warranty issue. INSPECTION (4/7/2011): No warranty issues. | 2014-11-21 | Expired
Asphalt | 880 | 25174 | 407 | 2003 | 2003-0407 | 9 | SCI-US52-31.98 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) | 2003-10-24 | 5 | 2004-04-28 | 2005-04-25 | 2006-04-13 | 2007-04-16 |  |  | 2008-10-02 |  | None | [14 empty] | DRT recommends this area of this project be released from the extended warranty. | 2008-10-24 | Expired
Asphalt | 880 | 18492 | 533 | 2004 | 2004-0533 | 9 | ROS-207-0.00 | 880 - ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-10-25 | 7 | [6 empty] | 2014-11-17 | [16 empty] | Accident involving a car fire under a railroad bridge which damaged the pavement; this area was void from the warranty. | 2014-10-25 | Expired
Asphalt | 880 | 15926 | 120 | 1997 | 1997-0120 | 10 | MOE-SR7-34.129 | SPECIAL - ASPHALT CONCRETE MISC.: - ASPHALT CONCRETE WITH WARRANTY | 1998-04-29 | 5 | By Central Office | [23 empty] | 2003-04-29 | Expired
Asphalt | 880 | 12761 | 3003 | 2001 | 2001-3003 | 11 | TUS-IR77-003.94 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) - | 2002-08-26 | 7 | 2003-04-29 | 2005-04-25 | 2006-04-19 |  |  |  |  | Minor distress at this time | [16 empty] | 2009-08-26 | Expired
Asphalt | 880 | 20996 | 3008 | 2002 | 2002-3008 | 11 | TUS-IR77-007.55 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) - | 2004-05-15 | 7 | 2005-04-25 | 2006-04-19 |  |  |  |  | 2010-05-21 | [16 empty] | Warranty lifted as of 7/7/2011 per release letter from Christine Murgida, DCE D11 | 2011-05-15 | Expired
Asphalt | 880 | 75269 | 326 | 2003 | 2003-0326 | 11 | CAR-39-10.23 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B WITH SUPPLEMENT 1059 WARRANTY | 2004-01-30 | 3 | 2004-06-16 | 2005-04-25 | 2006-04-19 |  |  |  | 2006-10-12 | None at this time | [16 empty] | 2007-01-30 | Expired
Asphalt | 880 | 13000 | 621 | 1997 | 1997-0621 | 12 | CUY-IR480-010.38 | SPECIAL - ASPHALT CONCRETE, MISC.: - ASPHALT CONCRETE WITH WARRANTY | 1998-12-09 | 5 | [24 empty] | 2003-12-09 | Expired
Asphalt | 880 | 11738 | 558 | 2000 | 2000-0558 | 12 | CUY-IR90-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2002-11-15 | 7 | 2003-12-08 | [23 empty] | 2009-11-15 | Expired
Asphalt | 880 | 19509 | 96 | 2001 | 2001-0096 | 12 | CUY-SR176-012.76 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2002-06-07 | 5 | 2003-05-15 | [23 empty] | 2007-06-07 | Expired
Asphalt | 880 | 19509 | 96 | 2001 | 2001-0096 | 12 | CUY-SR176-012.76 | SPECIAL - CONCRETE BASE JOINT, CLEANED AND FILLED - ASPHALT WARRANTY | 2002-06-07 | 5 | [24 empty] | 2007-06-07 | Expired
Asphalt | 880 | 20800 | 108 | 2001 | 2001-0108 | 12 | CUY-IR90-013.41 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2002-07-18 | 5 | 2003-06-15 | [23 empty] | 2007-07-18 | Expired
Asphalt | 880 | 19514 | 205 | 2001 | 2001-0205 | 12 | CUY-US422-018.53 | ASPHALT CONCRETE (5 YEAR WARRANTY) - | 2002-11-12 | 5 | [24 empty] | 2007-11-12 | Expired
Asphalt | 880 | 20228 | 309 | 2001 | 2001-0309 | 12 | LOR-SR10-000.00 | ASPHALT CONCRETE (5 YEAR WARRANTY) | Assumed Expired | 5 | [25 empty] | Expired
Asphalt | 880 | 18393 | 485 | 2002 | 2002-0485 | 12 | CUY-IR480-012.76 | ASPHALT CONCRETE (7 YEAR WARRANTY) - | 2003-11-19 | 7 | [24 empty] | 2010-11-19 | Expired
Asphalt | 880 | 23129 | 80 | 2003 | 2003-0080 | 12 | LAK-IR90-006.71 | ASPHALT CONCRETE (7 YEAR WARRANTY) - , 17" | Assumed Expired | 7 | [25 empty] | Expired
Asphalt | 880 | 21751 | 117 | 2006 | 2006-0117 | 12 | CUY-480-15.81 (Ramps) | ASPHALT CONCRETE(7 YEAR WARRANTY) | 2007-04-10 | 7 | [24 empty] | 2014-04-10 | Expired
Asphalt | 880 | 21751 | 117 | 2006 | 2006-0117 | 12 | CUY-480-15.81 (Westbound) | ASPHALT CONCRETE(7 YEAR WARRANTY) | 2008-07-29 | 7 | [24 empty] | 2015-07-29 | Expired
Asphalt | 880 | 75927 | 387 | 2007 | 2007-0387 | 7 | MOT-IR75-013.11 (All NB Pavment Sta3456+53 to 431+50) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2010-11-02 | 7 | [24 empty] | 2017-11-02 | Under Warranty
Asphalt | 880 | 75315 | 286 | 2008 | 2008-0286 | 7 | CLA-IR70-020.92 (30' of pavement Sta1110+60to1332+00 WB & EB Center to outside edge) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-09-09 | 7 | [24 empty] | 2016-09-09 | Under Warranty
Asphalt | 880 | 24664 | 480 | 2007 | 2007-0480 | 8 | BUT-IR75-003.76 (North Section) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2010-11-09 | 7 | [24 empty] | 2017-11-09 | Under Warranty
Microsurf | 881 | 20735 | 776 | 1999 | 1999-0776 | 2 | OTT-SR2-023.41 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE - | 2000-11-14 | 3 | Review Waived | Review Waived | [22 empty] | 2003-11-14 | Expired
Microsurf | 881 | 20735 | 776 | 1999 | 1999-0776 | 2 | OTT-SR2-023.41 | MICROSURFACING WITH WARRANTY, SINGLE COURSE - | 2000-11-14 | 3 | Review Waived | Review Waived | [22 empty] | 2003-11-14 | Expired
Microsurf | 881 | 22753 | 222 | 2002 | 2002-0222 | 2 | OTT-SR163-004.01 | MICROSURFACING WITH WARRANTY, SINGLE COURSE - | 2003-01-30 | 3 | 2004-07-14 | 2005-05-24 | 2006-03-04 |  |  |  |  | Deficiencies observed not covered by warranty | None | [15 empty] | 2006-01-30 | Expired
Asphalt | 881 | 24117 | 453 | 2003 | 2003-0453 | 2 | D02-PS-FY2004(B) | MICROSURFACING WITH WARRANTY | 2004-11-15 | 3 | 2005-05-19 | 2006-03-04 | 2007-04-02 |  |  |  | 2007-11-14 | Delaminations | [15 empty] | Warranty released. | 2007-11-15 | Expired
Microsurf | 881 | 24560 | 61 | 2004 | 2004-0061 | 2 | D02-PS-FY2004 | MICROSURFACING WITH WARRANTY | 2004-08-31 | 3 | 2005-05-26 | 2006-03-04 | 2007-04-02 |  |  |  | 2007-08-31 | None | [16 empty] | 2007-08-31 | Expired
Microsurf | 881 | 76969 | 127 | 2005 | 2005-0127 | 2 | LUC-295-19.06 | MICROSURFACING WITH WARRANTY | 2005-08-24 | 3 | 2006-03-04 | 2007-04-02 |  |  |  |  | 2008-08-25 | [16 empty] | Warranty released. | 2008-08-24 | Expired
Microsurf | 881 | 24559 | 547 | 2005 | 2005-0547 | 2 | WOO-795-3.25 | MICROSURFACING WITH WARRANTY | 2006-08-29 | 3 | 2007-04-02 | [5 empty] | 2009-03-04 | [16 empty] | Pavement performing adequately. District assumes the maintenance responsibility of the project and relieves the contractor from the warranty. | 2009-08-29 | Expired
Micro-Surf. | 881 | 88536 | 374 | 2012 | 2012-0374 | 2 | HEN-65/18/65-0.00/16.55/14.58 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2012-09-14 | 2 | [6 empty] | 2012-11-20 | [17 empty] | 2014-09-14 | Expired
Microsurf | 881 | 21242 | 445 | 2000 | 2000-0445 | 3 | LOR-SR2-003.48 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE - | 2001-07-06 | 3 |  | 2003-05-01 | [22 empty] | 2004-07-06 | Expired
Microsurf | 881 | 24646 | 352 | 2003 | 2003-0352 | 3 | D03-MICRO-2004 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2003-10-08 | 2 | [24 empty] | 2005-10-08 | Expired
Microsurf | 881 | 76820 | 381 | 2004 | 2004-0381 | 3 | WAY-SR3-010.13 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 24650 | 421 | 2004 | 2004-0421 | 3 | D03-US30-003.82 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 25750 | 421 | 2005 | 2005-0421 | 3 | D03-SR0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 25753 | 409 | 2006 | 2006-0409 | 3 | D03-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 25756 | 550 | 2007 | 2007-0550 | 3 | D03-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Micro | 881 | 82220 | 8033 | 2010 | 2010-8033 | 3 | WAY-SR585-002.56 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2010-10-04 | 2 | [24 empty] | 2012-10-04 | Expired
Microsurf | 881 | 24671 | 47 | 2004 | 2004-0047 | 4 | MAH 680 6.61 | MICROSURFACING W/WARRANTY,SINGLE | 2004-08-24 | 2 | 2005-05-14 | 2006-04-06 | [21 empty] | Ref 7 | 2006-08-24 | Expired
Microsurf | 881 | 24671 | 47 | 2004 | 2004-0047 | 4 | MAH 680 6.61 | MICROSURFACING W/WARRANTY,SINGLE | 2004-08-24 | 2 | 2005-05-14 | 2006-04-06 | [22 empty] | 2006-08-24 | Expired
Microsurf | 881 | 76935 | 231 | 2004 | 2004-0231 | 5 | MUS-70-0.76 | MICRO-SURFACING WITH WARRANTY | 2005-10-06 | 3 | 2006-04-12 | 2007-04-27 | 2008-04-28 |  |  |  |  | minor cracking | Crack sealing | [14 empty] | Multiple areas of cracking on project on both eastbound and westbound sections (driving and passing lanes) | 2008-10-06 | Expired
Microsurf | 881 | 25883 | 167 | 2004 | 2004-0167 | 6 | PPM-D06-FY04 | Microsurfacing w/ warranty Multiple Fra-104 0.00 to 5.93 | 2004-09-27 | 3 | 2005-08-04 | 2006-03-22 | 2007-02-24 |  |  |  | Out of warranty 09/27/07 | [16 empty] | Letter to Shelly Company sent 11/24/08 starting 2 year warranty. See file concerning roadway condition prior to chipseal, contractor questioned using warranty on this project, roadway in poor condition county is already filling potholes this had extensiv--2/12/2009-SUBBASE PROBLEM NO FAULT OF CONTRACTOR | 2007-09-27 | Expired
Microsurf | 881 | 25883 | 167 | 2004 | 2004-0167 | 6 | PPM-D060FY04 | Microsurfacing w/warranty Multiple De;-36 11/29-18.35 | 2004-09-27 | 3 | 2005-08-04 | 2006-03-22 | 2007-04-13 |  |  |  | Out of warranty 09/27/07 | [16 empty] | Letter to Shelly Company sent 11/24/08 starting 2 year warranty. See file concerning roadway condition prior to chipseal, contractor questioned using warranty on this project, roadway in poor condition county is already filling potholes this had extensiv--2/12/2009 SUBBASE PROBLEM NO FAULT OF CONTRACTOR | 2007-09-27 | Expired
Microsurf | 881 | 25883 | 167 | 2004 | 2004-0167 | 6 | PPM-D06-FY04 | Microsurfacing w/warranty Multiple Fra-161 17.11 to 23.62 and ramps | 2004-09-27 | 3 | 2005-08-04 | 2006-03-22 | 2007-02-24 |  |  |  | Out of warranty 09/27/07 | [16 empty] | Letter to Shelly Company sent 11/24/08 starting 2 year warranty. See file concerning roadway condition prior to chipseal, contractor questioned using warranty on this project, roadway in poor condition county is already filling potholes this had extensive pavement repairs.C-85 issued 02/12/2009--SUBBASE PROBLEM NO FAULT OF CONTRACTOR | 2007-09-27 | Expired
Microsurf | 881 | 25883 | 167 | 2004 | 2004-0167 | 6 | PPM-D06-FY04 | MicrosuRFACING W/WARRANTY,MULTIPLE Madison 142 2.01 to 9.84 | 2004-09-27 | 3 | 2005-08-04 | 2006-03-14 | 2007-04-13 |  |  |  | Out of warranty 09/27/07 | [16 empty] | OUT OF WARRANTY | 2007-09-27 | Expired
Microsurf | 881 | 19431 | 355 | 2004 | 2004-0355 | 6 | DEL.-36-16.57 | MICROSURFACING W/WARRANTY,MULTIPLE | 2005-10-02 | 3 | Review Waived 2005 | 2006-03-08 | 2007-04-12 | 2008-02-25 |  |  | 2008-10-01 | OUT OF WARRANTY | [15 empty] | out of warranty | 2008-10-02 | Expired
Microsurf | 881 | 25886 | 111 | 2005 | 2005-0111 | 6 | D06PPM-FY05 | Micr Multi/Fay US 62 0.00-11.87 | 2005-09-12 | 3 | 2006-03-30 | 2007-04-05 | 2008-04-08 |  |  |  |  | missing material | yes | [14 empty] | 3/30/06-review no problems found3/19/07-- some cracking(not covered) at struct 6.5 equipment gashes from others, not contractor responsibility to repair. 04/08/08 review missing material 125' long 4' wide contractor to repair, will send letter giving date and repair method 5/13/08--Strawser in , cleaned out area where material had come out, tacked, placed microsufacing material in the delaminated area and also topped 10 wide by 125 ' long with second course.. May 13, 2008 repairs made by Strawser on SR 62 at the11.85 mm OUT OF WARRANTY LETTER SENT 11/13/08 AND SIGN REMOVAL LETTER | 2008-09-12 | Expired
Microsurf | 881 | 25886 | 111 | 2005 | 2005-0111 | 6 | D06PPM-FY05 | Micro Multi/Del-Mrw/IR71-11.82(Del-3.17Mrw | 2005-11-02 | 3 | 2006-03-15 | 2007-02-09 | 2008-03-05 | [20 empty] | county repaired pothole SB D/L 134 mm cracking occuring but not under warranty Del. Mrw has cracking (not covered) rutting 120 days after c-85 issued passed not under warranty VERY MINUTE BLEEDING/FLUSHING 3/15/2006 2/8/07 MRW section small bleeding areas about 4sf total and cracking which is not covered delaware portion cracking which is not covered overall okay. 03/05/08--some cracking but this is not warrantied, previous patch holding up will look at in oct 08 for final OUT OF WARRANTY LETTER SENT 11/13 08 AND SIGN REMOVAL LETTER | 2008-11-02 | Expired
Microsurf | 881 | 25886 | 111 | 2005 | 2005-0111 | 6 | D06PPM-FY05 | Micro Multi/Fra IR 270 Ramps J,O,Q | 2005-07-06 | 3 | 2006-03-24 | 2007-02-20 | 2008-03-14 | [20 empty] | 3/24/06--no distress types found2/20/07-- no distress types found, some cracking (not covered) 03/14/08--no distress types found will look at again in June 08 for final OUT OF WARRANTY LETTER SENT 11/13/08 AND SIGN REMOVAL LETTER | 2008-07-06 | Expired
Microsurf | 881 | 25886 | 111 | 2005 | 2005-0111 | 6 | D06PPM-FY05 | Micro Multi/Uni-US36-13.88-18.89 | 2005-08-02 | 3 | 2006-03-15 | 2007-03-06 | 2008-02-06 | [20 empty] | 3/6/07-cracking not covered under warranty-county crew is going to crackseal, 3/15/2006 SOME CRACKING(NOT COVERED UNDER WARRANTY) NO RUTTING NO DETERIORATION, MINUTE BLEEDING(UNDER THRESHOLD LIMIT. Small amount of cracking(not covered) everything else looks good. 02/06/08--county cracksealing operation caused some lose of material in areas the county forces will repair. will look at in july 08 for final OUT OF WARRANTY LETTER SENT 11/13/08 | 2008-08-02 | Expired
Asphalt | 881 | 82310 | 215 | 2008 | 2008-0215 | 6 | D06-PPM-FY08B | Microsurfacing--MAD-SR 38- 15.48 to 22.76 | 2008-08-08 | 2 | 2009-02-25 | 2010-03-15 | [21 empty] | 02/250/09-in good condition minor cracking not covered under warranty 03/15/2010--minor cracking discovered in prelim inspection by county manager, not a warranty issue goes out of warranty 8/2010 will revisit prior to. | 2010-08-08 | Expired
Micro | 881 | 82122 | 364 | 2009 | 2009-0364 | 6 | FRA-US40-004.45 | MICROSURFACING WITH WARRANTY, SINGLE COURSE, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Micro | 881 | 83732 | 120 | 2010 | 2010-0120 | 6 | D06-PPM-FY10B - FAY-SR 35- 24.05 TO 6.58 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2010-09-23 | 3 | [24 empty] | 2013-09-23 | Expired
Micro | 881 | 83732 | 120 | 2010 | 2010-0120 | 6 | D06-PPM-FY10B - FAY- SR 62 - 26.79 TO 12.17 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2010-09-23 | 3 | [24 empty] | 2013-09-23 | Expired
Micro | 881 | 83732 | 120 | 2010 | 2010-0120 | 6 | D06-PPM-FY10B - FRA- SR 674 - 4.54 TO 3.11 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2010-09-23 | 3 | [24 empty] | 2013-09-23 | Expired
Micro | 881 | 83732 | 120 | 2010 | 2010-0120 | 6 | D06-PPM-FY10B - UNI -SR 4 - 24.29 TO 10.68 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2010-09-23 | 3 | [24 empty] | 2013-09-23 | Expired
Micro | 881 | 83732 | 120 | 2010 | 2010-0120 | 6 | D06-PPM-FY10B - UNI - SR 31 - 20.38 TO 4.75 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2010-09-23 | 3 | [24 empty] | 2013-09-23 | Expired
Microsurf | 881 | 75430 | 342 | 2003 | 2003-0342 | 7 | AUG-IR75-0.00/4.45 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2003-09-11 | 3 | 2004-06-15 | 2005-06-22 | [22 empty] | 2006-09-11 | Expired
Microsurf | 881 | 25403 | 240 | 2004 | 2004-0240 | 7 | LOG-US33-010.71 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 25403 | 240 | 2004 | 2004-0240 | 7 | LOG-US33-010.71 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 75955 | 243 | 2004 | 2004-0243 | 7 | MOT-IR75-000.00 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 77577 | 5020 | 2004 | 2004-5020 | 7 | MOT-IR75-010.44 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 75780 | 285 | 2006 | 2006-0285 | 7 | MOT-IR70-000.00 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 16610 | 339 | 1997 | 1997-0339 | 8 | GRE-US42-003.59 | MICRO-SURFACING - WITH WARRANTY | 1999-09-10 | 3 | Review Waived | [7 empty] | Didn't know project was warranty | [15 empty] | 2002-09-10 | Expired
Microsurf | 881 | 76028 | 38 | 2004 | 2004-0038 | 9 | PIK-220-9.70 | MICRO-SURFACING WITH WARRANTY | 2004-05-17 | 3 | 2005-04-11 | 2006-04-24 | 2007-04-19 |  |  |  | 2007-04-19 |  | None | [14 empty] | Okay to release warranty on 5/17/07 | 2007-05-17 | Expired
Microsurf | 881 | 78479 | 177 | 2005 | 2005-0177 | 9 | BRO-32-11.11 | MICRO-RESURFACING WITH WARRANTY | 2005-06-24 | 3 | Review Waived | Review Waived |  |  |  |  | 2008-07-10 | [16 empty] | Warranty released. | 2008-06-24 | Expired
Asphalt | 880 | 24664 | 480 | 2007 | 2007-0480 | 8 | BUT-IR75-003.76 (South Section) | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-11-01 | 7 | [24 empty] | 2016-11-01 | Under Warranty
Microsurf | 881 | 77701 | 26 | 2005 | 2005-0026 | 10 | VIN-SR124-005.74 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 77700 | 28 | 2005 | 2005-0028 | 10 | ATH-SR144-000.00 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 20439 | 582 | 1999 | 1999-0582 | 12 | CUY-IR271-006.41 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE - | 1999-10-27 | 3 | Review Waived | 2001-05-01 |  |  |  |  | 2002-05-01 | [17 empty] | 2002-10-27 | Expired
Microsurf | 881 | 21744 | 502 | 2004 | 2004-0502 | 12 | CUY-IR71-005.72 | MICROSURFACING WITH WARRANTY, SINGLE COURSE, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Microsurf | 881 | 21744 | 502 | 2004 | 2004-0502 | 12 | CUY-IR71-005.72 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 20737 | 777 | 1999 | 1999-0777 | 2 | OTT-SR163-004.05 | SINGLE CHIP SEAL WITH WARRANTY - | 2000-09-18 | 3 | Review Waived | Review Waived | [22 empty] | 2003-09-18 | Expired
Chip Seal | 882 | 22787 | 220 | 2001 | 2001-0220 | 2 | SEN-SR19-006.07 | SINGLE CHIP SEAL WITH WARRANTY - | 2001-10-15 | 3 | 2002-04-12 | Review Waived | 2004-04-10 | [21 empty] | 2004-10-15 | Expired
Chip Seal | 882 | 22755 | 224 | 2002 | 2002-0224 | 2 | SEN-SR18-023.56 | SINGLE CHIP SEAL WITH WARRANTY - | 2003-01-30 | 3 | 2005-05-26 | 2006-03-04 | [22 empty] | 2006-01-30 | Expired
Chip Seal | 882 | 24118 | 61 | 2003 | 2003-0061 | 2 | D02-SR0-000.00 | SINGLE CHIP SEAL WITH WARRANTY - | 2003-07-31 | 3 | 2005-05-26 | 2006-03-04 | [22 empty] | 2006-07-31 | Expired
Chip Seal | 882 | 75163 | 479 | 2003 | 2003-0479 | 2 | D02-CHIP-FY2004 | SINGLE CHIP SEAL WITH WARRANTY - | 2004-07-29 | 3 | 2006-03-04 | 2007-04-02 | 2007-07-27 |  |  |  | 2007-07-27 | None | [16 empty] | 2007-07-29 | Expired
Asphalt | 882 | 25650 | 95 | 2007 | 2007-0095 | 2 | SEN-19-0.00 to 5.56 SEN-19-4.44 to 6.07 | DOUBLE CHIP SEAL WITH WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Chip Seal | 882 | 81964 | 399 | 2007 | 2007-0399 | 2 | D02-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 83603 | 89 | 2009 | 2009-0089 | 2 | SEN-SR19-009.58 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 76000 | 104 | 2010 | 2010-0104 | 2 | WIL-SR49-016.54 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2010-11-08 | 2 | Waived | [23 empty] | 2012-11-08 | Expired
Chip Seal | 882 | 88477 | 158 | 2011 | 2011-0158 | 2 | FUL-SR120-002.26 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Under Construction | 2
Chip Seal | 882 | 88503 | 324 | 2014 | 2014-0324 | 2 | SAN SR 412 0.00/8.72 Resurf | SINGLE CHIP SEAL WITH TWO YEAR WARR, APP | Under Construction | 2
Asphalt | 880 | 75971 | 246 | 2008 | 2008-0246 | 8 | BUT-IR75-005.91 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-11-01 | 7 | [24 empty] | 2016-11-01 | Under Warranty
Chip Seal | 882 | 21244 | 284 | 2000 | 2000-0284 | 3 | ASD-SR604-000.00 | SINGLE CHIP SEAL WITH WARRANTY - | 2000-11-24 | 3 | 2001-07-31 | 2002-08-20 | 2003-05-08 |  |  |  |  | loss of aggregate | apply chip seal to affected areas | [15 empty] | 2003-11-24 | Expired
Chip Seal | 882 | 21212 | 286 | 2000 | 2000-0286 | 3 | CRA-SR103-009.92 | SINGLE CHIP SEAL WITH WARRANTY - | 2000-09-30 | 3 | 2001-04-01 | 2002-05-22 | 2003-05-08 |  |  |  |  | none | [16 empty] | 2003-09-30 | Expired
Chip Seal | 882 | 21243 | 333 | 2000 | 2000-0333 | 3 | ASD-SR95-010.26 | SINGLE CHIP SEAL WITH WARRANTY - | 2000-09-08 | 3 | 2001-07-31 | 2002-08-20 | 2003-05-08 |  |  |  |  | loss of aggregare | apply chip seal to affected areas | [15 empty] | 2003-09-08 | Expired
Chip Seal | 882 | 24647 | 351 | 2003 | 2003-0351 | 3 | D03-CHIP-2004 | SINGLE CHIP SEAL WITH WARRANTY - | 2003-09-02 | 2 | [24 empty] | 2005-09-02 | Expired
Chip Seal | 882 | 24651 | 419 | 2004 | 2004-0419 | 3 | D03-SR303-000.00 | SINGLE CHIP SEAL WITH WARRANTY | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 25751 | 420 | 2005 | 2005-0420 | 3 | D03-SR0-000000 | SINGLE CHIP SEAL WITH WARRANTY | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 25754 | 424 | 2006 | 2006-0424 | 3 | D03-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 79949 | 340 | 2007 | 2007-0340 | 3 | D03-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 79949 | 340 | 2007 | 2007-0340 | 3 | D03-VA0-000000 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 80050 | 477 | 2008 | 2008-0477 | 3 | D03-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2009-06-03 | 2 | [24 empty] | 2011-06-03 | Expired
Chip Seal | 882 | 80055 | 410 | 2009 | 2009-0410 | 3 | HUR-SR269-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2010-07-26 | 2 | [24 empty] | 2012-07-26 | Expired
Chip Seal | 882 | 82222 | 8044 | 2010 | 2010-8044 | 3 | RIC-SR181-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2011-08-05 | 2 | [24 empty] | 2013-08-05 | Expired
Chip Seal | 882 | 81128 | 53 | 2007 | 2007-0053 | 4 | TRU VARIOUS | CHIP SEAL WITH WARRANTY | Assumed Expired | 2 | [23 empty] | Completion Date 6/30/2007 Ref 10 |  | Expired
Chip Seal | 882 | 79086 | 369 | 2008 | 2008-0369 | 5 | GUE-SR265-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 84000 | 399 | 2008 | 2008-0399 | 5 | GUE-SR821-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 81436 | 408 | 2008 | 2008-0408 | 5 | MUS-SR340-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 25886 | 111 | 2005 | 2005-0111 | 6 | D06PPM-FY05 | Single Chip Seal/Mad SR 665 2.47-11.11 | 2005-06-15 | 3 | 2006-03-14 | 2007-02-23 | 2008-03-03 | [20 empty] | micro coming up over pre-existing pavement markings which were not required to be removed by contractor prior to chipseal thus a debonding is occuring over the polyester markings not contractors responsibility as contract did not specifiy pavmeent marking removal prior to placement 2-2307-preliminary review by Cnty Mngr some minor cracking, minimal bleeding, coming up over previous striping which was not required to be removed thus not a warranty issue overall pavement is good shape 3/17/2006 03/03/08--chipseal coming off over the existing pavement markings that were not removed--ODOT responsiblity to fix not contractors, everything else looks good. OUT OF WARRANTY LETTER SENT 11/13/08 AND SIGN REMOVAL LETTER | 2008-06-15 | Expired
Chip Seal | 882 | 25806 | 266 | 2007 | 2007-0266 | 6 | Del/Mrw SR656/314 | Double Chip Seal Morrow-SR314-0.00-3.20 | 2008-09-08 | 2 | 2009-02-12 | 0315/2010 | [20 empty] | 4/3/08 REVIEW--ODOT RESPONSIBILIYTY, LOSS OF MATERIAL AND CRACKING IS BEING CAUSED BY UNDERLYING PROBLEM WITH EXISTING-CONCURRENCE BY AREA ENGINEER AND DRT TEAM. 7/18/08 notified by county manager excessive bleeding/flushing and loss of material from tracking--rereview set up for 7/31/08. -- Shelly Co. on August 12, 2008 attempted to repair bleeding/flushing by placing #8 stone in bleeding areas, using a pnuematic roller to vibrate in but this did not work. On August21, 2008 Shelly Co. returned for another attempt to repair using a method whereas they heated to #8 stone to 250-300% then placing on bleeding areas and rolling in using a pneumatic roller, according to our engineer on site this attempt did not work either. A letter to Shelly Company was sent on 8/21/08 (wrong date on letter 8/5/08) asking them to repspond with repair fix and timeframe for such. addended letter for date sent 8/25/08. Sept. 08' Shelly milled 12000 feet of out of warranty chip seal. Proj Engr and Cnty Manager satisfied with temporary fix will re-visit for final repairs next spring.. Areas restriped by contractor. | Letter to Shelly Company sent 11/24/08 starting 2 year warranty. See file concerning roadway condition prior to chipseal, contractor questioned using warranty on this project, roadway in poor condition county is already filling potholes this had extensive. 0315/2010 prelim with project engineer and couty manager, cracking and potholes due to preexisting condition , raodway was in very bad shape lots of repairs done prior to chipseal application, not a warranty issue. | 2010-09-08 | Expired
Chip Seal | 882 | 25806 | 266 | 2007 | 2007-0266 | 6 | Del/Mrw SR656/314 | Double Chip Seal Mrw-SR656-0.00-4.87 | 2008-09-08 | 2 | 2009-02-12 | 2010-03-15 | [21 empty] | Letter to Shelly Company sent 11/24/08 starting 2 year warranty. See file concerning roadway condition prior to chipseal, contractor questioned using warranty on this project, roadway in poor condition county is already filling potholes this had extensive. 0315/2010 prelim with project engineer and couty manager, cracking and potholes due to preexisting condition , raodway was in very bad shape lots of repairs done prior to chipseal application, not a warranty issue. | 2010-09-08 | Expired
Chip Seal | 882 | 25806 | 266 | 2007 | 2007-0266 | 6 | Del/Mrw SR656/314 | DoubleChip Seal Delaware-SR656-0.00-4.69 | 2008-09-08 | 2 | 2009-02-12 | 2010-03-23 | [20 empty] | 2008 REVIEW NO PROBLEMS FOUND. Received work from county manager that the chipseal (kAugust 08) was bleeding excessively. Contractor notified (could becomea safety issue) tried sanding, heating applying more 8's this didn't work. Scarified 12000', this took care of the bleeding issue(safety slick when becomes wet). County manager is satisfied will readdress problem in sping of 2009. | Letter to Shelly Company sent 11/24/08 starting 2 year warranty. See file concerning roadway condition prior to chipseal, contractor questioned using warranty on this project, roadway in poor condition county is already filling potholes this had extensive. 3/23/2010 prelim by county manager cracking and potholes from preexisting roadway condition, lots of pavement repair done priot to chipseal application. Not a warranty issue. | 2010-09-08 | Expired
Chip Seal | 882 | 25600 | 280 | 2007 | 2007-0280 | 6 | Pic-SR316-0.00 | Double Chip Seal/PIC-SR316-0.00-9.48 w/Polymer | 2007-09-11 | 2 | 2008-04-03 | 2009-04-29 | [5 empty] | LOSS/CRACKING7/18/08 bleeding flushing loss of material | [15 empty] | 4/3/08 REVIEW--ODOT RESPONSIBILIYTY, LOSS OF MATERIAL AND CRACKING IS BEING CAUSED BY UNDERLYING PROBLEM WITH EXISTING-CONCURRENCE BY AREA ENGINEER AND DRT TEAM. 7/18/08 notified by county manager excessive bleeding/flushing and loss of material from tracking--rereview set up for 7/31/08. -- Shelly Co. on August 12, 2008 attempted to repair bleeding/flushing by placing #8 stone in bleeding areas, using a pnuematic roller to vibrate in but this did not work. On August21, 2008 Shelly Co. returned for another attempt to repair using a method whereas they heated to #8 stone to 250-300% then placing on bleeding areas and rolling in using a pneumatic roller, according to our engineer on site this attempt did not work either. A letter to Shelly Company was sent on 8/21/08 (wrong date on letter 8/5/08) asking them to repspond with repair fix and timeframe for such. addended letter for date sent 8/25/08. Sept. 08' Shelly milled 12000 feet of out of warranty chip seal. Proj Engr and Cnty Manager satisfied with temporary fix will re-visit for final repairs next spring.. Areas restriped by contractor. MEETING SET FOR aPRIL 28, 2009 TO GO OVER WITH CONTRACTOR FIX TO WARRANTY FAILURE. 4/29/09 meeting with Shelly proposed single chip seal over milled areas--agreed to by DCE, to be done end of May 2009 09/01/09--Shelly Co. in, set up traffic control using signs, flaggers, cones for one lane moving operation closures. Swept off previously milled areas applied a/c and stone for a single chip seal, broomed off loose stone, came back in on 9/2/09 to broom again. Jim Cooperider of Shelly and Ron Duncan of ODOT on site. OUT OF WARRANTY LETTER SENT TO SHELLY CO. 9/3/09 AND SIGN REMOVAL LETTER TO TODD SEITER IN TRAFFIC out of warranty letter sent 10/09/09 | 2009-09-11 | Expired
Chip Seal | 882 | 25600 | 280 | 2007 | 2007-0280 | 6 | Pic-316-0.00 | Single Chip Seal/PIC-SR 752-0.00-1.82 w/Polymer | 2007-09-11 | 2 | 2008-02-05 | 2009-04-29 | [6 empty] | scarified 12000' | [14 empty] | 2008 REVIEW NO PROBLEMS FOUND. 04/29/09 no problems found out of warranty letter sent 10/9/09 | 2009-09-11 | Expired
Chip Seal | 882 | 83732 | 120 | 2010 | 2010-0120 | 6 | D06-PPM-FY10B: MAD- SR 323-0.00 TO 18.64 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2011-03-16 | 2 | [24 empty] | 2013-03-16 | Expired
Chip Seal | 882 | 75906 | 157 | 2009 | 2009-0157 | 8 | PRE-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 25832 | 398 | 2003 | 2003-0398 | 9 | SCI-SR348-0.00 | SINGLE CHIP SEAL WITH WARRANTY - | 2003-09-26 | 3 | 2004-04-28 | 2005-04-25 | 2006-04-13 |  |  |  | 2006-10-11 | Potholes, and underlaying pavement issues | None | [15 empty] | 2006-09-26 | Expired
Chip Seal | 882 | 75437 | 580 | 2003 | 2003-0580 | 9 | PIK-23-5.23 | SINGLE CHIP SEAL WITH WARRANTY | 2004-08-18 | 3 | Review Waived | Review Waived | 2007-04-19 |  |  |  | 2007-08-31 |  | None | [14 empty] | DRT results okay. Will schedule 1 more review before warranty expires. | 2007-08-18 | Expired
Chip Seal | 882 | 21425 | 10 | 2004 | 2004-0010 | 9 | LAW-52-11.85 | SINGLE CHIP SEAL WITH WARRANTY | 2004-10-20 | 3 | Review Waived | Review Waived | 2007-04-05 | [5 empty] | None | [14 empty] | DRT results okay. Will schedule 1 more review before warranty expires. | 2007-10-20 | Expired
Chip Seal | 882 | 76027 | 35 | 2004 | 2004-0035 | 9 | JAC-233-0.00 | DOUBLE CHIP SEAL WITH WARRANTY - | 2004-07-24 | 3 | 2005-04-29 | Review Waived | 2006-08-21 | 2007-03-23 |  |  | 2007-07-24 | 150 ft. area exhibits bleeding/flushing | chip seal remedial action btwn. 5/1-9/1 | [14 empty] | chip seal remedial action btwn. 5/1-9/1, All redial action performed 8/26/2006 | 2007-07-24 | Expired
Chip Seal | 882 | 21730 | 520 | 2004 | 2004-0520 | 9 | JAC-32-17.41 | SINGLE CHIP SEAL WITH WARRANTY | 2005-11-08 | 3 | Review Waived | 2007-03-23 |  |  |  |  | 2008-12-08 |  | None | [14 empty] | DRT results okay. Recommendation of DRT to release pavement from warranty. | 2008-11-08 | Expired
Chip Seal | 882 | 77301 | 42 | 2005 | 2005-0042 | 9 | LAW-141-16.37 | SINGLE CHIP SEAL WITH WARRANTY | 2005-07-21 | 3 | Review Waived | 2007-04-05 |  |  |  |  | 2008-08-07 | [16 empty] | DRT results okay; DRT recommends project be released from warranty. | 2008-07-21 | Expired
Chip Seal | 882 | 77301 | 42 | 2005 | 2005-0042 | 9 | SCI-772-0.00 | SINGLE CHIP SEAL WITH WARRANTY | 2005-07-21 | 3 | 2006-04-26 | Review Waived, pending corrective work to be performed |  |  |  |  | 2008-08-07 | Streaking, loss of aggregate | chip seal remedial action btwn. 5/1-9/1 | [14 empty] | chip seal remedial action btwn. 5/1-9/1, 2007; DRT recommends project be released from warranty. | 2008-07-21 | Expired
Chip Seal | 882 | 77301 | 42 | 2005 | 2005-0042 | 9 | PIK-772-0.00 | SINGLE CHIP SEAL WITH WARRANTY | 2005-07-21 | 3 | 2006-04-26 | Review Waved |  |  |  |  | 2008-08-07 | [16 empty] | Warranty released. | 2008-07-21 | Expired
Chip Seal | 882 | 78961 | 513 | 2005 | 2005-0513 | 9 | ROS-772-0.00 | SINGLE CHIP SEAL WITH WARRANTY | 2006-08-11 | 3 | 2007-04-27 | [7 empty] | None | [14 empty] | DRT results okay. | 2009-08-11 | Expired
Chip Seal | 882 | 78961 | 513 | 2005 | 2005-0513 | 9 | ROS-772-0.00 | SINGLE CHIP SEAL WITH WARRANTY | 2006-08-11 | 2 | 2007-04-27 | [5 empty] | 2008-08-15 |  | None | [14 empty] | Warranty released. | 2008-08-11 | Expired
Chip Seal | 882 | 78962 | 588 | 2005 | 2005-0588 | 9 | ADA-73-0.00/7.96/10.26 | SINGLE CHIP SEAL WITH WARRANTY | 2006-08-10 | 3 | Review Waived | [23 empty] | 2009-08-10 | Expired
Chip Seal | 882 | 78962 | 588 | 2005 | 2005-0588 | 9 | ADA-73-0.00/7.96/10.26 | SINGLE CHIP SEAL WITH WARRANTY | 2006-08-10 | 2 | 2008-04-09 | [5 empty] | 2008-08-15 | Depressions | [15 empty] | Areas where the chip-n-seal has popped off over top of the stripe on the underlying pavement. It appears the lande width was increased after the chip-n-seal. There are depressions where the RPM's were removed. | 2008-08-10 | Expired
Chip Seal | 882 | 25836 | 113 | 2007 | 2007-0113 | 9 | BRO SR-774 003.24 | SINGLE CHIP SEAL WITH TWO YEAR WARR, APP | 2007-07-26 | 2 | 2009-05-08 | [22 empty] | Areas where the chip seal has come off the underlying striping but these areas do not approach the threshold limits of the warranty. | 2009-07-26 | Expired
Chip Seal | 882 | 78194 | 417 | 2007 | 2007-0417 | 9 | ADA SR-52 022.97 | SINGLE CHIP SEAL WITH TWO YEAR WARR | 2008-07-07 | 2 | 2009-04-09 | [5 empty] | Pike/Ross: 7/13/2010 Adams: 7/26/2010 | None | None | [14 empty] | Chip seal looks really good. Full coverage of aggregate throughout the project including sharp curves. | 2010-07-07 | Expired
Chip Seal | 882 | 75446 | 632 | 2008 | 2008-0632 | 9 | HIG-SR247-004.17 | CHIP SEAL, MISC.: | Assumed Expired | 2 | [25 empty] | Expired
Chip Seal | 882 | 78164 | 283 | 2009 | 2009-0283 | 9 | LAW-141-8.43 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2009-09-15 | 2 | 2011-04-07 | [5 empty] | 2011-09-20 | [16 empty] | INSPECTION (4/7/2011): A few areas where the chip seal has come off of the underlying striping, small and intermittent. NO warranty issues at this time. FINAL (9/20/11) DRT recommends release from warranty. | 2011-09-15 | Expired
Chip Seal | 882 | 79967 | 334 | 2009 | 2009-0334 | 9 | HIG-SR-506-0.00 | SINGLE CHIP SEAL WITH TWO YEAR WARR | 2009-09-21 | 2 | 2010-07-13 | 5/5/2011 & 5/9/2011 |  |  |  |  | 2011-08-10 | Area of concern: Bleeding | [15 empty] | First year review: bleeding area of concern. Recommend repair. Remedial Action plan must be submitted prior to performing work. (5/5/2011): Some areas of chip seal have come off over top of the original stripes, no warranty issues at this time. | 2011-09-21 | Expired
Chip Seal | 882 | 87398 | 278 | 2010 | 2010-0278 | 9 | JAC-Lake Katharine State Nature Preserve | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2010-10-15 | 2 | 2011-05-06 | [5 empty] | 2012-10-04 | [16 empty] | No warranty issues | 2012-10-15 | Expired
Chip Seal | 882 | 79969 | 459 | 2010 | 2010-0459 | 9 | D9 Various Chip Seal | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2011-08-04 | 2 | 2012-04-27 | [5 empty] | 2014-07-02 | [16 empty] | No Warranty issues. Final release letter sent 7/12/13. | 2013-08-04 | Expired
Chip Seal | 882 | 81735 | 622 | 2011 | 2011-0622 | 9 | D09-CHIP-FY2012 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2012-09-11 | 2 | 2013-04-26 | 2014-04-22 |  |  |  |  | 2014-09-11 | 4/26/2013-Some discolored joints but there appears to be no loss of aggregate. | [15 empty] | No warranty issues. Final release letter sent 9/16/2014 | 2014-09-11 | Expired
Chip Seal | 882 | 83083 | 195 | 2013 | 2013-0195 | 9 | DO9-CHIP-FY2013 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2013-09-17 | 2 | [6 empty] | 2015-08-26 | [16 empty] | SCI-371-0.00-0.40) was inspected on 4/17/15 and found to have chip-and-seal performing as intended. Final inspection to be done in August of 2015 | 2015-09-17 | Expired
Chip Seal | 882 | 83083 | 195 | 2013 | 2013-0195 | 9 | DO9-CHIP-FY2013 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2013-09-17 | 2 | [6 empty] | 2015-09-29 | [16 empty] | SCI-371-0.00-0.40) was inspected on 4/17/15 and found to have chip-and-seal performing as intended. Final inspection to be done in August of 2015 | 2015-09-17 | Expired
Chip Seal | 882 | 83083 | 195 | 2013 | 2013-0195 | 9 | DO9-CHIP-FY2013 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2013-09-17 | 2 | [6 empty] | 2015-10-08 | [16 empty] | SCI-371-0.00-0.40) was inspected on 4/17/15 and found to have chip-and-seal performing as intended. Final inspection to be done in August of 2015 | 2015-09-17 | Expired
Crack Seal | 883 | 21211 | 299 | 2000 | 2000-0299 | 3 | RIC-US30-003.46 | CRACK SEALING WITH WARRANTY, TYPE II OR III - | 2000-08-24 | 2 | 2001-04-01 | 2002-04-01 | [22 empty] | 2002-08-24 | Expired
Crack Seal | 883 | 20221 | 8002 | 2000 | 2000-8002 | 3 | RIC-IR71-000.00 | CRACK SEALING WITH WARRANTY, TYPE II OR III - | 2000-08-02 | 2 | [24 empty] | 2002-08-02 | Expired
Crack Seal | 883 | 20220 | 8003 | 2000 | 2000-8003 | 3 | WAY-IR71-000.00 | CRACK SEALING WITH WARRANTY, TYPE II OR III - | 2000-09-30 | 2 | 2001-04-01 | 2002-04-01 | [22 empty] | 2002-09-30 | Expired
Crack Seal | 883 | 22599 | 167 | 2001 | 2001-0167 | 3 | ASD-SR60-001.49 | CRACK SEALING WITH WARRANTY, MISC.: - TYPE II OR TYPE III | 2001-09-27 | 2 | 2002-04-01 | 2003-04-01 | [22 empty] | 2003-09-27 | Expired
Crack Seal | 883 | 21023 | 257 | 2000 | 2000-0257 | 5 | LIC-SR13-000.00 | CRACK SEALING WITH WARRANTY, TYPE II - | 2001-05-02 | 2 | 2002-04-30 | [5 empty] | 2003-04-30 | [17 empty] | 2003-05-02 | Expired
Concrete | 884 | 10289 | 199 | 2001 | 2001-0199 | 1 | WYA-US30-28.009 | 260 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | Assumed Expired | 7 | 2006-04-14 | [6 empty] | Slight cracking | [17 empty] | Expired
Asphalt | 880 | 10754 | 171 | 2009 | 2009-0171 | 8 | WAR-IR75-003.40 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 11/12/11 & 8/7/12 | 7 | [23 empty] | South bound started on 11/21/11 and north bound started on 8/7/12 | 11/21/18 & 8/7/19 | Under Warranty
Concrete | 884 | 24664 | 480 | 2007 | 2007-0480 | 8 | BUT-IR75-003.76 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-12-17 | 7 | [24 empty] | 2016-12-17 | Under Warranty
Concrete | 884 | 13458 | 323 | 2000 | 2000-0323 | 4 | SUM-IR76-24.799 | 350 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | Voided | 7 | Warranty Waived | [22 empty] | Ref 108, 109 Warranty Waived |  | Expired
Concrete | 884 | 18687 | 45 | 2002 | 2002-0045 | 4 | POR-IR76-001.09 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2003-08-22 | 7 | [24 empty] | 2010-08-22 | Expired
Concrete | 884 | 18687 | 45 | 2002 | 2002-0045 | 4 | POR-IR76-001.09 | 14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2004-07-07 | 7 | [24 empty] | 2011-07-07 | Expired
Concrete | 884 | 19920 | 45 | 2002 | 2002-0045 | 4 | POR IR-76 1.09 | 14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | 2005-06-25 | 7 | 2006-07-31 | 2007-04-27 | [21 empty] | Refs 59,60 | 2012-06-25 | Expired
Concrete | 884 | 22364 | 118 | 2003 | 2003-0118 | 4 | POR SR-43 8.14 | 14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | 2004-06-25 | 7 | 2006-08-16 | 2007-04-27 | [21 empty] | Ref 92 | 2011-06-25 | Expired
Concrete | 884 | 18696 | 464 | 2003 | 2003-0464 | 4 | MAH IR-76 3.08 | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | 2005-12-08 | 7 | 2006-08-02 | 2007-04-24 | [21 empty] | Westbound - December 9, 2004; 13" Ref 86 Eastbound – December 8, 2005 11" Ref 85 | 2012-12-08 | Expired
Concrete | 884 | 24591 | 108 | 2005 | 2005-0108 | 4 | ATB IR 90 3.70 (EB) | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | Voided | 7 | [23 empty] | Ref 151 |  | Expired
Concrete | 884 | 24591 | 108 | 2005 | 2005-0108 | 4 | ATB IR 90 3.70 (WB) | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | Voided | 7 | [23 empty] | Ref 151 |  | Expired
Concrete | 884 | 10754 | 171 | 2009 | 2009-0171 | 8 | WAR-IR75-003.40 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 11/12/11 & 8/7/12 | 7 | [23 empty] | South bound started on 11/21/11 and north bound started on 8/7/12 | 11/21/18 & 8/7/19 | Under Warranty
Concrete | 884 | 6080 | 2 | 2006 | 2006-0002 | 4 | MAH IR 80 0097 (80 EB & 680 WB) | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR) | 2007-11-03 | 7 |  |  |  |  | 2012-04-18 | 2013-04-25 |  | 4/25/2013 - Cracking and Disintegrated Areas | [15 empty] | Completion Date 8/31/2009 Ref 136 | 2014-11-03 | Expired
Concrete | 884 | 16671 | 463 | 2003 | 2003-0463 | 6 | FRA-IR270-0.60 (WB Lanes) | PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | 2004-11-23 | 7 | Review waived 2005 | 2006-03-22 | 2007-03-01 | 2008-03-13 | 2009-03-30 | 2010-05-06 | [17 empty] | 3/22/06-drt team no osigns of distress types noted 03/01/07 NO PROBLEMS AT THIS TIME 03/13/08--review previous joint sealer okay no distress items found 03/30/09 PAVEMENT OKAY May 6, 2010--warranty review with contractor in attendance potholes, cracking of concrete pavement. Pictures e-mailed to J. Thompson of Complete General . Letter of findings sent 6/13/10 to contractor. 1.3 mm outside 2 lanes potholes at longitudinal joint between two lanes tie bars visible closte to surface. | 2011-11-23 | Expired
Concrete | 884 | 16671 | 463 | 2003 | 2003-0463 | 6 | FRA-IR270-0.60 (WB Lanes) | PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | 2005-11-15 | 7 | 2006-03-22 | 2007-03-01 | 2008-03-13 | 2009-03-30 | 2010-05-06 | [18 empty] | 3/22/2006--drt team no signs of distress types noted 03/01/07 NO PROBLEMS AT THIS TIME 03/13/08--review no distress types found 03/30/09 PAVEMENT OKAY May 6, 2010--warranty review with contractor in attendance potholes, cracking of concrete pavement. Pictures e-mailed to J. Thompson of Complete General . Letter of findings sent 6/13/10 to contractor. 1.91 wb disitergration at edges of 4 slbs against expansion joint p same location 2 slabs inside shoulder longitudinal craclking supple 884 all 6 should be replaced and 2.1 wb pot holes at edge of 2 slabs , 1 slab inside should and 1 outside pots holes, per 884 all 4 should be replaced. | 2012-11-15 | Expired
Concrete | 884 | 77118 | 294 | 2004 | 2004-0294 | 6 | MAD-70-0.00 | PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | Non performed | 7 | not a warranty item | bid option contract | [21 empty] | NOT A WARRANTY PROJECT HAD BID OPTION |  | Expired
Concrete | 884 | 11160 | 3001 | 1999 | 1999-3001 | 7 | MIA IR-75 004.94 | PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | 2005-02-01 | 7 | 2005-05-09 | 2007-09-11 | [5 empty] | Longitudenal cracks in several panels | Patching temporarily, panel replacement before end of waranty period | [15 empty] | 2012-02-01 | Expired
Concrete | 884 | 22935 | 465 | 2005 | 2005-0465 | 7 | MOT-IR70-017.04 (EB&WB - Inside shoulder and high spped lane: 60') | 14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-12-19 | 7 | [24 empty] | 2013-12-19 | Expired
Concrete | 884 | 22935 | 465 | 2005 | 2005-0465 | 7 | MOT-IR70-017.04 (EB&WB - Middle lane, Right lane, Rt shoulder, and all ramps except SR235 interchg) | 14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2008-09-09 | 7 | [24 empty] | 2015-09-09 | Expired
Concrete | 884 | 25523 | 7 | 2005 | 2005-0007 | 8 | CLE-275-13.79 | CONCRETE PAVEMENT WITH WARRANTY | 2006-10-31 | 7 |  | 2008-04-22 | [5 empty] | None | None | [15 empty] | 2013-10-31 | Expired
Micro-Surf. | 881 | 84646 | 306 | 2014 | 2014-0306 | 9 | D09 Microsurfacing Project 2014 | MICROSURFACING W/ WARRANTY, SINGLE | 2014-10-16 | 4 | 2015-04-28 | 2016-04-28 | [5 empty] | Cracks were observed on all routes. The cracks appear to be caused by the underlying pavement condition. No warranty issues after first inspections | [15 empty] | Waiting on final completion date and warranty start date. 12/9/14 - Currently under dispute | 2018-10-16 | Under Warranty
Asphalt | 880 | 21751 | 117 | 2006 | 2006-0117 | 12 | CUY-480-15.81 (Eastbound) | ASPHALT CONCRETE(7 YEAR WARRANTY) | 2009-06-12 | 7 | [24 empty] | 2016-06-12 | Expired
Concrete | 884 | 17440 | 248 | 2000 | 2000-0248 | 10 | WAS-IR77-006.59 | 11" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | 2000-12-18 | 7 | 2001-04-21 |  | 2003-04-24 |  |  |  | 2007-05-30 | Some cracking | Crack repair | [14 empty] | project notes there is spalling on deck will look at in spring of 06. final inspection was not done until 11-21-05 | 2007-12-18 | Expired
Concrete | 884 | 17440 | 248 | 2000 | 2000-0248 | 10 | WAS-IR77-006.59 | 8" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | 2000-12-18 | 7 | 2001-04-21 |  | 2003-04-24 |  |  |  | 2007-05-30 | Corner cracks/Pop-outs | None Required | [15 empty] | 2007-12-18 | Expired
Concrete | 884 | 19905 | 3001 | 2000 | 2000-3001 | 10 | NOB-IR77-006.22 |  | 2001-12-31 | 7 | 2001-03-27 |  | 2003-04-14 | 2007-05-22 | 2007-08-03 | 2008-04-18 |  | Some transverse and longitudinal cracks | Two cracks were removed and repaired. Contractor only responsible for one crack. (5/9/2008) - Slab cracking at various locations. Repair using item 255 and/or 256. | [14 empty] | (4/18/2008): Remedial action action required (repairs using item 255/256 to repair cracks). | 2008-12-31 | Expired
Concrete | 884 | 19738 | 145 | 2001 | 2001-0145 | 10 | MEG-SR124-031.57 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - 10" by VECP | 2003-06-25 | 7 | 2005-11-23 | 2007-04-17 |  |  |  |  | 2007-07-17 | Longitudinal cracking, 2" separation in places, some expansion joint failures, midslab cracking | Repair cut tie bar areas | [14 empty] | Warranty terminated due to excessive ESAL's. | 2010-06-25 | Expired
Concrete | 884 | 19718 | 229 | 2001 | 2001-0229 | 10 | MEG-SR124-022.72 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | 2004-10-14 | 7 | 2005-11-23 | [6 empty] | Several Expansion joint problems | [16 empty] | 2011-10-14 | Expired
Concrete | 884 | 18288 | 246 | 2001 | 2001-0246 | 10 | ATH-US33-40.981 | 225 MM PORTLAND CEMENT CONCRETE PAVEMENT(7 YEAR WARRANTY) - | 2004-10-22 | 7 | 2007-06-17 | [22 empty] | The ESAL increased by more than 20%. 884 Supplemental Spec notes that if the ESAL increases more than 20% the remaining warranty shall be waived. | 2011-10-22 | Expired
Concrete | 884 | 19719 | 403 | 2001 | 2001-0403 | 10 | MEG-SR124-026.66 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) - | 2004-10-14 | 7 | 2005-11-23 | [6 empty] | Hot applied sealer missing | [16 empty] | 2011-10-14 | Expired
Concrete | 884 | 18287 | 425 | 2001 | 2001-0425 | 10 | ATH-US33-30.981 | 225 MM PORTLAND CEMENT CONCRETE PAVEMENT(7 YEAR WARRANTY) - | 2005-02-23 | 7 | [24 empty] | 2012-02-23 | Expired
Concrete | 884 | 18287 | 425 | 2001 | 2001-0425 | 10 | ATH-US33-30.981 | 250 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEARWARRANTY) - | 2005-02-23 | 7 | [23 empty] | The referenced project has experienced an increase in ESAL by more than 20%. The 884 supplemental specification notes that if ESAL increases by more than 20% the remaining warranty shall be waived. | 2012-02-23 | Expired
Concrete | 884 | 76160 | 3000 | 2005 | 2005-3000 | 10 | NOB-IR77-6.59 | ASPHALT OR CONCRETE PAVEMENT? (7 YEAR WARRANTY) | 2006-11-27 | 7 |  | 2008-04-18 | 2009-04-22 |  |  | 2012-04-17 | 2014-04-30 | Cracking 4/17/12: Transverse Cracking 428+07, 579+65, 673+75, 674+00, 647+60: Resotre Load Transfer (Item 255). Disentegratinmg 381+50NB - Concrete Bonding or Full Depth Repair. | 4/17/12: Transverse Cracking 428+07, 579+65, 673+75, 674+00, 647+60: Resotre Load Transfer (Item 255). Disentegratinmg 381+50NB - Concrete Bonding or Full Depth Repair. | [14 empty] | Traverse Cracks at Stations 551+35 North Bound Driving & Passing Lane and 4' shoulder, 872+90 4' shoulder, 873+08 NBPL & 4' shoulder, NB exit 16 ramp @ beginning of gore in 8' shoulder and 16' ramp lane, 67+85 SBD, P & 10' & 4' shoulders, 68+35 SBD, P & 10' & 4' shoulders, 69+50 SB 4' shoulder and 2070+30 SBD, P & 10' shoulder. Longitudinal cracks at Sta. 376+70 NBDL & 437+70 NBDL were <1/16" | 2013-11-27 | Expired
Concrete | 884 | 5774 | 518 | 2005 | 2005-0518 | 12 | LAK-IR90-6.71 Westbound | CONCRETE PAVEMENT WITH WARRANTY | 2006-12-21 | 7 | [24 empty] | 2013-12-21 | Expired
Concrete | 884 | 5774 | 518 | 2005 | 2005-0518 | 12 | LAK-IR90-6.71 (Eastbound) | CONCRETE PAVEMENT WITH WARRANTY | 2007-11-28 | 7 | [24 empty] | 2014-11-28 | Expired
Asphalt | 880 | 22222 | 211 | 2008 | 2008-0211 | 12 | CUY-IR77-001.89 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2009-11-24 | 7 | [23 empty] | Pleasant Valley Road to Rockside Road | 2016-11-24 | Under Warranty
Painting | 885 | 15992 | 119 | 2000 | 2000-0119 | 1 | WYA-SR37-14.806 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-07-14 | 5 | 2001-05-08 | 2001-05-13 | [22 empty] | 2005-07-14 | Expired
Painting | 885 | 21152 | 3014 | 2000 | 2000-3014 | 1 | HAN-SR103-016.57 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-11-01 | 5 | 2002-05-10 | 2003-04-22 | 2004-04-18 | 2006-03-27 | [5 empty] | HAN-SR103-016.57 | [13 empty] | Under review by CO | 2006-11-01 | Expired
Painting | 885 | 76681 | 107 | 2008 | 2008-0107 | 1 | DEF-SR281-001.23 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed | 5 | [23 empty] | The mainline there was three areas of remove and replace |  | Expired
Painting | 885 | 76681 | 107 | 2008 | 2008-0107 | 1 | DEF-SR281-001.23 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 76681 | 107 | 2008 | 2008-0107 | 1 | DEF-SR281-001.23 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 76681 | 107 | 2008 | 2008-0107 | 1 | DEF-SR281-001.23 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Painting | 885 | 76681 | 107 | 2008 | 2008-0107 | 1 | DEF-SR281-001.23 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 76681 | 107 | 2008 | 2008-0107 | 1 | DEF-SR281-001.23 | FINAL INSPECTION REPAIR | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 20211 | 655 | 1999 | 1999-0655 | 2 | SAN-US6-014.76 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-11-14 | 5 | 1 month Prior to Warranty Expirartion (Oct 2005) |  |  |  |  | 2004-06-28 | By Central Office | Paint peeling / Rust | Repair Paint | 7201834 SAN-20-14.86 | 7200277 SAN-6-14.76L | 7200307 SAN-6-14.76R | 7200331 SAN-6-14.89 | [10 empty] | Under review by CO | 2005-11-14 | Expired
Painting | 885 | 20225 | 656 | 1999 | 1999-0656 | 2 | SAN-US20-021.31 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-11-14 | 5 | 1 month Prior to Warranty Expirartion (Oct 2005) |  |  |  |  | 2004-06-28 | By Central Office | Paint peeling / Rust | Repair Paint | 7201109 SAN-19-10.79 | 7202679 SAN-412-0.22 | 7202253 SAN-53-10.64 | 7202016 SAN-20-21.31R | [10 empty] | Under review by CO | 2005-11-14 | Expired
Painting | 885 | 20667 | 763 | 1999 | 1999-0763 | 2 | LUC-IR75-001.99 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-01-02 | 5 | 1 month Prior to Warranty Expirartion (Dec. 2005) |  |  |  |  | 2004-06-30 |  |  |  | 4803000 LUC-75-1.99 | 4803094 LUC-75-2.34 | 4805496 LUC-246-5.84 | [11 empty] | Under review by CO | 2006-01-02 | Expired
Painting | 885 | 19358 | 274 | 2000 | 2000-0274 | 2 | LUC-US20-009.54 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-08-21 | 5 | 1 month Prior to Warranty Expiration (July 2006) | [8 empty] | 4800605 LUC-20-9.54 | [13 empty] | Under review by CO | 2006-08-21 | Expired
Painting | 885 | 81567 | 340 | 2008 | 2008-0340 | 2 | LUC-IR475-014.53 | FINAL INSPECTION REPAIR | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 18286 | 302 | 2000 | 2000-0302 | 3 | ASD-US30-09.484 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-11-28 | 5 | 2006-10-15 | [8 empty] | ASD-US30-05.87L | ASD-US30-05.87R | ASD-US30-06.14 | ASD-US30-06.54 | [10 empty] | Under review by CO | 2006-11-28 | Expired
Painting | 885 | 18951 | 246 | 2006 | 2006-0246 | 3 | D03-VA0-000000 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed | 3 | [25 empty] | Expired
Painting | 885 | 18951 | 246 | 2006 | 2006-0246 | 3 | D03-VA0-000000 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 18951 | 246 | 2006 | 2006-0246 | 3 | D03-VA0-000000 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 18951 | 246 | 2006 | 2006-0246 | 3 | D03-VA0-000000 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Assumed Expired | 5 | [25 empty] | Expired
Painting | 885 | 18951 | 246 | 2006 | 2006-0246 | 3 | D03-VA0-000000 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 18951 | 246 | 2006 | 2006-0246 | 3 | D03-VA0-000000 | FINAL INSPECTION REPAIR | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 13458 | 323 | 2000 | 2000-0323 | 4 | SUM-IR76-24.799 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-10-11 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | SFN 7706758 WB, Over SR 532, SUM-IR76-16.97 | SFN 7706782 EB Over SR 532, SUM-IR76-17.72 | SFN 7706812 Eastwood Ave, SUM-76-27.326R | 7706847, Over Eastwood Ave, SUM-IR76-28.533R | NO WORK 7706693 Under Munroe Falls Rd | NO WORK 7706723 Under Newton St | [8 empty] | Ref's 172-175, 328-330 & 202-205 SFN 7706758(10/31/01); Ref's 231-234, 334-336 & 262-265 SFN 7706812(10/11/01), * No longer on Bridge Inventory due to widening of original structures | 2006-10-11 | Expired
Painting | 885 | 18375 | 406 | 2000 | 2000-0406 | 4 | POR-IR76-013.55 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-10-05 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 6702791 WB, Mainline Over Silver Creek, POR-IR76-015.78L | 6702821 EB , MainlineOver Silver Creek, POR-IR76-015.78R | 6702732 Under Rock Springs Rd NOT PAINTED | 6702945 Slab Deck Not Painted | 6703003 Slab Deck Not Painted | 6703038 Culvert Not Painted | 6703151 Slab Deck Not Painted | 6703186 Slab Deck Not Painted | [6 empty] | All bridge painting use same warranty date 10/5/01 Ref nos. 86-89, 112-115, 246-249 | 2006-10-05 | Expired
Painting | 885 | 19963 | 425 | 2000 | 2000-0425 | 4 | MAH-IR680-000.67 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-08-01 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 5006392, Under Four Mile Run Rd, MAH-IR680-000.67 | 5006422, Under Lanterman Rd, MAH-IR680-001.23 | 5006511, Under Vestal Rd, MAH-IR680-002.83 | 5006570, Pedestrian Bridge, MAH-IR680-003.15 | 5006759, Under Belle Vista Ave, MAH-IR680-003.74 | 5006783, Under Wellington St, MAH-IR680-003.85 | 5006813, Under Steel St, MAH-IR680-004.14 | [7 empty] | All bridge painting use same warranty date 8/1/01 Refs 10-13, 21-24, 34-37, 45-48, 56-59, 67-70, 77-80 | 2006-08-01 | Expired
Painting | 885 | 10055 | 524 | 2000 | 2000-0524 | 4 | ATB-SR11-024.62 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-06-21 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 0401536, Under Seven Hills Rd, ATB-SR11-024.62 | 0401625, Under Plymouth Ridge Rd, ATB-SR11-025.14 | [12 empty] | Corretive work to Plymouth Ridge top coat 7-1-02 Refs 60-63, 124-127 | 2007-06-21 | Expired
Painting | 885 | 11608 | 539 | 2000 | 2000-0539 | 4 | SUM-IR77-11.971 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-10-15 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 7702469, Under Killian Rd, SUM-IR77-07.44 | [13 empty] | Under review by CO Refs 117, 120 | 2006-10-15 | Expired
Painting | 885 | 12836 | 8 | 2001 | 2001-0008 | 4 | STA-IR77-05.938 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-04-28 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [9 empty] | SUM-77-41954 R | [11 empty] | Under review by CO Refs 99-102, 133-136 | 2007-04-28 | Expired
Painting | 885 | 18715 | 137 | 2001 | 2001-0137 | 4 | ATB-SR534-019.35 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-10-25 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 0407119, ATB-SR534-019.35 | [13 empty] | Under review by CO Refs 141-144 | 2006-10-25 | Expired
Painting | 885 | 18722 | 3000 | 2001 | 2001-3000 | 4 | MAH-SR11-016.04 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-11-08 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | SFN 5000807 SR11 SB Over IR 80 EB | SFN 5000815 SR11 NB Ramp Over 11SB | SFN 5000823 SR 11 Ramp Under IR680 WB | [11 empty] | All bridge painting use same warranty date 11/8/02 Refs 101-104 | 2007-11-08 | Expired
Painting | 885 | 22163 | 3002 | 2001 | 2001-3002 | 4 | TRU-IR80-009.08 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-07-10 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 7803303 Under Salt Springs Rd (7/29/01) | 7803516 Pedestrian Walk (8/19/01) | 7803575 Under Moser Rd (8/22/01) | 7804237 Ramp Over Yankee Run (9/13/01) | 7804261 WB Over Yankee Run (9/6/01) | 7804296 EB Over Yankee Run (9/5/01) | 7804326 WB Over SR 7, US 62 (8/31/01) | 7804350 EB Over SR 7, US 62 (8/31/01) | 7804415 Under Penn Central RR (10/4/01) | 7804474 WB Over Erie RR (9/23/01) | 7804504 EB Mainline over Erie RR (9/16/01) | 7804539 Under Price Shaffer Rd (10/01/01) |  |  | Varies; See Individual Structure info Refs 13, 17, 21, 26, 32, 38, 44, 50, 52, 57, 63, 66 | 2007-07-10 | Expired
Painting | 885 | 19899 | 3005 | 2001 | 2001-3005 | 4 | ATB-SR11-023.33 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-05-29 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 0401382 SB Mainline Over Carson Rd, ATB-SR11-023.33L | [13 empty] | Under review by CO Ref 14 | 2007-05-29 | Expired
Painting | 885 | 19854 | 3010 | 2001 | 2001-3010 | 4 | POR-US224-000.00 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-07-30 | 5 | 1 month Prior to Warranty Expirartion | Administered by Cols | [7 empty] | 6703755, Over N & S RR, POR-US224-001.04 | 6703909 Over Stroup Rd, POR-US224-011.72 | 6703933 Over Conrail RR US224-011.89 | [11 empty] | All bridge painting use same warranty date 7/30/02 Refs 26, 36 | 2007-07-30 | Expired
Painting | 885 | 20768 | 111 | 2000 | 2000-0111 | 5 | MUS-US22-006.10 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-10-13 | 5 | 2001-04-30 | 2002-04-30 | 2003-04-30 | [6 empty] | MUS-US22-006.10 | [13 empty] | Under review by CO | 2005-10-13 | Expired
Painting | 885 | 16806 | 378 | 2000 | 2000-0378 | 5 | LIC-IR70-25.685 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-07-31 | 5 | [6 empty] | 2006-06-30 |  |  | LIC-IR70-16.09 | LIC-IR70-17.45 | LIC-IR70-21.00 | LIC-IR70-22.10 | LIC-IR70-26.53 | [9 empty] | Under review by CO | 2006-07-31 | Expired
Painting | 885 | 16105 | 533 | 2000 | 2000-0533 | 5 | LIC-SR661-000.24 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-10-31 | 5 | [6 empty] | 2007-09-30 |  |  | LIC-SR661-000.28 | [13 empty] | Under review by CO | 2007-10-31 | Expired
Painting | 885 | 5881 | 4 | 2000 | 2000-0004 | 6 | FRA-IR70-014.69 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-11-26 | 5 |  |  | 2004-09-18 | by c.o. | see comments |  |  |  |  | 2504774 2504804 | 2504839 2504863 | 2504898 2504928 | 2504952 2504987 | 2505010 2505045 | 2505134 2505169 | 25057595 2505193 | 2505223 2505258 | 2505282 2505312 | 2505347 2505436 | 2516500 | 2505614 2505738 |  |  | being handled by chief legal office4/12/06-see e-mail in file | 2006-11-26 | Expired
Painting | 885 | 14005 | 22 | 2001 | 2001-0022 | 6 | FRA-IR70-013.22 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-07-31 | 5 | 2002-09-10 |  |  | by c.o. | see comments |  |  |  |  | 2504413 L | 2504448 R | [12 empty] | being handled by chief legal office4/12/06-see e-mail in file | 2006-07-31 | Expired
Painting | 885 | 19361 | 26 | 2001 | 2001-0026 | 6 | MAR-US23-018.15 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-11-27 | 5 | 2002-03-06 | Review Waived 2003 | 2004-09-07 | by c.o. | see comments |  |  |  |  | 5101204L | 5101239 R | [12 empty] | being handled by chief legal office | 2006-11-27 | Expired
Painting | 885 | 18019 | 88 | 2001 | 2001-0088 | 6 | PIC-SR138-006.32 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | Voided | 5 | by central off. | see comments | [7 empty] | VOIDED | [15 empty] | Expired
Painting | 885 | 19724 | 39 | 2000 | 2000-0039 | 8 | BUT-SR4-000.40 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-12-06 | 5 | 2005-11-06 | [8 empty] | 0900516 BUT-SR122D-000.59L | 0900540 BUT-SR122D-000.64L | 0902365 BUT-SR128-08.58 | 0902349 BUT-SR4B-000.40 | 0903159 BUT-SR4B-001.91 | [9 empty] | Under review by CO | 2005-12-06 | Expired
Painting | 885 | 15348 | 67 | 2000 | 2000-0067 | 8 | HAM-US22-013.30 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-12-13 | 5 | 2005-11-13 | [8 empty] | 3100995, HAM-US22-013.30 | [13 empty] | Under review by CO | 2005-12-13 | Expired
Painting | 885 | 19349 | 165 | 2000 | 2000-0165 | 8 | CLE-SR749-000.00 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - (OZEU) | 2000-11-20 | 5 | 2005-08-15 | [8 empty] | 1301357, CLE-SR52-001.42 | [13 empty] | Under review by CO | 2005-11-20 | Expired
Painting | 885 | 15350 | 184 | 2000 | 2000-0184 | 8 | PRE-US127-003.76 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-10-25 | 5 | 2005-09-25 | [8 empty] | 6802370, PRE-US127-003.76 | [13 empty] | Under review by CO | 2005-10-25 | Expired
Painting | 885 | 21007 | 471 | 2000 | 2000-0471 | 8 | GRE-IR675-010.25 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-05-25 | 5 | 2005-04-25 | [8 empty] | 2903792, GRE-IR675-010.25L | 3903806, GRE-IR675-010.25R | 2904438, GRE-IR675-017.53L | 2904446, GRE-IR675-017.53R | [10 empty] | Under review by CO | 2006-05-25 | Expired
Painting | 885 | 17226 | 114 | 2001 | 2001-0114 | 8 | HAM-IR75-014.26 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-12-12 | 5 | 2006-11-12 | [8 empty] | 3110745, HAM-IR75-012.92 | 3110824, HAM-IR75-013.38 | 3110869, HAM-IR75-013.90 | 3100901, HAM-IR75-014.26 | [10 empty] | Under review by CO | 2006-12-12 | Expired
Painting | 885 | 17357 | 155 | 2001 | 2001-0155 | 8 | BUT-SR4-009.28 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-10-26 | 5 | 2006-09-26 | [8 empty] | 0900184, BUT-SR4-014.80L | 0900184, BUT-SR4-014.80R | [12 empty] | Under review by CO | 2006-10-26 | Expired
Painting | 885 | 20911 | 467 | 2001 | 2001-0467 | 8 | BUT-127-17.21 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - " | 2003-08-01 | 5 | [24 empty] | 2008-08-01 | Expired
Painting | 885 | 19705 | 3009 | 2001 | 2001-3009 | 8 | HAM-IR71-011.08 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-12-17 | 5 | [8 empty] | No C85 issued to date | HAM-IR71-011.08 | [14 empty] | 2007-12-17 | Expired
Painting | 885 | 19795 | 466 | 2000 | 2000-0466 | 9 | Ross-35-25.84 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-07-08 | 5 | 7/13/2004 (by District) | 9/7/2005 (by Central Office) | [5 empty] | Rust showing, lack of surface prep, unpainted areas | Pending | ROS-US35-024.69 | [13 empty] | Top of top flange of all diaphragms not painted. Areas on bottom flange of diaphragms not painted or lacks all coats of paint. Sliding bearings/sole plates not properly prepared prior to painting. Areas noted along edge of bottom flange showing signs of rust, outside edge of upper flange lacking all coats of paint, bolt heads under top flange not painted, slivers showing signs of rust. Warranty demand letter sent out by Division of Construction Management 3-30-05. | 2006-07-08 | Expired
Painting | 885 | 19795 | 466 | 2000 | 2000-0466 | 9 | HIG-US62-025.43 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-07-08 | 5 | 7/23/2004 (by District) | 7/1/2005 (by Central Office) | [5 empty] | Minor peeling, Rust showing, Lack of surface prep, improper painting | Pending | Hig-62-25.09 | [13 empty] | Cracking and of paint system along top outside bottom flange, Bearings showing signs of rust, 8" square stiffener plate showing signs of rust, back of angles/attachment angles/rivets not properly painted, bottom flange of rear girder not properly painted, areas not having proper surface prep. Warranty demand letter sent out by Division of Construction Management 3-30-05. | 2006-07-08 | Expired
Painting | 885 | 19307 | 3000 | 2000 | 2000-3000 | 9 | ROS-SR159-0.00 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2000-10-17 | 5 | 7/13/2004 (by District) | 9/6/2005 (by Central Office) | [5 empty] | Rust showing, uncoated sections |  | Ross-159-3.24-L | [13 empty] | Most bottom flanges of floor beams showing signs of rust spots coming through. Inside and outside between horizontal stiffeners and bottom angles lack caulking. Edges of floor beams has signs of rust at various locations. Areas noted on bottom of diaphragms behind, left rear rocker on horizontal stiffener plates showing rust/lacking finish coat. Warranty demand letter sent out by Division of Construction Management 9-30-05. | 2005-10-17 | Expired
Painting | 885 | 13226 | 118 | 2001 | 2001-0118 | 9 | SCI-US52-32.686 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-01-08 | 5 | 7/20/2004 (by District) | 4/28/2005 (by Central Office) | [5 empty] | Rust showing, inadaquate surface prep |  | SCI-52-20.32 | [13 empty] | Cross frames light in paint. Not cleaned or painted between bottom of angle and top of bottom flange and between top of angles and bottom of deck. Edges of flanges and bottom moment plates showing signs of rust stains. Bottom of moment plate at pier bearings showing signs of rust. Areas noted where slivers not ground showing signs of rust and painting over grit. Warranty demand letter sent out by Division of Construction Management 3-30-05. | 2007-01-08 | Expired
Painting | 885 | 15936 | 511 | 2000 | 2000-0511 | 11 | HAS-US22-017.48 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-12-19 | 5 | 2002-12-18 | [6 empty] | none |  | HAS-US22-017.49L | HAS-US22-017.49R | HAS-US22-017.53L | HAS-US22-017.53R | [10 empty] | Under review by CO | 2006-12-19 | Expired
Painting | 885 | 21709 | 371 | 2008 | 2008-0371 | 11 | HAS-US22-017.17 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 21709 | 371 | 2008 | 2008-0371 | 11 | HAS-US22-017.17 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 21709 | 371 | 2008 | 2008-0371 | 11 | HAS-US22-017.17 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 21709 | 371 | 2008 | 2008-0371 | 11 | HAS-US22-017.17 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Painting | 885 | 21709 | 371 | 2008 | 2008-0371 | 11 | HAS-US22-017.17 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 21709 | 371 | 2008 | 2008-0371 | 11 | HAS-US22-017.17 | FINAL INSPECTION REPAIR | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 22784 | 428 | 2008 | 2008-0428 | 11 | TUS-US36-018.00 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 22784 | 428 | 2008 | 2008-0428 | 11 | TUS-US36-018.00 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 22784 | 428 | 2008 | 2008-0428 | 11 | TUS-US36-018.00 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 22784 | 428 | 2008 | 2008-0428 | 11 | TUS-US36-018.00 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Painting | 885 | 22784 | 428 | 2008 | 2008-0428 | 11 | TUS-US36-018.00 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 22784 | 428 | 2008 | 2008-0428 | 11 | TUS-US36-018.00 | FINAL INSPECTION REPAIR | Non performed | 5 | [25 empty] | Expired
Painting | 885 | 19494 | 306 | 2000 | 2000-0306 | 12 | CUY-US6-000.42 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-11-06 | 5 | 2004-09-03 | [6 empty] | Adhesion failure | Complete repaint | CUY-US6A-000.42 | [13 empty] | Under review by CO | 2006-11-06 | Expired
Painting | 885 | 18746 | 444 | 2000 | 2000-0444 | 12 | LAK-IR90-000.80 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-10-21 | 5 | [9 empty] | LAK-IR90-000.80 | LAK-IR90-003.80 | LAK-IR90-007.11 | LAK-IR90-007.67 | LAK-IR90-008.77 | LAK-IR90-010.07 | LAK-IR90-010.31 | LAK-IR90-010.51 | LAK-IR90-011.51 | LAK-IR90-012.97 | LAK-IR90-022.10 |  |  |  | Under review by CO | 2006-10-21 | Expired
Painting | 885 | 19502 | 526 | 2000 | 2000-0526 | 12 | CUY-SR237-004.84 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-07-22 | 5 | [9 empty] | CUY-SR237-004.84 | [13 empty] | Under review by CO | 2007-07-22 | Expired
Painting | 885 | 18739 | 559 | 2000 | 2000-0559 | 12 | CUY-IR90-008.92 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2001-08-09 | 5 | [9 empty] | CUY-IR90-008.92 | CUY-IR90-009.09 | CUY-IR90-010.62 | CUY-IR90-010.82 | CUY-IR90-010.94 | CUY-IR90-011.10 | CUY-IR90-011.78 | CUY-IR90-011.85 | CUY-IR90-012.01 | CUY-IR90-012.14S | CUY-IR90-012.37 | CUY-IR90-012.70 | CUY-IR90-013.45 | CUY-IR90-013.61 | Under review by CO | 2006-08-09 | Expired
Painting | 885 | 12339 | 107 | 2001 | 2001-0107 | 12 | CUY-IR90-006.21 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY - | 2002-05-15 | 5 | [9 empty] | CUY-IR90-006.21 | CUY-IR90-006.48 | CUY-IR90-008.49 | [11 empty] | Under review by CO | 2007-05-15 | Expired
Traffic | 887 | 20980 | 75 | 2000 | 2000-0075 | 2 | OTT-SR2-23.240 | EDGE LINE, LANE LINE, CENTER LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 19309 | 79 | 2000 | 2000-0079 | 2 | WIL-SR49-002.05 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 19339 | 112 | 2000 | 2000-0112 | 2 | OTT-SR53-011.83 | EDGE LINE, LANE LINE, CENTER LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 19308 | 118 | 2000 | 2000-0118 | 2 | WIL-US6-000.00 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 18410 | 300 | 2000 | 2000-0300 | 2 | SEN-SR67-002.33 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 19342 | 341 | 2000 | 2000-0341 | 2 | FUL-US20-010.86 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 11376 | 23 | 2000 | 2000-0023 | 3 | ERI-SR2-12.558 | EDGE LINE, CENTER LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Voided | 5 | 2002-04-01 | 2003-04-01 | [23 empty] | Expired
Traffic | 887 | 11365 | 151 | 2000 | 2000-0151 | 3 | RIC-IR71-20.220 | EDGE LINE, CENTER LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 16924 | 154 | 2000 | 2000-0154 | 3 | ASD-US250-016.48 | EDGE LINE, LANE LINE CENTERLINE, CHANNELIZING LINE (3 YEAR WARRANTY) - | Voided | 3 | [25 empty] | Expired
Traffic | 887 | 7885 | 239 | 2000 | 2000-0239 | 3 | MED-IR71-015.78 | EDGE LINE, CENTER LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 16738 | 273 | 2000 | 2000-0273 | 3 | LOR-SR83-06.727 | EDGE LINE, CENTER LINE CHANNELIZING LINE (3 YEAR WARRANTY) - | Voided | 3 | [25 empty] | Expired
Traffic | 887 | 18286 | 302 | 2000 | 2000-0302 | 3 | ASD-US30-09.484 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Voided | 5 | [25 empty] | Expired
Traffic | 887 | 16894 | 328 | 2000 | 2000-0328 | 3 | WAY-SR94-000.00 | EDGE LINE, CENTER LINE (3 YEAR WARRANTY) - | Voided | 3 | [25 empty] | Expired
Traffic | 887 | 18200 | 3002 | 2000 | 2000-3002 | 3 | MED-IR271-000.00 | SPECIAL - MISC.: - EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) | Voided | 5 | [25 empty] | Expired
Pavement Markings | 887 | 18546 | 357 | 2000 | 2000-0357 | 4 | POR-SR05-0.19 | PAVEMENT MARKINGS< WITH WARRANTY | Voided | 3 | Warranty Waived | [22 empty] | Refs 50, 51, 52, 53 Warranty Waived |  | Expired
Other | 887 | 7278 | 722 | 1999 | 1999-0722 | 6 | FRA-IR71-025.60 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | [23 empty] | NON PERFORMED |  | Expired
Other | 887 | 5881 | 4 | 2000 | 2000-0004 | 6 | FRA-IR70-014.69 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | [23 empty] | NON PERFORMED BY CHANGE ORDER |  | Expired
Other | 887 | 20943 | 17 | 2000 | 2000-0017 | 6 | FRA-IR670-005.61 | EDGE LINE, LANE LINE, CENTER LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | [23 empty] | NON PERFORMED BY CHANGE ORDER |  | Expired
Other | 887 | 20660 | 59 | 2000 | 2000-0059 | 6 | FRA-IR71-000.00 | EDGE LINE, LANE LINE, CHANNELIZING LINE (3 YEAR WARRANTY) - | Non performed | 3 | [23 empty] | NON PERFORMED BY CHANGE ORDER |  | Expired
Other | 887 | 19980 | 61 | 2000 | 2000-0061 | 6 | FRA-IR270-037.00 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | [23 empty] | NON PERFORMED BY CHANGE ORDER |  | Expired
Other | 887 | 4388 | 91 | 2000 | 2000-0091 | 6 | GRE-US35-026.20 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | [23 empty] | NON PERFORMED BY CHANGE ORDER |  | Expired
Other | 887 | 19175 | 194 | 2000 | 2000-0194 | 6 | MAR-SR95-016.77 | EDGE LINE, CENTER LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | [23 empty] | OUT OF WARRANTY |  | Expired
Other | 887 | 12387 | 217 | 2000 | 2000-0217 | 6 | FRA-US33-026.12 | EDGE LINE, CENTER LINE, LANE LINE, CHANNELIZING LINE (3 YEAR WARRANTY) - | Non performed | 3 | [23 empty] | non performed |  | Expired
Other | 887 | 17003 | 279 | 2000 | 2000-0279 | 6 | UNI-US33-008.74 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | [23 empty] | NON PERFORMED BY CHANGE ORDER |  | Expired
Other | 887 | 19402 | 353 | 2000 | 2000-0353 | 6 | MAR-US23-010.63 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | Non | [22 empty] | none performed |  | Expired
Traffic | 887 | 19349 | 165 | 2000 | 2000-0165 | 8 | CLE-SR749-000.00 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Voided | 5 | 2001-10-18 | 2002-08-21 | [23 empty] | Expired
Traffic | 887 | 19344 | 175 | 2000 | 2000-0175 | 8 | BUT-SR73-016.64 | EDGE LINE, LANE LINE, CENTER LINE, CHANNELIZING LINE (3 YEAR WARRANTY) - | Voided | 3 | 2001-10-18 | 2002-08-21 | [23 empty] | Expired
Traffic | 887 | 19393 | 223 | 2000 | 2000-0223 | 8 | PRE-SR503-001.00 | EDGE LINE, CENTER LINE (3 YEAR WARRANTY) - | Voided | 3 | 2001-10-18 | 2002-08-21 | [23 empty] | Expired
Traffic | 887 | 19687 | 236 | 2000 | 2000-0236 | 8 | HAM-IR275-010.57 | EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Voided | 5 | 2001-10-18 | 2002-08-21 | [23 empty] | Expired
Traffic | 887 | 19392 | 242 | 2000 | 2000-0242 | 8 | PRE-US40-000.00 | EDGE LINE, LANE LINE, CENTER LINE, CHANNELIZING LINE (3 YEAR WARRANTY) - | Voided | 3 | 2001-10-18 | 2002-08-21 | [23 empty] | Expired
Traffic | 887 | 19660 | 251 | 2000 | 2000-0251 | 8 | CLI-SR350-000.00 | EDGE LINE, CENTER LINE (3 YEAR WARRANTY) - | Voided | 3 | 2001-10-18 | 2002-08-21 | [23 empty] | Expired
Traffic | 887 | 18899 | 3003 | 2000 | 2000-3003 | 8 | PRE-IR70-000.00 | SPECIAL - MISC.: - PERM. PAVEMENT MARKINGS/5 YEAR WARRANTY | 2002-09-24 | 5 | 2005-04-27 | [23 empty] | 2007-09-24 | Expired
Traffic | 887 | 19156 | 28 | 2000 | 2000-0028 | 9 | ADA-SR41-000.00 | EDGE LINE, CENTER LINE (3 YEAR WARRANTY) - 20% REDUCTION | Non performed | 3 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 19156 | 28 | 2000 | 2000-0028 | 9 | ADA-SR41-000.00 | EDGE LINE, LANE LINE, CENTER LANE (3 YEAR WARRANTY) - | Non performed | 3 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 17045 | 114 | 2000 | 2000-0114 | 9 | ROS-US23-000.00 | EDGE LINE, CENTER LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Non performed | 5 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 19218 | 411 | 2000 | 2000-0411 | 9 | BRO-SR774-000.00 | EDGE LINE, CENTER LINE (3 YEAR WARRANTY) - | Non performed | 3 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 19307 | 3000 | 2000 | 2000-3000 | 9 | ROS-SR159-0.00 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Non performed | 5 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 13348 | 109 | 2000 | 2000-0109 | 10 | MOE-SR800-35.170 | EDGE LINE, CENTER LINE LANE LINE (5 YEAR WARRANTY) - | Assumed Expired | 5 | [25 empty] | Expired
Traffic | 887 | 14524 | 150 | 2000 | 2000-0150 | 10 | NOB-SR78-09.185 | EDGE LINE, CENTER LINE (3 YEAR WARRANTY) - | Voided | 3 | [25 empty] | Expired
Traffic | 887 | 19933 | 188 | 2000 | 2000-0188 | 10 | ATH-SR78-001.58 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Non performed | 5 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 19960 | 193 | 2000 | 2000-0193 | 10 | HOC-SR93-013.68 | EDGE LINE, CENTER LINE (5 YEAR WARRANTY) - | Non performed | 5 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 17440 | 248 | 2000 | 2000-0248 | 10 | WAS-IR77-006.59 | EDGE LINE, LANE LINE (5 YEAR WARRANTY) - | Non performed | 5 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 19905 | 3001 | 2000 | 2000-3001 | 10 | NOB-IR77-006.22 | SPECIAL - MISC.: - EDGE LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) | Non performed | 5 | Non Performed by Change Order | [24 empty] | Expired
Traffic | 887 | 18730 | 263 | 2000 | 2000-0263 | 12 | CUY-IR90-023.93 | EDGE LINE, CENTER LINE, LANE LINE, CHANNELIZING LINE (5 YEAR WARRANTY) - | Voided | 5 | 2002-10-03 | 2003-10-22 | [23 empty] | Expired
Concrete | 888 | 22698 | 349 | 2002 | 2002-0349 | 10 | ATH-US33-001.87 | PORTLAND CEMENT CONCRETE PAVEMENT, 8" THICK (NON-REINFORCED PER 452) | Assumed Expired | 7 | [25 empty] | Expired
Other | 889 | 12387 | 217 | 2000 | 2000-0217 | 6 | FRA-US33-026.12 | SAWING AND SEALING ASPHALT CONCRETE PAVEMENT JOINTS WITH WARRANTY - | 2000-08-21 | 2 | 2001-05-31 | 2002-06-03 |  |  |  | 2002-08-21 | [17 empty] | out of warranty | 2002-08-21 | Expired
Concrete | 889 | 20800 | 108 | 2001 | 2001-0108 | 12 | CUY-IR90-013.41 | SAWING AND SEALING ASPHALT CONCRETE PAVEMENT JOINTS WITH WARRANTY - | 2002-07-18 | 2 | 2003-06-15 | [23 empty] | 2004-07-18 | Expired
Concrete | 889 | 18391 | 7 | 2002 | 2002-0007 | 12 | LAK-SR2-013.05 | SAWING AND SEALING ASPHALT CONCRETE PAVEMENT JOINTS WITH WARRANTY - | 2004-01-12 | 2 | [24 empty] | 2006-01-12 | Expired
Bridge | 892 | 17124 | 3000 | 1999 | 1999-3000 | 1 | ALL-IR75-29.564 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (MIN. 25MM THICK) | 2000-07-07 | 3 | 2001-05-09 | [23 empty] | 2003-07-07 | Expired
Bridge | 892 | 19339 | 112 | 2000 | 2000-0112 | 2 | OTT-SR269-1.67 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (1 1/4" THICK) | 2001-05-02 | 3 | 1 month Prior to Warranty Expirartion (Apr 2004) | [5 empty] | 2004-04-06 | [17 empty] | 2004-05-02 | Expired
Bridge | 892 | 19753 | 316 | 2001 | 2001-0316 | 2 | HEN-SR6-10.64 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY | 2002-07-24 | 2 | [24 empty] | 2004-07-24 | Expired
Bridge | 892 | 23995 | 1040 | 2010 | 2010-1040 | 2 | LUC-C.R.505-0.28 (WHEELING STREET) | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2012-07-13 | 2 | [6 empty] | 2012-08-02 | [17 empty] | 2014-07-13 | Expired
Bridge | 892 | 16054 | 277 | 2007 | 2007-0277 | 3 | LOR-SR301-40.673 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 892 | 24868 | 421 | 2008 | 2008-0421 | 3 | LOR-IR90-012.42 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2009-11-03 | 2 | [24 empty] | 2011-11-03 | Expired
Overlay | 892 | 22163 | 3002 | 2001 | 2001-3002 | 4 | TRU-IR80-009.08 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (2-1/2" THICK) | 2002-07-10 | 7 | 2006-08-03 | 2007-05-03 | [7 empty] | 7803303 Under Salt Springs Rd (7/29/01) | 7803516 Pedestrian Walk (8/19/01) | 7803575 Under Moser Rd (8/22/01) | 7804237 Ramp Over Yankee Run (9/13/01) | 7804261 WB Over Yankee Run (9/6/01) | 7804296 EB Over Yankee Run (9/5/01) | 7804326 WB Over SR 7, US 62 (8/31/01) | 7804350 EB Over SR 7, US 62 (8/31/01) | 7804415 Under Penn Central RR (10/4/01) | 7804474 WB Over Erie RR (9/23/01) | 7804504 EB Mainline over Erie RR (9/16/01) | 7804539 Under Price Shaffer Rd (10/01/01) |  |  | Refs 27, 33, 39, 45, 51, 58, 64, 100-106 | 2009-07-10 | Expired
Overlay | 892 | 19854 | 3010 | 2001 | 2001-3010 | 4 | POR-US224-000.00 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (2-1/2" THICK) | 2002-07-30 | 7 | 2006-07-28 | 2007-04-27 | [7 empty] | 6703755, Over N & S RR, POR-US224-001.04 | 6703909 Over Stroup Rd, POR-US224-011.72 | 6703933 Over Conrail RR US224-011.89 | [11 empty] | Refs 26, 100, 112, 113 | 2009-07-30 | Expired
Overlay | 892 | 22478 | 390 | 2005 | 2005-0390 | 4 | POR SR 14 13.39 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (2-1/2" THICK) | 2007-08-13 | 7 | [9 empty] | SFN 6700721 POR SR 14 1340 | [13 empty] | Ref 120 | 2014-08-13 | Expired
Overlay | 892 | 6080 | 2 | 2006 | 2006-0002 | 4 | MAH IR 80 0097 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (2-1/2" THICK) | 2009-09-15 | 2 | [23 empty] | Completion Date 8/31/2009 Refs 266, 292, 334, 376, 403, 428, 458, 483 | 2011-09-15 | Expired
Bridge | 892 | 24508 | 467 | 2006 | 2006-0467 | 4 | SUM SR 8 15.63 | QA/QC HIGH PERFORMANCE DECK CONCRETE | 2009-11-06 | 2 | [9 empty] | SFN 7700717 SUM-8 16.36 | SFN 7700768 SUM-8 17.09A | SFN 7700776 SUM-8 17.58A | SFN 7700792 SUM-8 17.57B | SFN 7700784 SUM-8 17.24B | SFN 7709331 SUM-271 11.86Lt | SFN 7709366 SUM-271 11.86Rt | SFN 7709218 SUM-271 11.16Lt | SFN 7709277 SUM-271 11.22Lt | [5 empty] | Completion Date 7/31/2010 Refs 498, 527, 555, 612, 649, 685, 718, 778, 803 | 2011-11-06 | Expired
Bridge | 892 | 19069 | 555 | 2004 | 2004-0555 | 7 | MOT-IR70-22.890 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 892 | 22935 | 465 | 2005 | 2005-0465 | 7 | MOT-IR70-017.04 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2008-09-23 | 2 | [9 empty] | MOT-70-1734L&R (Started 9/23/08 - 2yr) | MOT-70-2097L&R (Started 9/23/08 - 2yr) | MOT-70-0016L&R (Started 9/23/08 - 2yr) | [12 empty] | 2010-09-23 | Expired
Bridge | 892 | 24346 | 558 | 2005 | 2005-0558 | 7 | MIA-IR75-017.49 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 892 | 16446 | 113 | 2001 | 2001-0113 | 8 | HAM-US52-030.59 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (2-1/2" THICK) | 2001-07-27 | 3 | 2003-07-27 | [22 empty] | Warranty finished | 2004-07-27 | Expired
Bridge | 892 | 15278 | 500 | 2005 | 2005-0500 | 8 | GRE-SR 725-00.395 | QC/QA CONCRETE FOR NEW BRIDGE DECKS WITH WARRANTY | 2006-11-17 | 2 | [9 empty] | SFN 2902826 | [14 empty] | 2008-11-17 | Expired
Bridge | 892 | 23976 | 524 | 2005 | 2005-0524 | 8 | GRE-IR 71-02.49 | QC/QA CONCRETE FOR NEW BRIDGE DECKS WITH WARRANTY | 2006-10-31 | 2 | 2008-04-21 | [6 empty] | Cracking, spalling, deck scaling | Remedial actions | SFN 2901749 | SFN 2901773 | [12 empty] | Distresses encountered, contractor notified to submit plan for remedial action. | 2008-10-31 | Expired
Bridge | 892 | 75882 | 4 | 2006 | 2006-0004 | 8 | HAM-US22-015.84 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 892 | 24664 | 480 | 2007 | 2007-0480 | 8 | BUT-IR75-003.76 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2010-11-09 | 2 | [24 empty] | 2012-11-09 | Expired
Bridge | 892 | 78570 | 507 | 2008 | 2008-0507 | 8 | CLI-SR73-008.34 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2011-11-02 | 2 | [24 empty] | 2013-11-02 | Expired
Bridge | 892 | 20422 | 541 | 2006 | 2006-0541 | 9 | SCI-140-12.80 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USINGHYDRO-DEMOLITION WITH WARRANTY - (2-1/2" THICK) | 2007-05-12 | 2 | 2008-07-24 | [5 empty] | 2009-05-12 | Cracking |  | SFN 7304544 Sci-140-12-80SR | [13 empty] | 2 longitudinal cracks, grown since initial warranty inspection. Two areas of map-cracking on surface. Amount of cracking under 20% of the deck area. | 2009-05-12 | Expired
Bridge | 892 | 12928 | 31 | 2008 | 2008-0031 | 9 | SCI-SR522-000.98 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 892 | 75457 | 323 | 2008 | 2008-0323 | 9 | BRO-US68-025.54 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 892 | 84212 | 6001 | 2008 | 2008-6001 | 9 | ROS-US23-015.30 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 893 | 15992 | 119 | 2000 | 2000-0119 | 1 | WYA-SR37-14.806 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2000-07-14 | 7 | 2001-05-08 | 2001-05-08 | 2006-04-05 |  |  |  | 2007-05-08 | [16 empty] | Warranty released. | 2007-07-14 | Expired
Bridge | 893 | 17071 | 138 | 2000 | 2000-0138 | 1 | ALL-SR81-00.821 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2000-11-02 | 7 | 2001-05-08 | 2002-05-10 | 2004-04-18 | 2006-04-03 |  |  | 2007-05-10 | [16 empty] | Warranty released. | 2007-11-02 | Expired
Bridge | 893 | 12961 | 570 | 2000 | 2000-0570 | 1 | WYA-SR231-06.160 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-09-18 | 7 | 2002-05-13 | 2003-04-28 | 2004-04-18 | 2006-04-05 | [20 empty] | 2008-09-18 | Expired
Bridge | 893 | 19303 | 424 | 2001 | 2001-0424 | 1 | ALL-SR65-011.37 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-07-24 | 7 | 2004-04-18 | 2006-04-10 | [22 empty] | 2009-07-24 | Expired
Bridge | 893 | 8831 | 116 | 2000 | 2000-0116 | 4 | STA-SR44-21.050 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-08-08 | 7 | 2003-03-18 | 2005-04-12 | 2006-07-24 |  |  |  |  | Appears to be paved over |  | SFN 7601786 SLM 13.08 | [13 empty] | Paved Over in 2007 Ref 124 | 2008-08-08 | Expired
Bridge | 893 | 10055 | 524 | 2000 | 2000-0524 | 4 | ATB-SR11-024.62 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-08-31 | 7 | 2006-08-01 | 2007-05-03 | [7 empty] | SFN 0401536 SLM 24.62 | [13 empty] | Refs 64, 128 | 2009-08-31 | Expired
Bridge | 893 | 11608 | 539 | 2000 | 2000-0539 | 4 | SUM-IR77-11.971 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-10-15 | 7 | 2006-07-26 | 2007-04-30 | [7 empty] | 7702469, Under Killian Rd, SUM-IR77-07.44 | [13 empty] | Ref 121 | 2008-10-15 | Expired
Bridge | 893 | 16572 | 566 | 2000 | 2000-0566 | 4 | SUM-IR77-41.954 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-11-08 | 7 | 2006-07-25 | 2007-04-30 | [7 empty] | SFN 7704267 Bath Rd. SUM-77-26.07 L | SFN 7704291 Bath Rd. SUM-77-26.07R | [12 empty] | Refs 105, 140 | 2008-11-08 | Expired
Bridge | 893 | 8950 | 165 | 2001 | 2001-0165 | 4 | SUM IR-77 29.515 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-09-16 | 7 | 2006-07-26 | 2007-04-30 | [7 empty] | SFN 7703880 White Pond SLM 18.34 | [13 empty] | Ref 254 | 2009-09-16 | Expired
Bridge | 893 | 11933 | 540 | 2001 | 2001-0540 | 4 | MAH-US224-000.08 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-04-29 | 7 | 2004-05-15 | 2005-09-29 | 2006-08-02 | 2007-04-24 | [5 empty] | SFN 5004535 Berlin Lake SLM 0.10 | [13 empty] | Varies; See Individual Structure info Ref 62 | 2010-04-29 | Expired
Bridge | 893 | 18712 | 543 | 2001 | 2001-0543 | 4 | TRU-SR-5-06.45 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-07-14 | 7 | 2006-08-07 | 2007-04-24 | [7 empty] | SFN 7800908 TRU SR 5 12.26 R 5/14/03 | SFN 7800878 TRU SR 5 12.26 L 7/14/03 | [12 empty] | Refs 134, 152, 166, 201, 221, 244, 269, 307, 315 | 2010-07-14 | Expired
Bridge | 893 | 19920 | 395 | 2002 | 2002-0395 | 4 | TRU SR-45 20.18 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-09-26 | 7 | 2006-08-07 | 2007-05-03 | [7 empty] | SFN 7802285 TRU SR 45 20.18 | [13 empty] | Ref 72 | 2010-09-26 | Expired
Bridge | 893 | 22340 | 2 | 2004 | 2004-0002 | 4 | ATB US-20 2.01 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-07-08 | 7 | 2006-08-01 | 2007-05-03 |  |  |  |  | 2012-05-16 | none |  | SFN 0402087 ATB-20-3.26 | [13 empty] | Ref 135 - Released 6/29/12 Correspondence | 2012-07-08 | Expired
Bridge | 893 | 24507 | 581 | 2008 | 2008-0581 | 4 | SUM-SR8-13.31 | SUPERSTRUCTURE DECK CLOSURE POUR REPAIR | 2010-10-29 | 2 | [6 empty] | 2012-11-06 | [16 empty] | No Distresses were observed on Final Inspection | 2012-10-29 | Expired
Bridge | 893 | 16299 | 136 | 2000 | 2000-0136 | 5 | MUS-SR16-007.16 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-08-28 | 7 | 2006-01-17 | [8 empty] | MUS-16-0770L | MUS-16-0770R | MUS-16-0989L | MUS-16-0989R | MUS-16-1020L | MUS-16-1020R | [8 empty] | No distress to date | 2009-08-28 | Expired
Bridge | 893 | 16293 | 136 | 2001 | 2001-0136 | 5 | FAI-US33-007.31 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-11-14 | 7 | 2006-01-13 | [8 empty] | FAI-33-0808L | FAI-33-0808R | FAI-33-0826L | FAI-33-0826R | FAI-33-0994L | FAI-33-0994R | FAI-33-1076L | FAI-33-1076R | FAI-33-1105L | FAI-33-1105R |  |  |  |  | No distress to date | 2010-11-14 | Expired
Bridge | 893 | 16511 | 140 | 2001 | 2001-0140 | 6 | DEL-US23-010.15 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-12-18 | 7 | Review waived 2002 | 2003-03-05 | Review waived 2004 | 2005-08-04 | Review waived 2006 |  |  | taken out of warranty due to work on abutment and wingwalls this is on US 42 over Sandusky |  | 2101823 structure on US 42 | [13 empty] | taken out of warranty due to problems with forward wingwalls, abut, etc repaired twice | 2008-12-18 | Expired
Bridge | 893 | 6225 | 134 | 2003 | 2003-0134 | 6 | FAY-IR71-000.00 (NB) | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-07-21 | 7 | 2005-08-06 | 2006-04-08 | 2007-03-01 | 2008-04-30 | 2010-03-01 |  |  |  |  | 2402580 L/R | [13 empty] | CONTRACTOR SEALING CRACKIN ON BRIDGE DECKS USING HMWM ON 10/24 THRU 10/26/05' AND 11/14/05. 04/08/2006- inspection okay, 04/08/06 NO DISTRESS TYPES FOUND 8/11/05 LETTER TO CONTRACTOR ON DEFICIENCES (CRACKING ) CONTRACTOR SEALED WITH HMWM. CONTRACTOR IN CLAIM PROCESS WITH CHIEF LEGAL (DESIGN , AGGREGATE) CHIEF LEGAL HANDLING. 3/1 07-- overall good condition. 2008 review okay 03/2010 prelim review by county showed no warranty issues. | 2011-07-21 | Expired
Bridge | 893 | 6225 | 134 | 2003 | 2003-0134 | 6 | FAY-IR71-000.00 (SB) | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2005-06-23 | 7 | 2006-04-08 | 2007-03-01 | 2008-04-30 |  | 2010-03-01 | [18 empty] | 04/08/06 no distress types found 2008 review no distress types found 03/2010 prelim review by county showed no warranty issues | 2012-06-23 | Expired
Bridge | 893 | 17413 | 502 | 2000 | 2000-0502 | 7 | LOG-SR273-007.36 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - , FOR BRIDGE DECK WITH WARRANTY | 2001-06-14 | 7 | 2002-06-17 | 2003-09-17 | 2005-02-10 | 2006-03-02 | [20 empty] | 2008-06-14 | Expired
Bridge | 893 | 17066 | 60 | 2001 | 2001-0060 | 7 | MIA-SR41-006.26 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-10-02 | 7 | 2002-09-27 | 2003-09-17 | 2004-03-05 | 2005-04-26 | [20 empty] | 2008-10-02 | Expired
Bridge | 893 | 13507 | 110 | 2001 | 2001-0110 | 7 | DAR-US127-019.77 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-11-21 | 7 | 2002-09-27 | 2003-09-18 | 2004-01-23 | 2005-05-17 | [20 empty] | 2008-11-21 | Expired
Bridge | 893 | 17106 | 430 | 2001 | 2001-0430 | 8 | WAR-73-8.79 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - " | 2002-08-07 | 7 | Warranty Waived | [23 empty] | 2009-08-07 | Expired
Bridge | 893 | 20911 | 467 | 2001 | 2001-0467 | 8 | BUT-127-17.21 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-08-01 | 7 | [24 empty] | 2010-08-01 | Expired
Bridge | 893 | 23839 | 32 | 2002 | 2002-0032 | 8 | HAM-IR275-028.28 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-12-15 | 7 | [8 empty] | No C85 issued to date | [15 empty] | 2010-12-15 | Expired
Bridge | 893 | 23839 | 32 | 2002 | 2002-0032 | 8 | HAM-IR275-028.28 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - " | 2005-12-01 | 7 |  | 2007-04-03 | [6 empty] | Partial Final C-85 | SFN 3138062 | SFN 3113027 | SFN 3112993 | SFN 3112969 | SFN 3113051 | SFN 3113116 | SFN 3113086 | SFN 3113140 | SFN 3113175 | SFN 3113205 | SFN 3113264 | SFN 3113299 | SFN 3113329 | SFN 3113353 |  | 2012-12-01 | Expired
Bridge | 893 | 10914 | 172 | 2002 | 2002-0172 | 8 | CLE-IR275-009.79 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-11-01 | 7 |  |  | 2007-04-03 | [5 empty] | No C85 issued to date | SFN 1305719 | SFN 1305735 | SFN 1305743 | SFN 1305758 | SFN 1305794 | SFN 1305816 | SFN 1305824 | SFN 1305859 | SFN 1305867 | [6 empty] | 2010-11-01 | Expired
Bridge | 893 | 21012 | 91 | 2003 | 2003-0091 | 8 | BUT-SR73-004.44 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-09-26 | 7 | 2004-05-20 | 2005-08-01 | 2006-07-14 | [6 empty] | SFN 0901113 | SFN 0901083 | [13 empty] | 2010-09-26 | Expired
Bridge | 893 | 20337 | 119 | 2003 | 2003-0119 | 8 | PRE-US127-010.51 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-09-26 | 7 | 2005-04-18 | [8 empty] | SFN 6802559 | [14 empty] | 2010-09-26 | Expired
Bridge | 893 | 20400 | 142 | 2003 | 2003-0142 | 8 | HAM-SR128-010.06 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-10-06 | 7 | [9 empty] | SFN 3104532 | [14 empty] | 2010-10-06 | Expired
Bridge | 893 | 17621 | 260 | 2003 | 2003-0260 | 8 | HAM-US22-11.40 | CLASS S CONCRETE, FOR NEW BRIDGE DECKS WITH WARRANTY | 2005-11-03 | 7 | **10/25/2006 | [8 empty] | SFN 3100901 | [14 empty] | 2012-11-03 | Expired
Bridge | 893 | 5872 | 509 | 2003 | 2003-0509 | 8 | BUT-SR129-14.25 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2006-11-04 | 7 | [8 empty] | No Project Awarded to date | SFN 0903361 | [14 empty] | 2013-11-04 | Expired
Bridge | 893 | 13080 | 519 | 2003 | 2003-0519 | 8 | WAR-SR123-29.23 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-09-27 | 7 | [8 empty] | No Project Awarded to date | [15 empty] | 2011-09-27 | Expired
Bridge | 893 | 5889 | 570 | 2003 | 2003-0570 | 8 | WAR-48-21.05 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-11-04 | 7 | [8 empty] | No C85 issued to date | [15 empty] | 2011-11-04 | Expired
Bridge | 893 | 19723 | 164 | 2004 | 2004-0164 | 8 | BUT-SR4-22.61 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-12-16 | 7 |  | 2006-06-14 | [7 empty] | SFN 0900362 | SFN 0900397 | [13 empty] | 2011-12-16 | Expired
Bridge | 893 | 11938 | 393 | 2004 | 2004-0393 | 8 | WAR-63-5.651 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | Assumed Expired | 7 | [25 empty] | Expired
Bridge | 893 | 75122 | 559 | 2004 | 2004-0559 | 8 | HAM-SR 561- 7.00 | CLASS S CONCRETE, FOR NEW BRIDGE DECKS WITH WARRANTY | 2005-11-07 | 7 | [9 empty] | SFN 3113728 | [14 empty] | 2012-11-07 | Expired
Bridge | 893 | 25523 | 7 | 2005 | 2005-0007 | 8 | CLE-275-13.79 | CLASS S CONCRETE, FOR NEW BRIDGE DECKS WITH WARRANTY | 2005-10-10 | 2 | Review Waived | [7 empty] | HAM-275-35.71 | SFN 3116786 | [14 empty] | 2007-10-10 | Expired
Bridge | 893 | 25523 | 7 | 2005 | 2005-0007 | 8 | CLE-275-13.79 | CLASS S CONCRETE, FOR NEW BRIDGE DECKS WITH WARRANTY | 2006-10-31 | 2 | 2007-09-25 | [6 empty] | Alligator and Map Cracking | Remedial actions required. | SFN 3116743 | SFN 3116735 | SFN 3116875 | SFN 3116883 | [11 empty] | 2008-10-31 | Expired
Bridge | 894 | 16440 | 106 | 2000 | 2000-0106 | 1 | HAN-SR613-20.331 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2000-11-29 | 7 | 2001-05-09 | 2002-05-14 | 2004-04-18 | 2006-03-31 |  |  | 2007-05-09 | [16 empty] | Warranty released. | 2007-11-29 | Expired
Bridge | 894 | 20917 | 3007 | 2000 | 2000-3007 | 1 | PAU-SR613-022.02 | SPECIAL - STRUCTURE,MISC.: - CLASS S CONCRETE FOR BRIDGE DECK WITH | 2001-05-10 | 7 | 2001-05-08 | 2002-05-10 | 2004-04-18 | 2006-04-03 |  |  | 2007-05-10 | [16 empty] | Warranty released. | 2008-05-10 | Expired
Bridge | 894 | 21082 | 3010 | 2000 | 2000-3010 | 1 | ALL-US30-018.18 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY - , 7 YEAR,BRIDGE DECK, AS PER SS894 | 2001-12-11 | 7 | 2002-05-14 | 2003-04-22 | 2004-04-18 | 2006-04-06 | [20 empty] | 2008-12-11 | Expired
Bridge | 894 | 21152 | 3014 | 2000 | 2000-3014 | 1 | HAN-SR103-016.57 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY - , 7 YEAR, BRIDGE DECK, AS PER SS894 | 2001-11-01 | 7 | 2002-05-10 | 2003-04-22 | 2004-04-18 | 2006-03-27 | [20 empty] | 2008-11-01 | Expired
Bridge | 894 | 18922 | 83 | 2001 | 2001-0083 | 1 | HAN-SR15-021.52 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-06-14 | 7 | 2002-05-13 | Review Waived | [22 empty] | 2009-06-14 | Expired
Bridge | 894 | 22496 | 135 | 2001 | 2001-0135 | 1 | WYA-US23-12.429 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-08-22 | 7 | 2004-04-18 | 2006-04-11 | [22 empty] | 2009-08-22 | Expired
Bridge | 894 | 10289 | 199 | 2001 | 2001-0199 | 1 | WYA-US30-28.009 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | Assumed Expired | 7 | 2006-04-14 | [6 empty] | Slight cracking | [17 empty] | Expired
Bridge | 894 | 19451 | 330 | 2000 | 2000-0330 | 2 | WOO-IR280-003.85 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-07-25 | 7 | [9 empty] | 8705844 WOO-280-3.85 | [14 empty] | 2009-07-25 | Expired
Bridge | 894 | 20787 | 568 | 2000 | 2000-0568 | 2 | WOO-IR75-000.73 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-12-06 | 7 | 2002-04-03 | 2003-04-10 | 2006-05-10 |  |  |  | 2008-05-27 | Crackings (Minor) | Apply HMWMR as per SS 846 | 8702942 (new) 8702918 (retired) WOO-75-0.73 | [13 empty] | Based on the final district review, the bridges appear to be performing adequately. The district now assumes the maintenance responsibility of the projects and relieves the contractor from the warranty. | 2008-12-06 | Expired
Bridge | 894 | 20761 | 3007 | 2001 | 2001-3007 | 2 | SAN-US6-014.76 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY - | 2002-01-07 | 7 | 2002-04-03 | 2003-04-09 |  |  |  |  | 2009-03-02 | Crackings (Minor) | Apply HMWMR as per SS 846 | 7200277 SAN-6-14.76 L | 7200307 SAN-6-14.76 R | [12 empty] | Based on the final district review, the bridges appear to be performing adequately. The district now assumes the maintenance responsibility of the projects and relieves the contractor from the warranty. | 2009-01-07 | Expired
Bridge | 894 | 20762 | 3008 | 2001 | 2001-3008 | 2 | SAN-US20-014.86 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY - | 2002-01-07 | 7 | 2002-04-03 | 2003-04-09 | 2009-03-02 |  |  |  |  | Crackings (Minor) | Apply HMWMR as per SS 846 | 7201834 SAN-20-14.86 | [13 empty] | Based on the final district review, the bridges appear to be performing adequately. The district now assumes the maintenance responsibility of the projects and relieves the contractor from the warranty. | 2009-01-07 | Expired
Bridge | 894 | 8861 | 421 | 2002 | 2002-0421 | 2 | HAN-IR75-024.02 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2005-05-05 | 7 | 2006-04-25 | 2007-04-25 | 2008-05-25 |  |  |  |  | Map cracking | Seal cracks | 8700826 new 8700818 (retired) WOO-18-14.14 | [13 empty] | Contractor notified of distress and required remedial action | 2012-05-05 | Expired
Bridge | 894 | 25431 | 496 | 2003 | 2003-0496 | 2 | SAN-US20-3.19 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2005-09-08 | 7 |  | 2007-04-05 | [7 empty] | 7201427 (new) 7201419 (retired) SAN-20-3.19 | [14 empty] | 2012-09-08 | Expired
Bridge | 894 | 23956 | 584 | 2004 | 2004-0584 | 2 | OTT-2-28.39 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2007-06-30 | 7 | 2008-04-23 | 2008-05-07 | [5 empty] | Cracking | See file | 6200788 OTT-2-28.39 | [13 empty] | Inspection looked for map or alligator cracking. Contractor notified of action to take. | 2014-06-30 | Expired
Bridge | 894 | 22517 | 95 | 2006 | 2006-0095 | 2 | LUC-475-9.81 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2006-11-20 | 2 | Waived | 2008-05-29 | [5 empty] | Cracks | Repair | 4808010 LUC-475-10.90 | 4808703 LUC-475-9.81R | 4801083 LUC-23-10.06L | 4801113 LUC-23-10.06R | 4801172 LUC-23-10.74R | 4801148 LUC-23-10.74L | 4801237 LUC-23-10.83R | 4801202 LUC-23-10.83L | [6 empty] | Contractor notified of distress and required remedial action | 2008-11-20 | Expired
Bridge | 894 | 11378 | 116 | 2001 | 2001-0116 | 3 | RIC-IR71-013.66 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - , (MIX 4) | 2002-12-27 | 7 | 2003-12-01 | [23 empty] | 2009-12-27 | Expired
Bridge | 894 | 18224 | 200 | 2001 | 2001-0200 | 3 | ASD-US250-023.45 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - (MIX 4) | 2002-04-26 | 7 | [24 empty] | 2009-04-26 | Expired
Bridge | 894 | 14016 | 517 | 2001 | 2001-0517 | 3 | WAY-IR71-000.28 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-11-22 | 7 | [7 empty] | Cracking / Flushing / Disintegration | [16 empty] | 2009-11-22 | Expired
Bridge | 894 | 11385 | 26 | 2002 | 2002-0026 | 3 | LOR-IR90-013.20 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-11-19 | 7 | [24 empty] | 2010-11-19 | Expired
Bridge | 894 | 16284 | 33 | 2002 | 2002-0033 | 3 | CRA-US30-33.500 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-08-04 | 7 | [9 empty] | 33602 (out 8/4/12) | 34250 (out) | 04075 (out) | 02371 (out) | 05405 (out) | [10 empty] | 2012-08-04 | Expired
Bridge | 894 | 16283 | 36 | 2002 | 2002-0036 | 3 | CRA-US30-24.000 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | Non performed | 7 | [25 empty] | Expired
Bridge | 894 | 19491 | 144 | 2002 | 2002-0144 | 3 | LOR-SR57-018.16 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-01-04 | 7 | [24 empty] | 2012-01-04 | Expired
Bridge | 894 | 18579 | 486 | 2002 | 2002-0486 | 3 | RIC-US30-011.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | Non performed | 7 | [25 empty] | Expired
Bridge | 894 | 16282 | 509 | 2002 | 2002-0509 | 3 | CRA-US30-15.865 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | Non performed | 7 | 2006-06-19 | [6 empty] | Minor cracking | HMWM sealing | [16 empty] | Expired
Bridge | 894 | 18632 | 465 | 2003 | 2003-0465 | 3 | RIC-IR71-6.73 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | Non performed | 7 | 2006-06-22 | [6 empty] | Minor cracking | HMWM sealing | RIC-71-0641L | RIC-71-0641R | RIC-71-0652R | RIC-71-0652L | RIC-71-0670L | RIC-71-0670R | RIC-71-0712L | RIC-71-0712R | [8 empty] | Expired
Bridge | 894 | 25880 | 44 | 2004 | 2004-0044 | 3 | WAY US-30 011.86 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, | 2006-05-10 | 7 | 2006-12-11 | [6 empty] | Slight Cracking of decks | sealing of bridge decks | Way-30-1215 Out 12/7/11 | Way-30-1309 LT/RT Out 12/19/12 | Way-30-1366 Out 8/12/012 | Way-30-1551 Out 12/8/12 | Way-30-1662 Out 5/12/12 | Way-30-1752 Out 12/19/12 | Way-30-1803 Out 12/19/12 | Way-30-1907 Out 5/10/13 | [7 empty] | 2013-05-10 | Expired
Bridge | 894 | 18631 | 82 | 2004 | 2004-0082 | 3 | WAY-USR30-9.26 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2006-05-25 | 7 | [9 empty] | 0935 LT Out: 9/9/12 | 0935 RT Out: 5/25/13 | 1039 Out 5/25/13 | [12 empty] | 2013-05-25 | Expired
Bridge | 894 | 19956 | 583 | 2004 | 2004-0583 | 3 | MRW-IR71-019.54 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | Non performed | 7 | [25 empty] | Expired
Bridge | 894 | 14017 | 48 | 2005 | 2005-0048 | 3 | WAY IR-0071 007.04 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | Non performed | 7 | 2007-01-03 | [6 empty] | Cracking | Deck sealing | MED-71-0342 L/R | MED-71-0437 L/R | MED-71-0539 L/R | [11 empty] | Some cracking / piting |  | Expired
Bridge | 894 | 14018 | 343 | 2005 | 2005-0343 | 3 | MED-IR71-009.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 894 | 14018 | 343 | 2005 | 2005-0343 | 3 | MED-IR71-009.56 | SPECIAL - HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | Assumed Expired | 2 | [25 empty] | Expired
Bridge | 894 | 75657 | 349 | 2006 | 2006-0349 | 3 | MED-IR71-006.06 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2009-11-15 | 2 | [24 empty] | 2011-11-15 | Expired
Bridge | 894 | 23109 | 449 | 2007 | 2007-0449 | 3 | HUR-US250-018.39 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2009-09-25 | 2 | [24 empty] | 2011-09-25 | Expired
Bridge | 894 | 18385 | 119 | 2001 | 2001-0119 | 4 | SUM IR 77 24.19 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-06-10 | 7 | 2006-07-25 | 2007-04-30 | [7 empty] | SFN 7704194 SUM 77 25.13 R 10/29/02 | SFN 7704186 SUM 77 25.13 L 6/10/03 | [12 empty] | Varies; See Individual Structure info Refs 166, 207, 308, 316 | 2010-06-10 | Expired
Bridge | 894 | 18715 | 137 | 2001 | 2001-0137 | 4 | ATB-SR534-019.35 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-10-25 | 7 | 2006-08-01 | 2007-05-03 | [7 empty] | 0407119, ATB-SR534-019.35 | [13 empty] | Ref 145 | 2008-10-25 | Expired
Bridge | 894 | 13974 | 256 | 2001 | 2001-0256 | 4 | MAH IR-76 00.86 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-12-08 | 7 | 2005-04-11 | 2006-08-21 | 2007-05-03 | [6 empty] | SFN 5002702 Lake Milton SLM 00.91 L | SFN 5002737 Lake Milton SLM 00.91 R | [12 empty] | Ref 220, 255 | 2010-12-08 | Expired
Bridge | 894 | 16367 | 454 | 2001 | 2001-0454 | 4 | STA-IR77-17.61 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-11-05 | 7 | 2006-08-16 | 2007-04-30 | [7 empty] | SFN 7604718 STA-77-1725 Warr Dat 8-16-02 | SFN 7604807 STA-77-18.53R Warr Dat 11/5/03 | SFN 7604777 STA-77-18.53L Warr Dat 10/7/03 | SFN 7702108 SUM IR-77 00.54 Warr Dat 11/5/03 | [10 empty] | Varies; See Individual Structure info Refs 278, 306, 332, 369 | 2010-11-05 | Expired
Bridge | 894 | 18722 | 3000 | 2001 | 2001-3000 | 4 | MAH-SR11-016.04 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-11-08 | 7 | 2004-05-15 | 2006-08-02 | 2007-04-24 | [6 empty] | SFN 5000807 SR11 SB Over IR 80 EB | SFN 5000815 SR11 NB Ramp Over 11SB | SFN 5000823 SR 11 Ramp Under IR680 WB | [11 empty] | Ref 105 | 2009-11-08 | Expired
Bridge | 894 | 19899 | 3005 | 2001 | 2001-3005 | 4 | ATB-SR11-023.33 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-05-29 | 7 | 2006-08-01 | 2007-05-03 | [7 empty] | SFN '0401382 Over Carson Rd, ATB-SR11-023.33L | [13 empty] | Ref 15 | 2009-05-29 | Expired
Bridge | 894 | 19854 | 3010 | 2001 | 2001-3010 | 4 | POR-US224-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-07-30 | 7 | 2006-07-28 | 2007-04-27 | [21 empty] | Ref 32 | 2009-07-30 | Expired
Bridge | 894 | 18687 | 45 | 2002 | 2002-0045 | 4 | POR-IR76-001.09 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-07-07 | 7 | [24 empty] | 2011-07-07 | Expired
Bridge | 894 | 19920 | 45 | 2002 | 2002-0045 | 4 | POR IR-76 1.09 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-06-25 | 7 | 2006-07-31 | 2007-04-27 |  |  |  |  | 2005-05-18 | [16 empty] | Refs 254, 289 | 2012-06-25 | Expired
Bridge | 894 | 18721 | 70 | 2002 | 2002-0070 | 4 | ATB IR-90 19.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-11-03 | 7 | 2006-08-01 | 2007-05-03 | [7 empty] | SFN 0404446 ATB-90-2172R 10-29-2003 | SFN 0404470 ATB-90-2172L 11-3-2003 | [12 empty] | Varies; See Individual Structure info Refs 167, 190 | 2010-11-03 | Expired
Bridge | 894 | 18688 | 80 | 2002 | 2002-0080 | 4 | STA US-30 29.58 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-10-23 | 7 | 2006-07-24 | 2007-08-25 | [21 empty] | Ref 85 | 2009-10-23 | Expired
Bridge | 894 | 22114 | 231 | 2002 | 2002-0231 | 4 | POR SR-82 10.67 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-12-23 | 7 | 2006-07-27 | 2007-04-27 | [7 empty] | SFN 6703364 Cuyahoga River POR 82 10.67 | [13 empty] | Ref 78 | 2009-12-23 | Expired
Bridge | 894 | 21609 | 467 | 2002 | 2002-0467 | 4 | STA IR-77 12.76 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-05-31 | 7 | 2006-08-16 | 2007-04-25 | [21 empty] | Refs 285, 316, 350, 380, 414, 444 | 2012-05-31 | Expired
Bridge | 894 | 19951 | 545 | 2002 | 2002-0545 | 4 | SUM SR-21 0.26 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-11-03 | 7 | 2006-07-26 | 2007-04-25 | [7 empty] | SFN 7701144 SUM SR 21 0.28 R 11/3/03 | SFN 7701055 SUM SR 21 0.28 L 11/3/03 | SFN 7710895 SUM SR 585 0.61 9/30/03 | [11 empty] | Varies; See Individual Structure info Refs 180, 216, 245 | 2010-11-03 | Expired
Bridge | 894 | 22174 | 3000 | 2002 | 2002-3000 | 4 | ATB SR-11 25.16 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2004-09-05 | 7 | 2006-08-01 | 2007-05-03 | [7 empty] | SFN 0401684 Ashtabula River ATB SR-11 25.16L | SFN 0401714 Ashtabula River ATB SR-11 25.16R | [12 empty] | Refs 25, 31 | 2011-09-05 | Expired
Bridge | 894 | 22229 | 3001 | 2002 | 2002-3001 | 4 | SUM IR-77 15.47 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-08-31 | 7 | 2006-08-15 | 2007-04-25 | [7 empty] | Stoner St. over I-77 | [13 empty] | Ref 21 | 2010-08-31 | Expired
Bridge | 894 | 18718 | 3004 | 2002 | 2002-3004 | 4 | SUM SR-21 0.26 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-09-12 | 7 | 726/2006 | 2007-04-25 | [7 empty] | SFN 7701233 SUM-21-01.79 R 9/12/2003 | [13 empty] | Ref 19 | 2010-09-12 | Expired
Bridge | 894 | 22364 | 118 | 2003 | 2003-0118 | 4 | POR SR-43 8.14 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-11-06 | 7 | 2006-08-16 | 2007-04-27 | [7 empty] | POR-43-2188 | [13 empty] | Ref 204 | 2010-11-06 | Expired
Bridge | 894 | 20410 | 333 | 2003 | 2003-0333 | 4 | STA IR-77 9.46 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-11-16 | 3 | 2005-11-16 | 2007-04-27 |  |  |  |  | 2006-08-24 | [16 empty] | Refs 543, 572, 604, 637, 662 | 2008-11-16 | Expired
Bridge | 894 | 11044 | 511 | 2003 | 2003-0511 | 4 | TRU SR 82 25.24 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-11-18 | 7 | 2006-08-07 | 2007-05-03 |  |  |  |  | 2012-10-24 |  |  | SFN 7804806 TRU-82-25.24 L | SFN 7804830 TRU-82-25.24 R | SFN 7804865 TRU-82-25.42 L | SFN 7804954 TRU-82-25.42 R | SFN 7804989 TRU-82-25.47 L | SFN 7805012 TRU-82-25.47 R | SFN 7805047 TRU-82-29.62 | [7 empty] | Refs 166, 197, 224, 251, 263, 275, 307 | 2012-11-18 | Expired
Bridge | 894 | 21004 | 534 | 2003 | 2003-0534 | 4 | POR IR-76 9.50 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2002-07-30 | 7 | 2006-07-28 | 2007-04-27 | [7 empty] | SFN 402648 | [13 empty] | All bridge painting use same warranty date 7/30/02 Refs 164, 197, 281, 302, 323, 344 | 2009-07-30 | Expired
Bridge | 894 | 23675 | 302 | 2004 | 2004-0302 | 4 | MAH 680 9.92 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-12-03 | 7 | 2006-08-02 | 2007-04-24 | [7 empty] | SFN 5007615 MAH 680 9.92 Under Thalia Ave | [13 empty] | Refs 196, 222 | 2012-12-03 | Expired
Bridge | 894 | 21610 | 532 | 2004 | 2004-0532 | 4 | STA IR 77 14.80 (NB) | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2006-12-13 | 7 | [9 empty] | 1504 R SFN 7604475 | 1516 R SFN 7604564 | 1668 R SFN 7604688 | [11 empty] | Refs 289, 328, 366, 818 | 2013-12-13 | Expired
Bridge | 894 | 21610 | 532 | 2004 | 2004-0532 | 4 | STA IR 77 14.80 (SB) | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2006-11-05 | 7 | [23 empty] | Refs 289, 328, 366, 818 | 2013-11-05 | Expired
Bridge | 894 | 16372 | 582 | 2004 | 2004-0582 | 4 | SUM IR 77 1.40 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2006-09-29 | 7 | 2007-01-17 |  |  |  |  | 2012-04-12 |  | Minor Spalling - 0159NB Driving Lane |  | SFN 7702221 SUM-77-0284 Warr Date 5-15-06 | SFN 7702132 SUM-77-0157 Lt Warr Date 9-29-06 | SFN 7702167 SUM-77-0157 Rt Warr Date 10-11-06 | SUM-77-0378 Warr Date: 8/11/05 | [10 empty] | Ref nos. 226, 257, 290, 330 | 2013-09-29 | Expired
Bridge | 894 | 21005 | 633 | 2004 | 2004-0633 | 4 | TRU SR 5 12.50 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-11-07 | 7 | 2006-08-07 | 2007-05-03 |  |  |  |  | 2012-04-03 |  |  | SFN 7800967 TRU-5-1393 L 5/11/ 2005 | SFN 7800991 TRU-5-1393 R 11/7/ 2005 | SFN 7801025 TRU-5-1411 L 5/11/ 2005 | SFN 7801084 TRU-5-1411 R 11/7/ 2005 | TRU SR 82 1722E 5/11/2005 | TRU SR 82 1722W 11/07/2005 | [8 empty] | Varies; See Individual Structure info Refs 227, 256, 278, 300, 334 Relieved of Warranty per 4/4/12 Correspondence | 2012-11-07 | Expired
Bridge | 894 | 19940 | 122 | 2005 | 2005-0122 | 4 | STA SR 183 3.26 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-12-27 | 7 | 2006-07-24 | 2007-04-25 | [7 empty] | SFN 7605609 STA 183 0326 | [13 empty] | Ref 74 | 2012-12-27 | Expired
Bridge | 894 | 21450 | 316 | 2005 | 2005-0316 | 4 | SUM IR 271 8.02 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2008-10-24 | 7 | [6 empty] | 2009-09-18 |  |  | SUM 271-0802L: 7709005 | SUM 271 0854L: 7709099 | [12 empty] | Held review 4/23/15 - Patching of some spalls will be peformed on the SB deck. Patching completed 5/19/15 | 2015-10-24 | Expired
Bridge | 894 | 21450 | 316 | 2005 | 2005-0316 | 4 | SUM IR 271 8.02 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2007-11-30 | 7 | [6 empty] | 2009-09-18 |  |  | SUM 271-0802R: 7709064 | SUM 271 0854R: 7709129 | [12 empty] | Refs 274, 312, 441, 470 | 2014-11-30 | Expired
Bridge | 894 | 7904 | 358 | 2005 | 2005-0358 | 4 | TRU SR 534 15.06 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2006-05-10 | 7 | 2006-08-07 | 2007-05-03 |  |  |  |  | 2013-04-30 | 4/30/2013 - Minor Spalling deficiencies were observed on Structure TRU 534-15.16 |  | SFN 7807457 TRU-534-15.16 | [13 empty] | Ref 105 | 2013-05-10 | Expired
Bridge | 894 | 20412 | 583 | 2005 | 2005-0583 | 4 | STA IR 77 10.33 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2008-06-03 | 2 | [23 empty] | Comp Date 6/30/08 Refs 569, 605, 648 | 2010-06-03 | Expired
Bridge | 894 | 16514 | 151 | 2006 | 2006-0151 | 4 | SUM IR 77 21.79 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2008-11-06 | 2 | [23 empty] | Completion Date 9-30-08 Refs 357, 393, 512, 547, 615 | 2010-11-06 | Expired
Bridge | 894 | 23752 | 89 | 2007 | 2007-0089 | 4 | MAH US 62 00.10 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2007-10-06 | 2 | [9 empty] | SFN 5008514 MAH US 62 0.10RT | SFN 5008522 MAH US 62 0.10LT | [12 empty] | Completion Date 10/15/2010 Ref 175 | 2009-10-06 | Expired
Bridge | 894 | 16105 | 533 | 2000 | 2000-0533 | 5 | LIC-SR661-000.24 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - , MIX 4 | 2001-12-07 | 7 | 2003-10-31 | 2006-01-19 | [7 empty] | LIC-661-0024 | [13 empty] | No distress to date | 2008-12-07 | Expired
Bridge | 894 | 13281 | 68 | 2002 | 2002-0068 | 5 | FAI-US33-000.41 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - (MIX 3) | 2004-10-05 | 7 | 2006-01-13 | 2007-04-19 | [7 empty] | FAI-33-0110 | [13 empty] | Minor scaling on NB lanes of Span 2 | 2011-10-05 | Expired
Bridge | 894 | 16294 | 110 | 2002 | 2002-0110 | 5 | FAI-US33-013.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-11-22 | 7 | 2006-01-13 | 2007-04-19 | [7 empty] | FAI-33-1417L | FAI-33-1417R | [12 empty] | No distress to date | 2011-11-22 | Expired
Bridge | 894 | 19433 | 119 | 2002 | 2002-0119 | 5 | GUE-SR209-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - , (MIX 3) | 2002-09-30 | 7 | 2006-01-18 | [8 empty] | GUE-209-0663 | [13 empty] | No distress to date | 2009-09-30 | Expired
Bridge | 894 | 19821 | 3005 | 2002 | 2002-3005 | 5 | GUE-77-7.54 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-10-28 | 7 | 2006-01-18 | 2007-04-23 | [7 empty] | GUE-77-0754 | GUE-77-0768 | [12 empty] | No distress to date | 2011-10-28 | Expired
Bridge | 894 | 23057 | 46 | 2003 | 2003-0046 | 5 | FAI-US33-019.79 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-10-26 | 7 | 2006-01-04 | 2007-04-19 | [5 empty] | Slight scaling on FAI-33-2092R |  | FAI-33-2092R | FAI-33-2092L | FAI-33-2065R | FAI-33-2065L | [11 empty] | 2012-10-26 | Expired
Bridge | 894 | 11723 | 207 | 2003 | 2003-0207 | 5 | GUE-SR209-011.50 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - , MIX 4 | 2004-11-18 | 7 | 2006-01-18 | 2007-04-23 | [7 empty] | GUE-209-1191 | [13 empty] | No distress to date | 2011-11-18 | Expired
Bridge | 894 | 21647 | 484 | 2003 | 2003-0484 | 5 | FAI-SR158-8.87 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | Non performed | 7 | [25 empty] | Expired
Bridge | 894 | 13421 | 565 | 2003 | 2003-0565 | 5 | LIC-US40-20.236 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-04-30 | 7 | 2006-01-19 | [8 empty] | LIC-40-1263 | [13 empty] | No distress to date | 2011-04-30 | Expired
Bridge | 894 | 19627 | 588 | 2003 | 2003-0588 | 5 | GUE-IR70/SR723-6.11/0.38 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-08-13 | 7 | 2006-01-18 | 2007-04-27 | [7 empty] | GUE-723-0038 | [13 empty] | No distress to date | 2011-08-13 | Expired
Bridge | 894 | 19834 | 157 | 2004 | 2004-0157 | 5 | LIC-SR668-1.92 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-09-08 | 7 | [24 empty] | 2011-09-08 | Expired
Bridge | 894 | 13411 | 353 | 2004 | 2004-0353 | 5 | COS-US36-11.282 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2005-11-04 | 7 | 2006-01-17 | 2007-04-19 | [7 empty] | COS-36-0701 | [13 empty] | No distress to date | 2012-11-04 | Expired
Bridge | 894 | 24486 | 150 | 2006 | 2006-0150 | 5 | FRA/LIC-161-23.20/0.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2008-10-21 | 2 | [24 empty] | 2010-10-21 | Expired
Bridge | 894 | 77221 | 138 | 2007 | 2007-0138 | 5 | LIC-161/37-6.65/10.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2009-07-31 | 2 | [9 empty] | LIC-37-1405 RT | LIC-37-1225 RT | [13 empty] | 2011-07-31 | Expired
Bridge | 894 | 77221 | 138 | 2007 | 2007-0138 | 5 | LIC-161/37-6.65/10.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2010-05-04 | 2 | [9 empty] | LIC-37-1225 LT | [14 empty] | 2012-05-04 | Expired
Bridge | 894 | 4354 | 35 | 2002 | 2002-0035 | 6 | FRA-IR670-002.61 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-09-19 | 7 | 2004-03-08 | 2005-08-04 | Review waived 2006 | 2007-02-21 | 2008-03-12 | 2009-03-30 | 2010-04-01 |  |  | 2517574 L/R | 2517590 | 2517612 | 2517639 | 2517647 L/R | [9 empty] | First 2 years project reviewed and structures were found to have no deficiences. Will final review in August of 2010 unless there is a problem. ON 2/21/07 NO PROBLEMS FOUND 03/12/08 no problems found 03/30/09 decks look good no distress types found 04/2010no waranty issues | 2010-09-19 | Expired
Bridge | 894 | 16670 | 150 | 2002 | 2002-0150 | 6 | FRA-IR270-048.47 (WB) | HIGH PERFORMANCE CONCRETE FOR BRIDGE DECK WITH WARRANTY | 2003-11-25 | 7 | 2004-03-08 | 2005-07-28 | Review waived 2006 | 2007-02-23 | 2008-03-13 | 2009-03-30 | 2010-04-01 |  |  | 2513749 | 2513684 | [12 empty] | 2/23/07 NO DISTRESS TYPES FOUND 03/13/08--small diagonal crack under limits. 03/30/09 everything looks good no distress types found 04/2010 no warranty issues found | 2010-11-25 | Expired
Bridge | 894 | 16670 | 150 | 2002 | 2002-0150 | 6 | FRA-IR270-048.47 (EB) | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-11-25 | 7 | 2004-03-08 | 2005-07-28 | Review waived 2006 | 2007-02-23 | 2008-03-13 | 2009-03-30 | 2009-10-01 |  |  | 2513714 | 2513625 | [12 empty] | 2/23/07 NO DISTRESS TYPES FOUND 03/13/08 -- no distress types found 03/30/09 everything looks good no distresstypes found PROJECT OUT OF WARRANTY LETTER SENT TO CONTRACTOR AND BONDING AGENCY 11/27/09. | 2009-11-25 | Expired
Bridge | 894 | 22359 | 107 | 2003 | 2003-0107 | 6 | FRA-IR270-004.97 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-06-24 | 7 | 2005-07-28 | 2006-03-22 | 2007-02-21 | 2008-03-13 | 2009-03-30 | 2010-04-01 |  |  |  | 2512637 L | 2512602 R | [12 empty] | 3/22/2006--drt team no distress problems found in good shape 2/21/07--NO DISTRESS TYPES FOUND 03/13/08 --- no distress types found 03/30/09 concrete looks good on decks no distress types found. 04/2010 no warranty issues | 2011-06-24 | Expired
Bridge | 894 | 6225 | 134 | 2003 | 2003-0134 | 6 | FAY-IR71-00.00 (SB) | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-06-23 | 7 | 2006-04-08 | 2007-03-02 | 2008-04-30 |  | 2010-03-01 |  |  |  |  | 2401681 | 2401746 | 2401924 | 2401983 | 2402041 | 2402106 | [8 empty] | 4/8/06 cracking within distress level of 0 to 20% found. Letter to contractor of findings 4/13/06 5/8/06 received contractor letter of remedial actions, seal cracks replace deteriorated concrete at joint waiting on DCE okay to proceed. Contractor also asked for time an work records to be kept as may claim for compensation of crack sealing 3/2/07-review overall good condition-any scalling less than 5% of deck . Notified on 6/7/07 by chief legal they (J. Jurgenson) have filed a civil claim. Correspondence, pictures, etc. sent to V. Schawber at chief legal on 6/12/07 2008 warranty review- no show by contractor-- 7.1 structure approach slab settlement, not a warranty issue- this has been given to our bridge dept engr. robert taylor Letter to contractor 5/5/08 03/2010--prelim review by Fayette County everything below threshold of warranty, some minor cracking and spalling but not a warranty issue at this time no review of structures required at this time by Warranty DRT | 2012-06-23 | Expired
Bridge | 894 | 6225 | 134 | 2003 | 2003-0134 | 6 | FAY-IR71-000.00 (NB) | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-07-21 | 7 | 2005-08-06 | 2006-04-08 | 2007-03-02 | 2008-04-30 | 2010-03-01 |  |  |  |  | 2401711 | 2401770 | 2401959 | 2402017 | 2402076 | 2402130 | [8 empty] | 8/11/05 letter to contractor on deficiences.(cracking/ Contracto sealed with hmwm. Being handled by Chief Legal as contractor has filed a claim (aggregate , design) 04/08/06 no distress types found 3/2/07--review overall good condition-any scalling less than 5% of deck Central Office resolution team denied claim by contractor on warry sealing of structures. Notified on 6/7/07 by chief legal they (J. Jurgenson)have filed a civil claim. Correspondence,pictures, etc sent to v. schawger at chief legal 6/12/07. 2008 warranty review. no show by contractor. Major spalling on .28 structure inside shoulder, inside lane and middle lane. PCB holes that had been filled have lost material and need refilled on structures, l28, .47, 3.01, 3.85 and 7.1 Letter of review sent to contractor 5/5/08. 03/2010--prelim review by Fayette County everything below threshold of warranty, some minor cracking and spalling but not a warranty issue at this time no review of structures required at this time by Warranty DRT | 2011-07-21 | Expired
Bridge | 894 | 16671 | 463 | 2003 | 2003-0463 | 6 | FRA-270-0.60 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | Non performed | 7 | [23 empty] | NOT A WARRANTY ITEM |  | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-10-24 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-10-24 | 2512378 | [12 empty] | May 28, 2008 okay 04/24/09 -- alligator/map cracking of tunnel ceiling approaching 20%. Construction joint opening and seeping water. Not possible to apply HMWM per SS894 as this is the bottom side of the tunnel roof. Review closely again next year 04/2010 no warranty issues found | 2014-10-24 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-10-24 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-10-24 | 2509644 | [12 empty] | May 28, 2008 okay 04/24/09----minor transverse cracking in spans 1, 2, and 3: spalling along north parapet west end. 0 to 20% cracks. Hmwm applied during summer 2008 to these cracks via punch list. 04/2010 no warranty issues found | 2014-10-24 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-11-03 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-11-03 | 2509563 | [12 empty] | May 28, 2008 okay 04/24/09-----no warrnty issues 04/2010 no warranty issues found | 2014-11-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-11-03 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-11-03 | 2509628 | [12 empty] | May 28, 2008 okay 04/24/09-----no warrnty issues 04/2010 no warranty issues found | 2014-11-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270- 25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-10-24 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-10-24 | 2509598 | [12 empty] | May 28, 2008 okay 04/24/09three mid span cracks in span 3(minor) no remedial actions necessary at this time 04/2010 no warranty issues found | 2014-10-24 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270- 25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-10-03 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-10-03 | 2509199 | [12 empty] | May 28, 2008 okay 04/24/09---minor longitudinal cracking 0 to 20% cracks. HMWM applied during summer 2008 to these cracks via punch list. 04/2010 no warranty issues found | 2014-10-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270- 25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-10-03 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-10-03 | 2509172 | [12 empty] | May 28, 2008 okay 04/24/09--minor longitudinalcracking 0 to 20% cracks. HMWM applied during summer 2008 to these cracks via punch list. 04/2010 no warranty issues found | 2014-10-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270- 25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-10-03 | 7 | 2008-05-01 | 2009-04-24 | 2010-04-01 | [6 empty] | 2014-10-03 | 2509202 | [12 empty] | May 28, 2008 okay 04/24/09--minor longitudinalcracking 0 to 20% cracks. HMWM applied during summer 2008 to these cracks via punch list. 04/2010 no warranty issues found. | 2014-10-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE | 2007-11-08 | 7 | 2008-05-01 | 2009-04-24 | SAME AS | 2512351 | 2010-04-01 |  |  | SAME AS | 2512351 | 2014-11-08 | 2509075 | THIS IS SFN | 2512351 | PER BOB TAYLOR | [9 empty] | May 28, 2008 okay04/24/09 --no warranty issues 04/2010 no warranty issues found | 2014-11-08 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE 49252 270 | 2006-10-03 | 7 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 | [5 empty] | 2512386 | [13 empty] | 2/27/07 NO DISTRESS TYPES FOUND 03/13/08 no distress type over threshold limits found 03/30/09 looks good 04/2010 no warranty issues found | 2013-10-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE 26702R IR-161 | 2006-11-15 | 7 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 | [5 empty] | 2509520 | [13 empty] | 2/27/07 NO DISTRESS TYPES FOUND 03/13/08===no distress type over threshold limits found 03/30/09 looks good 04/2010 no warranty issues found | 2013-11-15 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE 49037 270 | 2006-10-03 | 7 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 | [5 empty] | 2512351 | [13 empty] | 2/27/07 NO DISTRESS TYPES FOUND 03/13/08 == no distress types found small holes from popped out stone. 03/30/09 looks good 04/2010 no warranty issues found | 2013-10-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE 49058 270 | 2006-10-03 | 7 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 | [5 empty] | 2509149 | [13 empty] | 2/27/07 NO DISTRESS TYPES FOUND 03/13/08 no distress type over threshold limits found 03/30/09 looks good 04/2010 no warranty issues found | 2013-10-03 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA. SR161/I-270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE 49064 FRA-270 | 2005-12-22 | 7 | 2006-03-22 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 |  |  |  |  | 2509113 | [13 empty] | no alligator/map cracking found-drt 3/22/06 2/27/07 NO DISTRESS TYPES FOUND 03/13/08-minor cracking not reaching distress type 03/30/09 looks good 04/2010 no warranty issues found | 2012-12-22 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMANCE CONCRETE FOR STRUCTURE 49107L 270 | 2006-09-29 | 7 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 | [5 empty] | 2509059 | [13 empty] | 2/27/07 NO DISTRESS TYPES FOUND 03/13/08 == no distress types found 03/30/09 looks good 04/2010 no warranty issues found | 2013-09-29 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA. SR161/I-270-25.9/40.2 | HIGH PERFORMANCE CONCRETE, FOR DEMPSEY RD. 47636 i-270 BRIDGE DECK, WITH WARRANTY | 2004-12-21 | 7 | Review Waived 2005 | 2006-03-22 | 2007-02-27 | 2008-03-13 | 2009-03-30 |  |  | majorscalling3/22/06 |  | 2511895 | [13 empty] | 2/27/07-REPAIR OF DECK WILL OCCUR SOMETIME THIS SUMMERproject notes there is spalling on deck will look at in spring of 06. final inspection was not done until 11-21-05 majorscalling3/22/06To be peformed towards completion of project due to traffic control conflictions. Project completion is projected to be in 2007 and remedial actions will happen prior to completeion. Letter received on 5/2/06 from contractor. 3/22/06 80-100% of entire deck surface has scaling occuring 1/4" or more on average along wb edge 2/8"off face of curb. Face of curb where hand rubbed peeling concrete looks good though. Eblane rear 1/4" scalingsending letter to contractor with findings . Something definitely needs donedan johnson, project enginee stated 2/3 of deck was poured when rain hit poured from east to west3/24/06 letter to contractor on findings. 4/25/06 reminder letter have not received a response from 3/24/06 correspondence. E-mail rec'd from D. Johnson ODOT engineer May 2007 concerning deck repair--on file. July 9, 2007 letter received from NECC asking to perform remedial action on major scaling problem with minor scaling action. July 31, 2007 sent response to NECC deny request, remedial action should be for major scaling. August 15, 2007 received certified letter from NECCO rejecting our findings and sending a copy of letter to J Petro (DRB)and W. Lindenbaum(DDConst Dept of Trans) and Dist 6 DE Brad Jones). 8/16/07 sent e-mail to project eng. B. Hupp asking for diaries, test data concerning concrete placement for deck. 8/27/07 met with Lloyd Welker, B. Hupp, D. Johnson and B. Jones --Mr. Welker said that letter from National requesting to mill and seal acceptable, in his opionin will solve scaling issue. Deck is structurally sound. Brian to inform National. 03/13/08==everything looks okay previous repair holding up 03/3009 looks good 04/2010 no warranty issues found | 2011-12-21 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA SR 161/I 270-25.9/40.2 | HIGH PERFORMSNCE CONCRETE FOR STRUCTURE 26748L 161 | 2006-07-28 | 7 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 | [5 empty] | 2509539 | [13 empty] | 2/27/07 NO DISTRESS TYPES FOUND 03/13/08==minor cracking not reaching distress type 03/30/09 looks good 04/2010 no warranty issues found | 2013-07-28 | Expired
Bridge | 894 | 77003 | 163 | 2004 | 2004-0163 | 6 | FRA. SR161/I-270-25.9/40.2 | HIGH PERFORMSNCE CONCRETE FOR STRUCTURE 49208 I-270 | 2005-12-22 | 7 | 2006-03-22 | 2007-02-27 | 2008-03-13 | 2009-03-30 | 2010-04-01 |  |  |  |  | 2516616 | [13 empty] | no alligator/map cracking found-drt 3/22/06 2/27/07 DISTRESS TYPES FOUND 03/13/08--no distress types found 03/30/09 looks good 04/2010 no warranty issues found | 2012-12-22 | Expired
Bridge | 894 | 77118 | 294 | 2004 | 2004-0294 | 6 | MAD-70-0.00 | HIGH PERFMANCE CONCRETE FOR BRIDGE DECK W/ WARRANTY EASTBOUND | 2005-11-20 | 7 | 2006-03-20 | Review waived 2007 | 2008-04-14 | 2009-02-24 | 2010-04-22 |  |  |  |  | 4902521 | 4902319 | [12 empty] | 3/20/06--no defeciencies foundsee comments above 04/14/08---epoxy that has come out on structure from the barrier wall holes will be replaced by contractor .small amount of scalpiing from snow plows-not warranty issue. 03/15/2010 prelim by county manager 1.88 EB needs looked out. Epoxy out of barrier wall pin holes?????? REVIEW SET UP FOR APRIL 22, 2010. 4/22/10 hole popout in rear approach not contractor responsibility county will fill. | 2012-11-20 | Expired
Bridge | 894 | 77118 | 294 | 2004 | 2004-0294 | 6 | MAD-70-0.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - westbound | 2006-11-29 | 7 | Review waived 2007 | 2008-04-14 | 2009-02-24 | 2010-03-15 | [5 empty] | 4902491 | 4902289 | [12 empty] | 04/14/08 review everything okay at this time 03/15/2010prelim by county manager some minor cracking past 2 year threshold no need to review by DRT this year. 04/22/10 no warranty issues | 2013-11-29 | Expired
Bridge | 894 | 25714 | 274 | 2005 | 2005-0274 | 6 | FRA-IR70-7.94 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK, WITH WARRANTY | 2005-09-22 | 7 | 2006-03-22 | 2007-02-23 | 2008-03-13 | 2009-03-30 | 2010-04-01 |  |  |  |  | 2504308 |  | 1205307 | 4902386 | [10 empty] | 3/22/06 no problems found2/23/07-NO DISTRESS TYPES FOUND 03/13/08 NO DISTRESS TYPES FOUND 03/30/09 NO DISTRESS TYPES FOUND 04/2010 no warranty issues found | 2012-09-22 | Expired
Bridge | 894 | 17411 | 527 | 2000 | 2000-0527 | 7 | DAR-SR47-004.69 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-08-17 | 7 | 2002-09-27 | 2003-09-18 | 2004-01-20 | 2005-04-13 | [20 empty] | 2008-08-17 | Expired
Bridge | 894 | 17452 | 564 | 2000 | 2000-0564 | 7 | SHE-SR274-008.96 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-11-12 | 7 | 2002-10-11 | 2003-06-05 | 2004-08-02 | 2005-07-07 | [20 empty] | 2008-11-12 | Expired
Bridge | 894 | 17452 | 564 | 2000 | 2000-0564 | 7 | SHE-SR274-008.96 | SPECIAL - STRUCTURAL CONCRETE WITH WARRANTY - CORING DECK | 2001-11-12 | 7 | 2002-10-11 | 2003-09-17 | [5 empty] | Cracking | Bridge Deck sealed | [15 empty] | 2008-11-12 | Expired
Bridge | 894 | 13147 | 206 | 2001 | 2001-0206 | 7 | DAR-SR705-015.99 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-11-23 | 7 | 2002-09-27 | 2003-09-18 | 2004-02-13 | 2005-04-06 |  |  | 2005-04-06 | [17 empty] | 2008-11-23 | Expired
Bridge | 894 | 17448 | 468 | 2001 | 2001-0468 | 7 | CLA-IR70-006.34 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2005-02-08 | 7 | [24 empty] | 2012-02-08 | Expired
Bridge | 894 | 17461 | 569 | 2002 | 2002-0569 | 7 | SHE-IR75-002.35 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | Assumed Expired | 7 | [25 empty] | Expired
Bridge | 894 | 19070 | 100 | 2003 | 2003-0100 | 7 | MOT-IR75-31.842 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-08-04 | 7 | [9 empty] | MOT-075-32721 (Start: 8/4/05-7yr) | MOT-75-31849 (Start 9/9/07-7yr) | MOT-75-25218 (Start 9/9/07-7yr) | MOT-75-26876 (Start 9/9/07-7yr) | MOT-75-32721 (Start 9/9/07-7yr) | [10 empty] | 2012-08-04 | Expired
Bridge | 894 | 17450 | 474 | 2003 | 2003-0474 | 7 | MOT-IR75-10.55L/12.69L | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-08-25 | 7 | 2005-06-19 | [23 empty] | 2011-08-25 | Expired
Bridge | 894 | 22168 | 595 | 2003 | 2003-0595 | 7 | MIA-IR75-11.46 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-11-17 | 7 | 2005-06-01 | [23 empty] | 2011-11-17 | Expired
Bridge | 894 | 22619 | 88 | 2004 | 2004-0088 | 7 | DAR-SR127-24.04 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | Assumed Expired | 7 | [25 empty] | Expired
Bridge | 894 | 17097 | 8000 | 2004 | 2004-8000 | 7 | CLA-SR4-005.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-06-20 | 7 | [9 empty] | CLA-4-0851L (Ref#174: Start 12/23/05-7yr) | CLA-4-1102L (Ref#174: Start 12/23/05-7yr) | CLA-4-0851R (Ref#147: Start 06/20/05-7yr) | CLA-4-1102R (Ref#209: Start 06/20/05-7yr) | [11 empty] | 2012-06-20 | Expired
Bridge | 894 | 17106 | 430 | 2001 | 2001-0430 | 8 | WAR-SR73-008.79 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-08-07 | 7 | [8 empty] | Warranty not applied to project | [15 empty] | 2009-08-07 | Expired
Bridge | 894 | 16380 | 229 | 2000 | 2000-0229 | 9 | BRO-SR763-16.036 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-08-15 | 7 | 2002-08-23 | 2003-09-08 |  |  |  |  | 2008-06-22 | Minor Cracking | Bridge Cracks Sealed | Bro-763-9.98 | [13 empty] | Warranty released. | 2008-08-15 | Expired
Bridge | 894 | 13171 | 237 | 2000 | 2000-0237 | 9 | HIG-SR131-06.190 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2000-10-26 | 7 | 2001-12-18 | 2002-12-03 | 2004-11-09 |  |  |  | 2007-10-02 | Minor Cracking | Bridge Cracks Sealed | Hig-131-3.85 | [14 empty] | 2007-10-26 | Expired
Bridge | 894 | 13169 | 459 | 2000 | 2000-0459 | 9 | HIG-SR28-14.045 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-10-10 | 7 | 2002-12-03 | 2003-09-08 | 2004-11-09 | 2005-03-03 |  |  |  | Minor Cracking, Minor Deck Scaling, Intermediate Deck Scaling | Cracks Sealed, Grinding/Grooving/ Sealing, Removal/Patching/ Sealing | Hig-28-8.74 | [13 empty] | Structure will be overlaid with asphalt under project 536-05 (Highland-28-7.38) in 2006. When completed, warranty will cease. | 2008-10-10 | Expired
Bridge | 894 | 12917 | 488 | 2000 | 2000-0488 | 9 | ROS-SR159-000.42 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - (DECK AND DIAPHRAGM) | 2002-10-17 | 7 | 2003-10-16 | 2004-10-20 | [7 empty] | Ross-159-0.43 | [14 empty] | 2009-10-17 | Expired
Bridge | 894 | 19307 | 3000 | 2000 | 2000-3000 | 9 | ROS-SR159-0.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2000-12-04 | 7 | 2001-12-18 | 2002-12-03 | [5 empty] | Minor Cracking | Bridge Cracks Sealed | Ross-159-3.13-L | [14 empty] | 2007-12-04 | Expired
Bridge | 894 | 19307 | 3000 | 2000 | 2000-3000 | 9 | ROS-SR159-0.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2000-12-04 | 7 | 2001-12-18 | 2002-12-03 | [5 empty] | Minor Cracking | Bridge Cracks Sealed | Ross-159-3.13-R | [14 empty] | 2007-12-04 | Expired
Bridge | 894 | 12887 | 54 | 2001 | 2001-0054 | 9 | ADA-SR73-16.320 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-11-21 | 7 | 2003-10-16 | 2004-11-09 | [5 empty] | Minor Cracking | Bridge Cracks Sealed | Adams-73-10.17 | [14 empty] | 2009-11-21 | Expired
Bridge | 894 | 12887 | 54 | 2001 | 2001-0054 | 9 | ADA-SR73-19.240 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-11-21 | 7 | 2003-10-16 | 2004-11-09 | [5 empty] | Minor Cracking | Bridge Cracks Sealed | Adams-73-12.03 | [14 empty] | 2009-11-21 | Expired
Bridge | 894 | 12887 | 54 | 2001 | 2001-0054 | 9 | ADA-SR73-21.300 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-11-21 | 7 | 2003-10-16 | 2004-11-09 | [5 empty] | Minor Scaling | Sandblast and Seal | Adams-73-13.25 | [14 empty] | 2009-11-21 | Expired
Bridge | 894 | 12909 | 57 | 2001 | 2001-0057 | 9 | HIG-SR753-00.140 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-09-05 | 7 | 2002-12-03 | 2003-09-08 | [5 empty] | Minor Cracking | Bridge Cracks Sealed | Hig-753-0.17 | [14 empty] | 2008-09-05 | Expired
Bridge | 894 | 13226 | 118 | 2001 | 2001-0118 | 9 | SCI-US52-32.686 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - (INCLUDING END DIAPHRAGM) | 2002-01-08 | 7 | 2002-12-09 | 2003-12-09 |  |  |  |  | 2008-10-03 |  |  | Sci-52-2032 | [13 empty] | Warranty released. | 2009-01-08 | Expired
Bridge | 894 | 11858 | 178 | 2001 | 2001-0178 | 9 | SCI-US23-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2006-10-16 | 7 | 2007-10-05 | 2007-09-19 | 2008-04-07 |  |  |  | 2013-10-08 | Map Cracking | High Molecular Weight Methacrylate as per spec. | 7300025 | [13 empty] | Warranty applies to approach and main spans. | 2013-10-16 | Expired
Bridge | 894 | 13166 | 251 | 2001 | 2001-0251 | 9 | JAC-SR279-000.71 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-07-23 | 7 | 2003-07-14 | 2004-06-16 |  |  |  |  | 2009-06-02 | Minor Cracking | Bridge Cracks Sealed | Jack-279-0.73 | [13 empty] | Cracking not severe; consistent with initial inspection. A few more cracks on forward pier than on rear. Cracking under 20% of the deck area. | 2009-07-23 | Expired
Bridge | 894 | 13166 | 251 | 2001 | 2001-0251 | 9 | JAC-SR279-000.71 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-07-23 | 7 | 2003-07-14 | 2004-06-16 | [5 empty] | Minor Cracking | Bridge Cracks Sealed | Jack-279-2.11 | [14 empty] | 2009-07-23 | Expired
Bridge | 894 | 15438 | 446 | 2001 | 2001-0446 | 9 | JAC-SR32-27.631 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2006-04-24 | 7 | 2007-04-27 | [5 empty] | 2013-03-25 |  | None | Jack-32-16.58 | [13 empty] | DRT results okay. | 2013-04-24 | Expired
Bridge | 894 | 15438 | 446 | 2001 | 2001-0446 | 9 | JAC-SR32-27.631 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-08-02 | 7 | 2005-11-22 | [5 empty] | 2011-06-30 | Minor cracking | HMWM seal | JAC-32-1712/L | [13 empty] | (7/6/2011) Found no spalling or scaling of the bridge deck overlay which represents the top of the deck. It was noted that the minor cracking obsevred at the previous review was not sealed as suggested. | 2011-08-02 | Expired
Bridge | 894 | 19642 | 285 | 2003 | 2003-0285 | 9 | LAW-SR7-7.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2007-11-21 | 7 | 2008-11-24 |  |  |  |  | 2013-04-24 | 2014-10-22 | Cracking | Seal with High Molecular Weight Methcrylate | Law-775-00.81 | 4404394 | [12 empty] | Cracking was less than 20% of the deck area. Diagonoal cracks and a few longitudinal cracks. A few transverse cracks. No map cracking. | 2014-11-21 | Expired
Bridge | 894 | 19642 | 285 | 2003 | 2003-0285 | 9 | LAW-SR7-7.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2007-11-21 | 7 | 2008-11-24 |  |  |  |  | 2013-04-24 | 2014-10-22 | Cracking | Seal with High Molecular Weight Methcrylate | Law-7-8.40 -R | 4400615 | [12 empty] | Cracking was less than 20% of the deck area. Diagonoal cracks and a few longitudinal cracks. A few transverse cracks. No map cracking. | 2014-11-21 | Expired
Bridge | 894 | 19642 | 285 | 2003 | 2003-0285 | 9 | LAW-SR7-7.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2007-11-21 | 7 | 2008-11-24 |  |  |  |  | 2013-04-24 | 2014-10-22 | Cracking | Seal with High Molecular Weight Methcrylate | Law-7-8.91-R | 4400674 | [12 empty] | Cracking was less than 20% of the deck area. Diagonoal cracks and a few longitudinal cracks. A few transverse cracks. No map cracking. **Update** During inspection on 10/22/14, two areas of spalling were found and the contractor was notified to have work completed by 5/31/15. District 9 received email from The Ruhlin Company that a remedial plan would be submitted in January 2015. | 2014-11-21 | Expired
Bridge | 894 | 18492 | 533 | 2004 | 2004-0533 | 9 | ROS-207-0.00 | HIGH PERFORMANCE CONCRETE FOR BRIDGE DECK WITH WARRANTY | 2007-10-25 | 7 | 2008-10-27 |  |  | 2011-04-29 |  |  |  | Cracking | High Molecular Weight Methacrylate as per 894. | ROS-207-1.63 | 7104928 | [12 empty] | Longitudinal and transverse cracks over 20% of the deck area. Map cracking was seen, but limited to less than 20% of the deck area. (4/29/2011): Pavement is performing well. Condition is consistent with its age. No signs of distress at the intersection. Car fire occurred at the railroad overpass years ago, pavement affected is not part of warranty. No issues at this time. | 2014-10-25 | Expired
Bridge | 894 | 18492 | 533 | 2004 | 2004-0533 | 9 | ROS-207-0.00 | HIGH PERFORMANCE CONCRETE FOR BRIDGE DECK WITH WARRANTY | 2007-10-25 | 7 | 2008-10-27 | [6 empty] | Cracking | High Molecular Weight Methacrylate as per 894. | ROS-207-0.85 | 7104901 | [13 empty] | 2014-10-25 | Expired
Bridge | 894 | 18492 | 533 | 2004 | 2004-0533 | 9 | ROS-207-0.00 | HIGH PERFORMANCE CONCRETE FOR BRIDGE DECK WITH WARRANTY | 2007-10-25 | 7 | 2008-10-27 | [6 empty] | Cracking | High Molecular Weight Methacrylate as per 894. | ROS-207-0.24 | 7104847 | [13 empty] | 2014-10-25 | Expired
Bridge | 894 | 10213 | 427 | 2000 | 2000-0427 | 10 | MRG-SR669-00.209 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-11-13 | 7 | 2002-10-01 | [5 empty] | 2008-11-13 | [16 empty] | End of warranty period; no remedial action required. | 2008-11-13 | Expired
Bridge | 894 | 13204 | 503 | 2000 | 2000-0503 | 10 | MEG-SR124-012.52 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-11-07 | 7 | 2002-11-08 | [5 empty] | 2008-11-10 | [16 empty] | End of the warranty period; no remedial action required. | 2008-11-07 | Expired
Bridge | 894 | 19738 | 145 | 2001 | 2001-0145 | 10 | MEG-SR124-031.57 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-06-25 | 7 | 2005-11-23 | [5 empty] | 2010-06-21 | [16 empty] | End of warranty period (June 22 2010 Correspondence); no remedial action required. | 2010-06-25 | Expired
Bridge | 894 | 19718 | 229 | 2001 | 2001-0229 | 10 | MEG-SR124-022.72 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-10-14 | 7 | 2005-11-23 | 2006-02-24 |  |  |  | 2010-10-27 | 2011-09-16 | [16 empty] | 8/11/05 letter to contractor on deficiences.(cracking) No remedial action on 10/27/2010 | 2011-10-14 | Expired
Bridge | 894 | 18288 | 246 | 2001 | 2001-0246 | 10 | ATH-US33-40.981 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | Released | 7 | 2006-02-24 | [5 empty] | 2012-01-05 | [16 empty] | No remedial Action required - 1/10/12 |  | Expired
Bridge | 894 | 19719 | 403 | 2001 | 2001-0403 | 10 | MEG-SR124-026.66 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2004-10-14 | 7 | 2005-11-23 | 2006-02-24 |  |  |  | 2010-10-27 | 2011-09-16 | [16 empty] | No remedial action required 10/27/2010 | 2011-10-14 | Expired
Bridge | 894 | 18287 | 425 | 2001 | 2001-0425 | 10 | ATH-US33-30.981 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2005-02-23 | 7 | 2006-02-24 | 2007-02-06 | 2008-02-02 | 2009-02-13 | 2010-02-04 | 2011-01-31 | 2012-01-05 | [17 empty] | 2012-02-23 | Expired
Bridge | 894 | 21053 | 3001 | 2001 | 2001-3001 | 10 | ATH-US33-010.41 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY - , BRIDGE DECK (7 - YEAR WARRANTY) | 2002-10-18 | 7 | 2008-04-18 | [5 empty] | 2009-10-05 |  | Repair using item 255 and/or 256 of the 2008 specs | [14 empty] | End of warranty period; no remedial action required. | 2009-10-18 | Expired
Bridge | 894 | 18986 | 40 | 2002 | 2002-0040 | 10 | GAL-SR279-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-11-05 | 7 | [6 empty] | 2009-09-28 | [16 empty] | Warranty period has reached end, no remedial action required. | 2009-11-05 | Expired
Bridge | 894 | 13481 | 122 | 2002 | 2002-0122 | 10 | NOB-SR821-007.86 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2002-10-31 | 7 | [6 empty] | 2009-10-14 | [16 empty] | End of the warranty period; no remedial action required. | 2009-10-31 | Expired
Bridge | 894 | 19058 | 152 | 2002 | 2002-0152 | 10 | ATH-356-2.94 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-07-24 | 7 | [24 empty] | 2010-07-24 | Expired
Bridge | 894 | 19059 | 196 | 2002 | 2002-0196 | 10 | HOC-SR56-012.55 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2003-09-26 | 7 |  | 2005-09-23 |  |  |  |  | 2010-08-27 | [16 empty] | No remedial action required. Released from warranty as of 9/26/2010 | 2010-09-26 | Expired
Bridge | 894 | 23565 | 173 | 2005 | 2005-0173 | 10 | WAS-US50-4.40 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2008-05-13 | 7 | 2009-05-09 | 2010-05-14 | 2011-05-20 | 2012-05-14 | 2013-05-13 | 2014-05-13 | 2015-04-13 | [17 empty] | 2015-05-13 | Expired
Bridge | 894 | 13590 | 487 | 2000 | 2000-0487 | 11 | JEF-SR152-14.688 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-08-21 | 7 | 2002-08-20 | 2003-08-19 | [5 empty] | map cracking - minor | seal with HMWM per SS 846 | [15 empty] | 2008-08-21 | Expired
Bridge | 894 | 15936 | 511 | 2000 | 2000-0511 | 11 | HAS-US22-017.48 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY - | 2001-12-19 | 7 | 2002-12-18 | 2003-12-22 | [5 empty] | none | [16 empty] | 2008-12-19 | Expired
Bridge | 894 | 9176 | 197 | 2000 | 2000-0197 | 12 | CUY-IR271-009.72 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-11-21 | 7 | 2002-09-01 | 2003-03-01 | [22 empty] | 2008-11-21 | Expired
Bridge | 894 | 18122 | 232 | 2000 | 2000-0232 | 12 | CUY-IR71-013.16 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-01-12 | 7 | 2001-12-05 | 2002-05-01 | 2003-05-01 | [21 empty] | 2008-01-12 | Expired
Bridge | 894 | 18744 | 308 | 2000 | 2000-0308 | 12 | CUY-IR271-004.17 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2001-10-15 | 7 | [24 empty] | 2008-10-15 | Expired
Bridge | 894 | 12342 | 204 | 2001 | 2001-0204 | 12 | CUY-IR271-20.503 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN - | 2003-04-18 | 7 | [23 empty] | Letter sent for sign removal, to contractor and bonding company | 2010-04-18 | Expired
Concrete | 896 | 76691 | 2 | 2013 | 2013-0002 | 1 | ALL-75-5.53,PART1; ALL-117/309-18.65/15.17,PART2 | PORTLAND CEMENT CONCRETE PAVEMENT, 14" THICK | 2015-09-30 | 7 | [24 empty] | 2022-09-30 | Under Warranty
Concrete | 896 | 76691 | 2 | 2013 | 2013-0002 | 1 | ALL-75-5.53,PART1; ALL-117/309-18.65/15.17,PART2 | PORTLAND CEMENT CONCRETE PAVEMENT, 14" THICK | 2015-09-30 | 7 | [24 empty] | 2022-09-30 | Under Warranty
Concrete | 896 | 89029 | 568 | 2013 | 2013-0568 | 1 | ALL-75-0.21 | PORTLAND CEMENT CONCRETE PAVEMENT, 14" | Under Construction | 7
Asphalt | 880 | 22222 | 211 | 2008 | 2008-0211 | 12 | CUY-IR77-001.89 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2010-11-20 | 7 | [23 empty] | Oakes Road to Pleasant Valley Road | 2017-11-20 | Under Warranty
Concrete | 884 | 19181 | 80 | 2007 | 2007-0080 | 12 | GEA-US422-018.31 | 11" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-10-09 | 7 | [24 empty] | 2016-10-09 | Under Warranty
Asphalt | 1059 | 19555 | 27 | 2000 | 2000-0027 | 1 | WYA-US30-015.95 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY - | 2000-08-14 | 3 | 2001-04-30 | Review Waived | Review Waived | [21 empty] | 2003-08-14 | Expired
Asphalt | 1059 | 16074 | 44 | 2000 | 2000-0044 | 1 | Han/Wya USR 68/23/SR15 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2000-08-14 | 3 | 2001-04-25 | 2002-05-17 | [5 empty] | Disintegrated Area | Seal longitudinal center joint for raveling | [15 empty] | 2003-08-14 | Expired
Asphalt | 1059 | 19976 | 228 | 2000 | 2000-0228 | 10 | WAS-SR339-008.58 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY - | 2000-08-25 | 3 | 2001-04-21 | [5 empty] | 2003-04-14 | [17 empty] | 2003-08-25 | Expired
Asphalt | 1059 | 19948 | 321 | 2000 | 2000-0321 | 5 | PER-US13-020.38 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY - | 2000-11-07 | 3 | 2001-04-30 | 2002-04-30 | 2003-04-30 | [21 empty] | 2003-11-07 | Expired
Asphalt | 1059 | 16894 | 328 | 2000 | 2000-0328 | 3 | WAY-SR94-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY - | 2000-11-02 | 3 | 2001-07-13 | 2002-04-04 | 2003-04-10 |  |  |  |  | Disintegrated area | R & R distressed area | [15 empty] | 2003-11-02 | Expired
Other | 1059 | 20990 | 478 | 2000 | 2000-0478 | 6 | FRA-IR270-052.16 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY - | 2001-07-30 | 3 | Review Waived 2005 | 2003-03-27 | 2004-04-24 |  |  |  | 2004-07-30 | [16 empty] | OUT OF WARRANTY | 2004-07-30 | Expired
Asphalt | 1059 | 17068 | 505 | 2000 | 2000-0505 | 7 | MOT-IR70-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H, PG76-22 WITHSUPPLEMENT 1059 WARRANTY - | 2001-10-08 | 3 | 2002-10-09 | 2003-07-10 | 2004-07-15 | [21 empty] | 2004-10-08 | Expired
Other | 1059 | 21605 | 512 | 2000 | 2000-0512 | 6 | PIC-US23-012.92 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY - | 2001-07-25 | 3 | 2002-03-18 | 2003-04-02 | 2004-04-08 |  |  |  | 2004-07-25 | [16 empty] | OUT OF WARRANTY | 2004-07-25 | Expired
Asphalt | 1059 | 11738 | 558 | 2000 | 2000-0558 | 12 | CUY-IR90-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY - | 2002-11-15 | 3 | 2003-12-08 | [23 empty] | 2005-11-15 | Expired
Other | 1059 | 20994 | 6 | 2001 | 2001-0006 | 6 | FAY-IR71-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY - | 2001-08-31 | 3 | 2002-05-08 | 2003-03-21 |  |  |  |  | 2004-08-31 | [16 empty] | OUT OF WARRANTY | 2004-08-31 | Expired
Asphalt | 1059 | 20800 | 108 | 2001 | 2001-0108 | 12 | CUY-IR90-013.41 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1HWITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN - | 2002-07-18 | 3 | 2003-06-15 | [23 empty] | 2005-07-18 | Expired
Asphalt | 1059 | 17099 | 154 | 2001 | 2001-0154 | 7 | AUG-SR29-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1HWITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN - | 2001-12-01 | 3 | 2002-10-10 | 2003-05-21 | 2004-05-12 | [21 empty] | 2004-12-01 | Expired
Other | 1059 | 20985 | 214 | 2001 | 2001-0214 | 6 | UNI-US33-012.59 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2001-11-13 | 3 | 2002-03-21 | 2003-03-05 | 2004-04-13 |  |  |  | 2005-04-13 | POTHOLES/POPOUTS | FILL WITH SS3405 CRACK SEALER | [14 empty] | 3/22/06 no problems found2/23/07-NO DISTRESS TYPES FOUND 03/13/08-no distress types found 03/30/09 everything looks good no distress types found. | 2004-11-13 | Expired
Other | 1059 | 21258 | 225 | 2001 | 2001-0225 | 6 | FRA-SR104-010.61 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY - | 2001-09-20 | 3 | 2002-06-03 | 2003-03-29 | 2004-04-04 |  |  |  | 2004-09-20 | [16 empty] | out of warranty | 2004-09-20 | Expired
Other | 1059 | 21406 | 270 | 2001 | 2001-0270 | 6 | FRA-70-00.02 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY - | 2001-11-07 | 3 | Review Waived 2002 | 2003-03-19 | 2004-04-17 |  |  |  | 2004-11-07 | PAVING |  |  |  | 1205293 | 4902351 | [10 empty] | out of warranty | 2004-11-07 | Expired
Asphalt | 1059 | 16845 | 341 | 2001 | 2001-0341 | 7 | AUG-SR66-011.86 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY - | 2001-10-19 | 3 | 2002-10-10 | 2003-05-14 | 2004-05-13 | [21 empty] | 2004-10-19 | Expired
Asphalt | 1059 | 21811 | 362 | 2001 | 2001-0362 | 1 | WYA-US23-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE A (446)WITH SUPPLEMENT 1059 WARRANTY - | 2001-12-12 | 3 | 2002-05-15 | 2003-04-14 |  |  |  |  | 2004-11-19 | Disintegrated Area | Seal longitudinal center joint for raveling | [15 empty] | 2004-12-12 | Expired
Asphalt | 1059 | 17448 | 468 | 2001 | 2001-0468 | 7 | CLA-IR70-006.34 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN - | 2005-02-08 | 3 | 2006-03-06 | [23 empty] | 2008-02-08 | Expired
Asphalt | 1059 | 18249 | 560 | 2001 | 2001-0560 | 7 | MOT-IR75-29.305 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN - | 2005-07-18 | 3 | [24 empty] | 2008-07-18 | Expired
Asphalt | 1059 | 19799 | 229 | 2002 | 2002-0229 | 7 | MER-US127-014.67 | ASPHALT CONCRETE SURFACE COURSE, 9.5 MM, TYPE B (448) WITHSUPPLEMENT 1059 WARRANTY, AS PER PLAN - | 2002-10-25 | 3 | 2003-05-21 | 2004-05-12 | 2005-05-12 | [21 empty] | 2005-10-25 | Expired
Other | 1059 | 23882 | 488 | 2002 | 2002-0488 | 6 | FRA-IR70-011.21 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITHSUPPLEMENT 1059 WARRANTY - | 2003-08-27 | 3 | 2004-04-24 | 2005-06-18 | 4/29 & 4/30 2006 |  |  |  | 2006-06-07 | [16 empty] | Review by DRT on 6/18/05. Deficencies found (cracking at joints, structure joints. Letter sent to contractor 0n 6/21/05. In process of setting up meeting to discuss repairs. review scheduled for 4/29 and 4/30 2006 Review 2006- a few potholes fall under | 2006-08-27 | Expired
Asphalt | 1059 | 19673 | 534 | 2002 | 2002-0534 | 12 | CUY-IR90-029.92 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE A (446)WITH SUPPLEMENT 1059 WARRANTY - | 2005-11-01 | 3 | [24 empty] | 2008-11-01 | Expired
Asphalt | 1059 | 24719 | 110 | 2003 | 2003-0110 | 5 | PER-SR13-0.00 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 15659 | 117 | 2003 | 2003-0117 | 1 | PAU-US30-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITHSUPPLEMENT 1059 WARRANTY - | 2003-08-21 | 3 | 2004-04-18 | 2006-04-04 | [22 empty] | 2006-08-21 | Expired
Asphalt | 1059 | 22704 | 122 | 2003 | 2003-0122 | 2 | WOO-IR75-032.68 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITHSUPPLEMENT 1059 WARRANTY - | 2004-01-12 | 3 | 2004-04-22 | 2005-04-11 | 2006-03-04 |  |  |  |  | Crackings (Minor) | Crack Sealing | [15 empty] | 2007-01-12 | Expired
Asphalt | 1059 | 24711 | 268 | 2003 | 2003-0268 | 9 | ROS-US35-010.20 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY - | 2003-10-17 | 3 | Review Waived | Review Waived | 2006-04-20 |  |  |  | 2006-10-30 | [17 empty] | 2006-10-17 | Expired
Asphalt | 1059 | 75427 | 338 | 2003 | 2003-0338 | 7 | SHE-IR75-11-49/16.05 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B WITH SUPPLEMENT 1059 WARRANTY | 2003-09-25 | 3 | 2004-06-15 | 2005-06-22 | [22 empty] | 2006-09-25 | Expired
Asphalt | 1059 | 75429 | 339 | 2003 | 2003-0339 | 7 | SHE-IR75-16.05/20.55 | ULTRATHIN BONDED ASPHALT CONCRETE WITH SUPPLEMENT 1059 WARRANTY | 2003-09-25 | 3 | 2004-06-15 | 2005-06-22 | [22 empty] | 2006-09-25 | Expired
Asphalt | 1059 | 25174 | 407 | 2003 | 2003-0407 | 9 | SCI-US52-31.98 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY - | 2003-10-24 | 3 | 2004-04-28 | 2005-04-25 | 2006-04-13 |  |  |  | 2006-10-11 | Some rutting | [15 empty] | Rutting noted in 4/13 review. Contractor adviced. DRT to review in fall prior to warranty end date. | 2006-10-24 | Expired
Asphalt | 1059 | 21452 | 456 | 2003 | 2003-0456 | 11 | TUS-IR77-20.73 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2004-09-13 | 3 | 2005-04-25 | [23 empty] | 2007-09-13 | Expired
Asphalt | 1059 | 23728 | 476 | 2003 | 2003-0476 | 2 | SAN-USR6/20-14.61/14.59/18.68 | ASPHALT CONCRETE SURFACE COURSE 12.5MM TYPE A 446 WITH SUPPLEMENT 1059 WARRANTY | 2005-09-12 | 3 | 2006-03-04 | 2007-04-18 | [21 empty] | Some potholing / cracking | 2008-09-12 | Expired
Asphalt | 1059 | 23728 | 476 | 2003 | 2003-0476 | 2 | SAN-USR6/20-14.61/14.59/18.68 | STONE MASTIC ASPHALT CONCRETE SURFACE COURSE(PG76-22) WITH SUPPLEMENT 1059 WARRANTY | 2005-09-12 | 3 | 2006-03-04 | 2007-04-18 |  |  |  |  | 2008-09-12 | [16 empty] | Warranty released. | 2008-09-12 | Expired
Asphalt | 1059 | 25656 | 492 | 2003 | 2003-0492 | 5 | GUE-IR70-9.13 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2004-10-15 | 3 | [24 empty] | 2007-10-15 | Expired
Asphalt | 1059 | 21722 | 494 | 2003 | 2003-0494 | 10 | HOC-US33-0.00 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2004-06-29 | 3 | [6 empty] | 2006-12-08 |  | None | [14 empty] | End of warranty period; no remedial action required. | 2007-06-29 | Expired
Asphalt | 1059 | 25431 | 496 | 2003 | 2003-0496 | 2 | SAN-US20-0.00 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2005-09-08 | 3 | 2006-03-04 | 2007-04-02 |  |  |  |  | 2008-09-10 | [16 empty] | Warranty released. | 2008-09-08 | Expired
Asphalt | 1059 | 12725 | 536 | 2003 | 2003-0536 | 7 | MOT-SR4-019.14 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446), AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 21633 | 543 | 2003 | 2003-0543 | 5 | LIC-IR70-15.96 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2004-09-08 | 3 | [24 empty] | 2007-09-08 | Expired
Asphalt | 1059 | 16073 | 569 | 2003 | 2003-0569 | 1 | WYA US-23 010.24 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH WARRANTY | 2004-12-20 | 3 | 2005-04-19 | 2006-04-12 |  |  |  |  | 2007-04-12 | [16 empty] | Warranty released. | 2007-12-20 | Expired
Asphalt | 1059 | 75437 | 580 | 2003 | 2003-0580 | 9 | PIK-US23-5.23 | ASPHALT CONCRETE COURSE WITH SUPPLEMENT 1059 WARRANTY - | 2004-08-18 | 3 | Review Waived | Review Waived | 2007-04-19 |  |  |  | 2007-08-31 |  | None | [14 empty] | DRT results okay. Will schedule 1 more review before warranty expires. | 2007-08-18 | Expired
Asphalt | 1059 | 21481 | 608 | 2003 | 2003-0608 | 9 | SCI US-52-15.50 | ASPHALT CONCRETE COURSE WITH SUPPLEMENT 1059 WARRANTY - | 2004-11-23 | 3 | Review Waived | Review Waived | 2007-04-16 |  |  |  | 2007-11-28 |  | None | [14 empty] | DRT recommends this project be released from the warranty. | 2007-11-23 | Expired
Asphalt | 1059 | 21425 | 10 | 2004 | 2004-0010 | 9 | LAW-US52-11.85 | ASPHALT CONCRETE COURSE WITH SUPPLEMENT 1059 WARRANTY - | 2004-10-20 | 3 | Review Waived | Review Waived | 2007-04-05 |  |  |  | 2007-10-17 |  | None | [14 empty] | There is rutting which appears to be at threshold levels. DRT recommends this project be released from the warranty. | 2007-10-20 | Expired
Asphalt | 1059 | 17094 | 12 | 2004 | 2004-0012 | 7 | MER-SR29-13.52/19.36 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2004-11-16 | 3 | 2005-06-22 | [23 empty] | 2007-11-16 | Expired
Asphalt | 1059 | 25883 | 167 | 2004 | 2004-0167 | 6 | PPM-D06-FY04 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY Morrow 97 0.00 to 3.66 | 2004-06-07 | 3 | 2005-08-04 | 2006-02-16 | 2007-04-13 |  |  |  | Out of warranty 6/7/2007 | [16 empty] | OUT OF WARRANTY | 2007-06-07 | Expired
Asphalt | 1059 | 76991 | 356 | 2004 | 2004-0356 | 6 | PPM-D06-(FAY/UNI 35 | ASHPHALT CONCRET (3 YEAR) Uni-33-.14 to 8.74 | 2004-09-21 | 3 | 2005-08-06 | 2006-03-25 | 2007-04-12 |  |  |  | 2007-08-01 |  |  |  | repairs at 4.25 and 8.2 wb replacing asphalt and sealing of dust holes completed 6/15/06 by shelly company | [12 empty] | OUT OF WARRANTY | 2007-09-21 | Expired
Asphalt | 1059 | 76991 | 356 | 2004 | 2004-0356 | 6 | PPM-D06- | ASPHALT CONRETE Fay -us35-12.44-17.71 | 2004-09-21 | 3 | 2005-08-06 | Review waived 2007 | 2007-04-12 |  |  |  | 2007-08-01 | [16 empty] | Review by DRT on 6/18/05. Deficencies found (cracking at joints, structure joints. Letter sent to contractor 0n 6/21/05. In process of setting up meeting to discuss repairs. review scheduled for 4/29 and 4/30 2006 Review 2006- a few potholes fall under warranty spec. There is base and structure failures going on that are not covered under this warranty OUT OF WARRANTY | 2007-09-21 | Expired
Asphalt | 1059 | 19893 | 434 | 2004 | 2004-0434 | 9 | ROS-104-8.64 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY - | 2004-12-15 | 3 | Review Waived | Review Waived | 2007-04-23 |  |  |  | 2007-12-14 | Reflective cracking | None | [14 empty] | DRT recommends this project be released from the warranty. | 2007-12-15 | Expired
Asphalt | 1059 | 22511 | 456 | 2004 | 2004-0456 | 10 | NOB-IR77-1.56 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2005-04-25 | 3 | [6 empty] | 2008-05-23 | [16 empty] | Warranty released. | 2008-04-25 | Expired
Asphalt | 1059 | 21712 | 479 | 2004 | 2004-0479 | 10 | GAL-US35-01.03 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2005-12-08 | 3 | [6 empty] | 2008-12-08 | [16 empty] | End of warranty period; no remedial action required. | 2008-12-08 | Expired
Asphalt | 1059 | 23405 | 511 | 2004 | 2004-0511 | 9 | ROS-23-1.56 & ROS-35-22.65 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY - | 2006-01-04 | 3 | Review Waived | 2007-04-27 |  |  |  |  | 2009-02-05 | minor rutting/cracking | None | [14 empty] | Reflective cracking is noticed. The DRT's opinion is that the reflective cracking is a result of the underlying conditions and not the asphalt concrete overlay. It is the recommendation of the DRT that this pavement be released from the warranty. | 2009-01-04 | Expired
Asphalt | 1059 | 23805 | 517 | 2004 | 2004-0517 | 3 | ERI-SR2-030.46 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 21730 | 520 | 2004 | 2004-0520 | 9 | JAC-32-17.41 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2005-11-08 | 3 | 2006-04-24 | 2007-03-23 | [6 empty] | None | [14 empty] | DRT results okay. | 2008-11-08 | Expired
Asphalt | 1059 | 77459 | 522 | 2004 | 2004-0522 | 9 | ROS-23-9.36 | ASHPHALT CONCRETE SURFACE COURSE, 12.5 MM,TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2005-06-22 | 3 | Review Waived | 2007-04-23 |  |  |  |  | 2008-06-20 |  | None | [14 empty] | Warranty released. | 2008-06-22 | Expired
Asphalt | 1059 | 24441 | 562 | 2004 | 2004-0562 | 7 | MOT-IR75-006.16 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 21801 | 581 | 2004 | 2004-0581 | 8 | HAM-IR74-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 76564 | 3002 | 2004 | 2004-3002 | 6 | FAY-SR41-022.18 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 17097 | 8000 | 2004 | 2004-8000 | 7 | CLA-SR4-005.56 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2005-06-20 | 3 | [24 empty] | 2008-06-20 | Expired
Asphalt | 1059 | 21700 | 6 | 2005 | 2005-0006 | 12 | CUY-IR90-004.57 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 23005 | 150 | 2005 | 2005-0150 | 9 | ROS-23-16.34 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY - | 2006-01-04 | 3 | Review Waived | 2007-04-27 |  |  |  |  | 2009-02-05 | Reflective cracking | None | [14 empty] | Reflective cracking is noticed. The DRT's opinion is that the reflective cracking is a result of the underlying conditions and not the asphalt concrete overlay. It is the recommendation of the DRT that this pavement be released from the warranty. | 2009-01-04 | Expired
Asphalt | 1059 | 13389 | 280 | 2005 | 2005-0280 | 9 | JAC-35-13.23 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY - | 2005-11-08 | 3 | 2006-04-24 | 2007-02-28 | 2008-05-06 |  |  |  | 2008-12-08 | Deterioration of joints and reflective cracking. | [15 empty] | DRT opinion is that reflective cracking is a result of the underlying conditions and not the asphalt concrete overlay. Recommendation of the DRT that this pavement be released from the warranty. | 2008-11-08 | Expired
Asphalt | 1059 | 25887 | 381 | 2005 | 2005-0381 | 6 | D06-PPM-FY06 | FINE GRADE POLYMER ASPHALT TYPE B FRANKLIN i-70 7.35 TO 11.21 EB AND WB | 2006-08-11 | 3 | 2007-02-27 | 2008-03-14 | 03/30009 | [20 empty] | START OF WARRANTY LETTER SENT 8/22/06 letter of review sent 4/13/07, no problems with pavement but there is an existing backwall problem which is affecting pavement joint not contractors fault 03/14/08--no warranty issues at this time.03/2009 pavement looks good approach end of structure over rr at 96.65mmneeds atttention not a warranty issue. OUT OF WARRANTY LETTER SENT TO KOKOSING ON 9/3/09 SIGN REMOVAL LETTER SENT TO TODD SEITER IN TRAFFIC. | 2009-08-11 | Expired
Asphalt | 1059 | 25887 | 381 | 2005 | 2005-0381 | 6 | D06-PPM-FY06 | FINE GRADE POLYMER ASPHALT TYPE B MARION US 23 2.42-7.14 NORTHBOUND ONLY | 2006-06-24 | 3 | 2007-04-04 | 2008-03-17 | 2009-02-11 | [20 empty] | START OF WARRANTY LETTER SENT 8/22/06review of project 4/4/07 no distress types found , cracking on edge of shoulders observed pictures taken. 03/17/08--no distress types found cracking but not a warranty issue. Bad spot from car fire. OUT OF WARRANTY LETTER SENT 6/25/09 TO KOKOSING. remove warranty signs letter to todd seither in traffic. | 2009-06-24 | Expired
Asphalt | 1059 | 25887 | 381 | 2005 | 2005-0381 | 6 | D06-PPM-FY06 | FINE GRADE POLYMER ASPHALT TYPE B FAY-SR753-SLM0.24-10.45 | 2005-11-07 | 3 | 2006-04-08 | 4/7/2007 see comments | 2008-04-08 |  |  |  |  | disentegration previous patching needs repaird | [15 empty] | 4/13/06 letter sent problems with raveling pulling apart to contractor PAVEMENT NOT COMING UP WILL LOOK AT IN THE SPRING OF 07 3/24/07 review set for 9:00 a.m. reviewed on 4/7/07 with drt team and contractor and sub contractor no changes in constions found from last year- review letter sent 4/13/07 to prime contractor requesting repair and time frame of repair. Reminder letter sent to Koko on 6/11/07. 8/16/07 talked with Paul Cain of JUrgensen will be submitting remedial action plan through prime contractor Kokosing 8/27/07 letter from Kokosing, wants to meet and mark out areas. C. kiner will handle this action for ODOT--setting up meeting with Ken kerns, J.R. Jurgensen to repair potholes sometime in November 2007. Repairs made to potholes on 11/7 and 11/8 of 2007 by Jurgensen Co. 48/08--review previous patching to be repaired and disintegrated areas to be removed and replace by contractor. Contractor notified by letter of review result. J. R. Jurgensen in on 5/28/0 and made repairs letter on file. OUT OF WARRANTY | 2008-11-07 | Expired
Asphalt | 1059 | 25887 | 381 | 2005 | 2005-0381 | 6 | D06-PPM-FY06 | FINE GRADE POLYMER ASPHALT TYPE B PIC-SR104--SLM - 15.28-21.47 | 2005-09-22 | 3 | 2006-04-21 | 2007-03-13 | 2008-04-03 |  |  |  |  | disentegration | [15 empty] | OUT OF WARRANTY SEPTEMBER 2008 PAVEMENT IN GOOD SHAPE NO DEFIEIENCES FOUND---------3/26/06 DEFECIENCIES FOUND. Some marks in pavement but they look to be from parm equipment or outriggers on utility truck. 2/8/07--review scheduled for 3/13/07/ Mudflaps found in pavement area 15.5mm 3/13/07 reivw of pavement between 15.5 and 15.9 piesces of mud flaps or vonveyor bels runner found to be coming through pavement at about 17 differnet areas., in the northbund lane. Contracot at review and will be fixing at a later date. All other areas looked at are okay. Some minute cracking. Review letter sent on 3/14/07. Reminder letter sent 6/11/07 to Kokosing. Repairs made on 8/29/07 nb lane 15.0 to 15.5 mm removed and replaced. 4-3-08 Loss of material, hole sin pavement. some may be rubber conveyor belt that went to shreds inside of truck. Contractor notified by letter of review resuts 4/8/08. Received letter from contractor 6/24/08 will fix holes if state wants, agrees these are under warranty but disagrees that the southbound ar4eas at the 19.6-20.0 appproximately that are pushing, shoving, sliding, are a warranty issue. They contend it tis water coming up throught from the subbase. 7.8.08 DRT tem, Proj engr and Julia Miller from C.O. revisited the site. General concensus is it is a rutting issue not a warranty item. OUT OF WARRANTY | 2008-09-22 | Expired
Asphalt | 1059 | 21802 | 415 | 2005 | 2005-0415 | 9 | PIK-23-3.50 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2006-11-22 | 3 | Review Waived | 2009-04-13 | [5 empty] | Reflective cracking | None | [14 empty] | Reflective cracking is present throughout the project including the berms, but reflective cracking is not a warrant issue. Other than the reflective cracking, the pavement is in good condition. | 2009-11-22 | Expired
Asphalt | 1059 | 75476 | 607 | 2005 | 2005-0607 | 12 | CUY-IR480-021.88 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 19883 | 614 | 2005 | 2005-0614 | 9 | SCI-23-2.28 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY - | 2006-12-12 | 3 | 2009-05-08 | [6 empty] | Cracking | None | [14 empty] | Reflective cracking is present throughout the project including the berms, but reflective cracking is not a warranty issue. It appears this is a subbase/subgrade issue and not a problem with the asphalt concrete. | 2009-12-12 | Expired
Asphalt | 1059 | 22218 | 122 | 2006 | 2006-0122 | 12 | CUY-IR480-019.23 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 25459 | 134 | 2006 | 2006-0134 | 9 | ROS-35-4.38 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2006-12-18 | 3 | 2007-04-27 | 2009-05-19 | [5 empty] | Cracking | None | [14 empty] | Cracks are the result of thermo cracks from the underlying pavement. District is considering a rout and seal project to address these cracks. | 2009-12-18 | Expired
Asphalt | 1059 | 21927 | 249 | 2006 | 2006-0249 | 9 | ROS-35-14.41 | ASPHALT CONCRETE SURFACE COURSE, WITH SUPPLEMENT 1059 WARRANTY | 2007-07-03 | 3 | 2009-05-19 | [5 empty] | 2010-12-22 | Reflective Cracking | None | [14 empty] | Reflective cracking is present over original joints and pavement reapirs. Reflective cracking is not a warranty issue. (12/22/2010): Final warranty review performed by Victor Picciano and Chad Mitten. Drove entire project length in both directions. Reflective cracking is present over original joints and pavement repairs. DRT recommends project be released from warranty. | 2010-07-03 | Expired
Asphalt | 1059 | 80904 | 398 | 2006 | 2006-0398 | 9 | ROS-35-17.83 | ASPHALT CONCRETE SURFACE COURSE WITH SUPPLEMENT 1059 WARRANTY | 2007-07-03 | 3 | 2009-05-19 | [6 empty] | Reflective Cracking | None | [14 empty] | Reflective cracking is present over original joints and pavement reapirs. Reflective cracking is not a warranty issue. | 2010-07-03 | Expired
Asphalt | 1059 | 19047 | 433 | 2006 | 2006-0433 | 1 | DEF-US24-012.03 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2008-12-06 | 3 |  |  |  | 2012-04-17 | [20 empty] | 2011-12-06 | Expired
Asphalt | 1059 | 25530 | 435 | 2006 | 2006-0435 | 9 | JAC-35-1.69 | ASPHALT CONCRETE SURFACE COURSE WITH SUPPLEMENT 1059 WARRANTY | 2007-12-14 | 3 | 2008-05-06 | [5 empty] | 2010-12-22 | Rutting | None | [14 empty] | Slight amount of rutting observed in the driving lanes at all locations; only as thinck as a credit card. No warranty issues. (12/22/2010): Final warranty review performed by Victor Picciano and Chad Mitten. Drove entire length of project in both directions. Reflective cracking present in eastbound lanes. DRT recommends project be released from warranty. | 2010-12-14 | Expired
Asphalt | 1059 | 25520 | 9 | 2007 | 2007-0009 | 9 | LAW-7-0.00/LAW-527-0.19/LAW-52-22.16 | ASPHALT CONCRETE COURSE WITH SUPPLEMENT 1059 WARRANTY - | 2007-11-02 | 3 | 2009-04-22 | [5 empty] | 2010-11-30 | Cracking | None | [14 empty] | A hole has been patched in the centerline joint at approximately 2.00 mile marker in the southbound lanes. No other potholes were observed. Also there is a crack in the southbound driving lane at approximately .7 mile marker. This appears to be a subbase issue. (12/2/2010) Inspectors drove the entrie length of project in both directions. Condition of the pavement is good. The hole which had been patched in the centerline joint at approx 2.00 mile marker in the southbound lanes is still visible and the repair is performing acceptably. Reflective cracks are visible throughout the project. There are no warranty issues at this time. The DRT recommends this project be release from the warranty. | 2010-11-02 | Expired
Asphalt | 1059 | 77834 | 39 | 2007 | 2007-0039 | 9 | ROS-35-18.11/ROS-23-17.03 | ASPHALT CONCRETE COURSE WITHSUPPLEMENT 1059 WARRANTY - | 2007-11-19 | 3 | 2009-05-19 | [5 empty] | 2010-12-22 | Reflective Cracking | None | [14 empty] | Reflective cracking is present over original joints and pavement reapirs. Reflective cracking is not a warranty issue. (12/22/2010): Warranty Review was performed by Chad Mitten and Victor Picciano. Drove entire length of project, both directions/sections. Reflective cracking present over original joints and pavement repairs. DRT recommends project be released from warranty. | 2010-11-19 | Expired
Asphalt | 1059 | 25548 | 56 | 2007 | 2007-0056 | 11 | COL-US30-031.30 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 81415 | 126 | 2007 | 2007-0126 | 9 | BRO-USR-32-5.80/0.00 | FINE GRADED POLYMER ASPHALT CONCRETE SURFACE COURSE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, APP | 2007-07-17 | 3 | [6 empty] | 2010-07-13 | Reflective Cracking (non-warranty issue) | [15 empty] | Reflective cracking was observed but is not a warranty issue. Passing lane is noticeably worse than the driving lane. Warranty is released as of final review July 13th, 2010. | 2010-07-17 | Expired
Asphalt | 1059 | 79313 | 142 | 2007 | 2007-0142 | 6 | D06-PPM-FY07B Marion(WRNTY)/PIC(NO WRNTY) | Ultrathin Bonded Asphalt, Mar-SR98-0.00-17.17 | 2007-09-25 | 3 | 2008-03-17 | 2009-04-09 | [21 empty] | 03/17/08--no distress types found.---WARRANTY REVIEW SET FOR APRIL 9 2009 AT 10:00 ON SR 98040909 met with contracotr and review team. 5 areas beginning to ravel contractor will fix next spring as not a safety issue , county will watch if becomes one contractor will come in then. March 2010 prelim review areas of raveling have stayed the same contacted Kokosing 4/5/10for time frame on repairs email received 4/7/10 Russell Standard the sub contractor will be in 2- 3 weeks for a re review of areas goes out of warranty 2010. | 2010-09-25 | Expired
Asphalt | 1059 | 25462 | 176 | 2007 | 2007-0176 | 2 | OTT-2-23.77 | ASPHALT CONCRETE SURFACE COURSE 12.5MM TYPE A 446 WITH SUPPLEMENT 1059 WARRANTY | 2008-05-09 | 5 | [24 empty] | 2013-05-09 | Expired
Asphalt | 1059 | 80022 | 510 | 2007 | 2007-0510 | 9 | JAC-32-0.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2008-11-06 | 3 |  | 2011-05-06 |  |  |  |  | 2011-10-14 | [16 empty] | (5/6/2011): No warranty issues. | 2011-11-06 | Expired
Asphalt | 1059 | 22200 | 7 | 2008 | 2008-0007 | 12 | CUY-IR271-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 78981 | 22 | 2008 | 2008-0022 | 5 | LIC-IR70-023.84 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 23827 | 57 | 2008 | 2008-0057 | 7 | AUG-US33-013.10 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 25864 | 58 | 2008 | 2008-0058 | 9 | BRO-SR32-005.80 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 75276 | 162 | 2008 | 2008-0162 | 6 | D06-PPM-FY08A | Ultrathin Bonded Asphalt, Mad.-US71-4.56 to 11.68 | 2008-09-25 | 3 | 2009-04-06 | 2010-03-15 | [21 empty] | 022709--LOTS OF CRACKING(NOT COVERED) SOME POTHOLES, DIRT PUMPING UP THRU-SHOULD HAVE HAD THIS TREATMENT, IS IT CONTRACTOR RESPONSIBILITY LOOKING INTO 3/13/09. APRIL 6, 2009 WARRANTY REVIEW SET. Review found popouts and holes contractor will fix once plant is open in a few weeks there is an underlying problem with joint failures which is ODOT's problem to fix. 09/1/09-- Shelly and Sands crew in cleaning out popout areas and filling with an a/c polymer blend of 340 S by R. W. Meadows. Traffic control set up for travel lane closure using arrowboard, signage, cones. 03/15/2010--prelim review by county manager showed cracking and potholes resulting from an existing subbase problem, ODOT responsiblity does not fall under warranty guidelines. | 2011-09-25 | Expired
Asphalt | 1059 | 75276 | 162 | 2008 | 2008-0162 | 6 | D06-PPM-FY08A | Ultrathin Bonded Asphalt, Mar-SR 4 12.98 to 20.51 | 2008-09-25 | 3 | 2009-02-11 | 2010-03-01 | [21 empty] | 02-11-09---entire project reviewed. Lots of reflective cracking showing at previous pavement repairs and concrete joints. cracking alone is not covered under 1059 warranty spec. Also longitudinal at centerline joint(apprears to be widening but the existing was wide. Informed county manager and production of problems should be crack sealed. March 2010--county manager said he didn[t see any changes to pavement from last year still has reflective cracking put that is not a warranty issue. Goes out out warranty in 2011 | 2011-09-25 | Expired
Asphalt | 1059 | 75276 | 162 | 2008 | 2008-0162 | 6 | D06-PPM-FY08A | Ultrathin Bonded Asphalt, PIC-US71-0.00 to 3.16 | 2008-09-25 | 3 | 2009-04-06 | 2010-03-15 | [21 empty] | 022209--LOTS OF CRACKING(NOT COVERED)SOME POTHOLES FORMING WARRANTY REVIEW SET FOR APRIL 6, 2009/ review found popouts and holes in pavement contractor to fix once their asphalt plant opens--have subbase and joint problems going on below surface this is an ODOT problem to fix 03/15/2010--prelim review by county manager showed cracking and potholes resulting from an existing subbase problem, ODOT responsiblity does not fall under warranty guidelines. | 2011-09-25 | Expired
Asphalt | 1059 | 22985 | 247 | 2008 | 2008-0247 | 9 | LAW-US52-5.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2009-11-24 | 3 |  | 2011-04-07 |  |  |  |  | 2012-11-01 | Ravelling | None at time of 1st inspection | [14 empty] | INSPECTION (4/7/2011): Repairs were made by core drilling and replacement with asphalt concrete. Ravelling is occuring. DRT recommends the contractor inspects for possible additional repairs. Will decide next spring if remedial action is necessary. | 2012-11-24 | Expired
Asphalt | 1059 | 23824 | 305 | 2008 | 2008-0305 | 7 | MOT-SR4-021.02 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 25609 | 336 | 2008 | 2008-0336 | 9 | JAC-US35-008.35 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2008-11-06 | 3 | [24 empty] | 2011-11-06 | Expired
Asphalt | 1059 | 25909 | 336 | 2008 | 2008-0336 | 9 | JAC-35-8.35 | ASPHALT CONCRETE WITH SUPPLEMENT 1059 WARRANTY | 2008-11-06 | 3 | 2009-04-09 | 2011-05-06 |  |  |  |  | 2011-10-14 | Pothole | Addressed | [14 empty] | There is a pothole in the eastbound lanes which is being addressed by the contractor. (5/6/2011): No issues | 2011-11-06 | Expired
Asphalt | 1059 | 25461 | 421 | 2008 | 2008-0421 | 2 | WOO-75-0.71 | ASPHALT CONCRETE SURFACE COURSE 12.5MM TYPE A 446 WITH SUPPLEMENT 1059 WARRANTY | 2008-10-02 | 5 | 2009-04-15 | 2010-03-29 | 2011-04-27 | [21 empty] | 2013-10-02 | Expired
Asphalt | 1059 | 83671 | 445 | 2008 | 2008-0445 | 5 | GUE-IR70-010.54 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired | 3 | [25 empty] | Expired
Asphalt | 1059 | 24507 | 581 | 2008 | 2008-0581 | 4 | SUM-SR8-13.30 | Ashpahlt Concrete Surface Course, 12.5mm Type B | 2011-09-15 | 3 | 2012-04-26 | 2013-04-18 | 2014-07-16 |  |  |  |  | NB Mile15.10 due to vehicle fire - exempt. 4/18/2013 - Cracking 7/16/2014 - Cracking |  | Sum 8 1463R Warr Date: 10/29/10 | [14 empty] | 2014-09-15 | Expired
Asphalt | 1059 | 77350 | 8 | 2009 | 2009-0008 | 11 | BEL-SR7-008.70 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Released | 3 | [25 empty] | Expired
Microsurf | 881 | 88978 | 559 | 2015 | 2015-0559 | 9 | BRO-125-0.00 Village of Hammersville | MICROSURFACING SINGLE COURSE WITH 2 YEAR WARRANTY | 2016-08-05 | 2 | [24 empty] | 2018-08-05
Microsurf | 881 | 88978 | 559 | 2015 | 2015-0559 | 9 | BRO-125-0.00 (0.00-2.542) | MICROSURFACING SINGLE COURSE WITH 2 YEAR WARRANTY | 2016-08-05 | 2 | [24 empty] | 2018-08-05
Microsurf | 881 | 88978 | 559 | 2015 | 2015-0559 | 9 | BRO-125-0.00 (2.542-3.8740) | MICROSURFACING SINGLE COURSE WITH 2 YEAR WARRANTY | 2016-08-05 | 2 | [24 empty] | 2018-08-05
Microsurf | 881 | 88978 | 559 | 2015 | 2015-0559 | 9 | BRO-125-0.00 (3.8740-6.4200) | MICROSURFACING SINGLE COURSE WITH 2 YEAR WARRANTY | 2016-08-05 | 2 | [24 empty] | 2018-08-05
Microsurf | 881 | 87279 | 603 | 2015 | 2015-0603 | 9 | BRO-SR32-15.29 (15.29-17.55) | MICROSURFACING SINGLE COURSE WITH 2 YEAR WARRANTY | 2016-08-02 | 2 | [24 empty] | 2018-08-02
Microsurf | 881 | 87279 | 603 | 2015 | 2015-0603 | 9 | BRO-SR32-15.29 (17.55-19.83) | MICROSURFACING SINGLE COURSE WITH 2 YEAR WARRANTY | 2016-08-02 | 2 | [24 empty] | 2018-08-02
Formulas:
End of warranty date = IF(OR([Warranty Start (C-85)]="",ISERROR(DATE((YEAR([Warranty Start (C-85)])+([Warranty Length])),MONTH([Warranty Start (C-85)]), DAY([Warranty Start (C-85)])))),"",DATE((YEAR([Warranty Start (C-85)])+([Warranty Length])),MONTH([Warranty Start (C-85)]), DAY([Warranty Start (C-85)])))

## Summary
Warranty Summary Pivot Table
Count of PID | Project Year
Project Type | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2010 | 2009 | Grand Total
Asphalt | 3 | 1 | 3 | 33 | 25 | 16 | 27 | 19 | 11 | 15 | 6 | 9 | 2 | 3 | 173
Bridge |  |  | 1 | 34 | 47 | 33 | 30 | 20 | 19 | 5 | 4 | 3 | 2 |  | 198
Chip Seal |  |  | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 6 |  |  |  | 20
Concrete |  |  | 1 | 4 | 8 | 5 | 4 |  | 6 | 2 | 5 |  |  | 1 | 36
Crack Seal |  |  |  | 4 | 1 | [9 empty] | 5
Microsurf | 1 |  | 3 | 1 |  | 1 | 1 | 13 | 5 | 1 | 1 |  |  |  | 27
Painting |  |  | 3 | 26 | 15 |  |  |  |  | 6 |  | 12 |  |  | 62
Traffic |  |  |  | 33 | [10 empty] | 33
Other | 1 |  | 1 | 12 | 4 | 1 | [5 empty] | 1 |  |  | 20
Overlay |  |  |  |  | 2 |  |  |  | 1 | 1 |  |  |  |  | 4
Pavement Markings |  |  |  | 1 | [10 empty] | 1
Grand Total | 5 | 1 | 13 | 151 | 103 | 57 | 65 | 55 | 43 | 31 | 22 | 25 | 4 | 4 | 579

## CMS Query Results
896 | 80446 | 201 | 2009 | 2 | HEN/LUC-24-15.85/0.00 PART 1; HEN-24-10.42 (LUC) PART 2 | PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK | 2012-09-28 | 2019-09-28
880 | 25199 | 460 | 2009 | 4 | ATB-90-14.25 PART 1; ATB-84-20.50 PART 2 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2012-06-28 | 2019-06-28
882 | 81735 | 622 | 2011 | 9 | D09-CHIP-FY2012 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2012-09-11 | 2014-09-11
892 | 23995 | 1040 | 2010 | 2 | LUC-C.R.505-0.28 (WHEELING STREET) | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH | 2012-07-13 | 2014-07-13
880 | 25869 | 1078 | 2010 | 4 | ATB-90-22.06 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2013-08-29 | 2020-08-29
896 | 80444 | 8015 | 2009 | 2 | LUC-24-6.19 | PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK | 2012-09-28 | 2019-09-28
690 | 15926 | 1997-0120 | 1997 | 10 | MOE-SR7-34.129 | SPECIAL - ASPHALT CONCRETE MISC.: | 1998-04-29 | 2003-04-29
690 | 15866 | 1997-0219 | 1997 | 1 | VAN-US30-25.971 | SPECIAL - ASPHALT CONCRETE MISC.: | 1997-11-18 | 2002-11-18
807 | 16610 | 1997-0339 | 1997 | 8 | GRE-US42-003.59 | MICRO-SURFACING | 1999-09-10 | 2002-09-10
807 | 16610 | 1997-0339 | 1997 | 8 | GRE-US42-003.59 | SPECIAL - MICROSURFACING WITH WARRANTY, RUT FILL COURSE | 1999-09-10 | 2002-09-10
690 | 13000 | 1997-0621 | 1997 | 12 | CUY-IR480-010.38 | SPECIAL - ASPHALT CONCRETE, MISC.: | 1998-12-09 | 2003-12-09
632 | 9941 | 1997-3000 | 1997 | 6 | FRA-IR71-015.26 | SIGNALIZATION, MISC.: | Non performed
690 | 15283 | 1998-0015 | 1998 | 1 | VAN-US30-06.618 | SPECIAL - ASPHALT CONCRETE, MISC.: | 1998-12-10 | 2003-12-10
690 | 15283 | 1998-0015 | 1998 | 1 | VAN-US30-06.618 | SPECIAL - MISC.: | 1998-12-10 | 2003-12-10
990 | 18304 | 1998-0434 | 1998 | 3 | MED-SR301-04.184 | AGREED LUMP SUM | #N/A | #N/A
881 | 20439 | 1999-0582 | 1999 | 12 | CUY-IR271-006.41 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 1999-10-27 | 2002-10-27
885 | 20211 | 1999-0655 | 1999 | 2 | SAN-US6-014.76 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-11-14 | 2005-11-14
885 | 20211 | 1999-0655 | 1999 | 2 | SAN-US6-014.76 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-11-14 | 2005-11-14
885 | 20211 | 1999-0655 | 1999 | 2 | SAN-US6-014.76 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-11-14 | 2005-11-14
885 | 20211 | 1999-0655 | 1999 | 2 | SAN-US6-014.76 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-11-14 | 2005-11-14
885 | 20225 | 1999-0656 | 1999 | 2 | SAN-US20-021.31 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-11-14 | 2005-11-14
885 | 20225 | 1999-0656 | 1999 | 2 | SAN-US20-021.31 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-11-14 | 2005-11-14
885 | 20225 | 1999-0656 | 1999 | 2 | SAN-US20-021.31 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-11-14 | 2005-11-14
885 | 20225 | 1999-0656 | 1999 | 2 | SAN-US20-021.31 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-11-14 | 2005-11-14
880 | 7278 | 1999-0722 | 1999 | 6 | FRA-IR71-025.60 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2000-11-17 | 2005-11-17
887 | 7278 | 1999-0722 | 1999 | 6 | FRA-IR71-025.60 | EDGE LINE (5 YEAR WARRANTY) | 2000-11-17 | 2005-11-17
887 | 7278 | 1999-0722 | 1999 | 6 | FRA-IR71-025.60 | LANE LINE (5 YEAR WARRANTY) | 2000-11-17 | 2005-11-17
887 | 7278 | 1999-0722 | 1999 | 6 | FRA-IR71-025.60 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2000-11-17 | 2005-11-17
885 | 20667 | 1999-0763 | 1999 | 2 | LUC-IR75-001.99 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-01-02 | 2006-01-02
885 | 20667 | 1999-0763 | 1999 | 2 | LUC-IR75-001.99 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-01-02 | 2006-01-02
885 | 20667 | 1999-0763 | 1999 | 2 | LUC-IR75-001.99 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-01-02 | 2006-01-02
885 | 20667 | 1999-0763 | 1999 | 2 | LUC-IR75-001.99 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-01-02 | 2006-01-02
881 | 20735 | 1999-0776 | 1999 | 2 | OTT-SR2-023.41 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2000-11-14 | 2003-11-14
881 | 20735 | 1999-0776 | 1999 | 2 | OTT-SR2-023.41 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2000-11-14 | 2003-11-14
882 | 20737 | 1999-0777 | 1999 | 2 | OTT-SR163-004.05 | SINGLE CHIP SEAL WITH WARRANTY | 2000-09-18 | 2003-09-18
892 | 17124 | 1999-3000 | 1999 | 1 | ALL-IR75-29.564 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USING HYDRO-DEMOLITION WITH WARRANTY | 2000-07-07 | 2003-07-07
892 | 17124 | 1999-3000 | 1999 | 1 | ALL-IR75-29.564 | MICRO-SILICA MODIFIED CONCRETE OVERLAY (VARIABLE THICKNESS),MATERIAL ONLY WITH WARRANTY | 2000-07-07 | 2003-07-07
892 | 17124 | 1999-3000 | 1999 | 1 | ALL-IR75-29.564 | HAND CHIPPING WITH WARRANTY | 2000-07-07 | 2003-07-07
892 | 17124 | 1999-3000 | 1999 | 1 | ALL-IR75-29.564 | FULL DEPTH REPAIR WITH WARRANTY | 2000-07-07 | 2003-07-07
892 | 17124 | 1999-3000 | 1999 | 1 | ALL-IR75-29.564 | TEST SLAB | 2000-07-07 | 2003-07-07
892 | 17124 | 1999-3000 | 1999 | 1 | ALL-IR75-29.564 | SURFACE PREPARATION USING HYDRO-DEMOLITION WITH WARRANTY | 2000-07-07 | 2003-07-07
880 | 16967 | 1999-5028 | 1999 | 6 | FRA-IR670-005.61 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 1999-11-01 | 2004-11-01
885 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-11-11 | 2008-11-11
885 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-11-11 | 2008-11-11
885 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-11-11 | 2008-11-11
885 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-11-11 | 2008-11-11
880 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2001-11-11 | 2008-11-11
887 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | EDGE LINE (5 YEAR WARRANTY) | 2001-11-11 | 2008-11-11
887 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | LANE LINE (5 YEAR WARRANTY) | 2001-11-11 | 2008-11-11
887 | 5881 | 2000-0004 | 2000 | 6 | FRA-IR70-014.69 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2001-11-11 | 2008-11-11
880 | 20943 | 2000-0017 | 2000 | 6 | FRA-IR670-005.61 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2000-08-09 | 2005-08-09
887 | 20943 | 2000-0017 | 2000 | 6 | FRA-IR670-005.61 | EDGE LINE (5 YEAR WARRANTY) | 2000-08-09 | 2005-08-09
887 | 20943 | 2000-0017 | 2000 | 6 | FRA-IR670-005.61 | LANE LINE (5 YEAR WARRANTY) | 2000-08-09 | 2005-08-09
887 | 20943 | 2000-0017 | 2000 | 6 | FRA-IR670-005.61 | CENTER LINE (5 YEAR WARRANTY) | 2000-08-09 | 2005-08-09
887 | 20943 | 2000-0017 | 2000 | 6 | FRA-IR670-005.61 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2000-08-09 | 2005-08-09
887 | 11376 | 2000-0023 | 2000 | 3 | ERI-SR2-12.558 | EDGE LINE (5 YEAR WARRANTY) | 2001-11-14 | 2008-11-14
887 | 11376 | 2000-0023 | 2000 | 3 | ERI-SR2-12.558 | LANE LINE (5 YEAR WARRANTY) | 2001-11-14 | 2008-11-14
887 | 11376 | 2000-0023 | 2000 | 3 | ERI-SR2-12.558 | CENTER LINE (5 YEAR WARRANTY) | 2001-11-14 | 2008-11-14
887 | 11376 | 2000-0023 | 2000 | 3 | ERI-SR2-12.558 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2001-11-14 | 2008-11-14
880 | 11376 | 2000-0023 | 2000 | 3 | ERI-SR2-12.558 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2001-11-14 | 2008-11-14
446 | 19555 | 2000-0027 | 2000 | 1 | WYA-US30-015.95 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2000-08-14 | 2003-08-14
887 | 19156 | 2000-0028 | 2000 | 9 | ADA-SR41-000.00 | EDGE LINE (3 YEAR WARRANTY) | Non performed
887 | 19156 | 2000-0028 | 2000 | 9 | ADA-SR41-000.00 | LANE LINE (3 YEAR WARRANTY) | Non performed
887 | 19156 | 2000-0028 | 2000 | 9 | ADA-SR41-000.00 | CENTER LINE (3 YEAR WARRANTY) | Non performed
880 | 11366 | 2000-0037 | 2000 | 3 | ASD-IR71-14.383 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2001-11-28 | 2008-11-28
887 | 11366 | 2000-0037 | 2000 | 3 | ASD-IR71-14.383 | EDGE LINE (5 YEAR WARRANTY) | 2001-11-28 | 2008-11-28
887 | 11366 | 2000-0037 | 2000 | 3 | ASD-IR71-14.383 | LANE LINE (5 YEAR WARRANTY) | 2001-11-28 | 2008-11-28
887 | 11366 | 2000-0037 | 2000 | 3 | ASD-IR71-14.383 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2001-11-28 | 2008-11-28
644 | 11366 | 2000-0037 | 2000 | 3 | ASD-IR71-14.383 | EDGE LINE | 2001-11-28 | 2008-11-28
644 | 11366 | 2000-0037 | 2000 | 3 | ASD-IR71-14.383 | LANE LINE | 2001-11-28 | 2008-11-28
644 | 11366 | 2000-0037 | 2000 | 3 | ASD-IR71-14.383 | CHANNELIZING LINE | 2001-11-28 | 2008-11-28
885 | 19724 | 2000-0039 | 2000 | 8 | BUT-SR4-000.40 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-12-06 | 2005-12-06
885 | 19724 | 2000-0039 | 2000 | 8 | BUT-SR4-000.40 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-12-06 | 2005-12-06
885 | 19724 | 2000-0039 | 2000 | 8 | BUT-SR4-000.40 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-12-06 | 2005-12-06
885 | 19724 | 2000-0039 | 2000 | 8 | BUT-SR4-000.40 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-12-06 | 2005-12-06
887 | 20660 | 2000-0059 | 2000 | 6 | FRA-IR71-000.00 | EDGE LINE (3 YEAR WARRANTY) | Non performed
887 | 20660 | 2000-0059 | 2000 | 6 | FRA-IR71-000.00 | LANE LINE (3 YEAR WARRANTY) | Non performed
887 | 20660 | 2000-0059 | 2000 | 6 | FRA-IR71-000.00 | CHANNELIZING LINE (3 YEAR WARRANTY) | Non performed
887 | 19980 | 2000-0061 | 2000 | 6 | FRA-IR270-037.00 | EDGE LINE (5 YEAR WARRANTY) | Non performed
887 | 19980 | 2000-0061 | 2000 | 6 | FRA-IR270-037.00 | LANE LINE (5 YEAR WARRANTY) | Non performed
887 | 19980 | 2000-0061 | 2000 | 6 | FRA-IR270-037.00 | CHANNELIZING LINE (5 YEAR WARRANTY) | Non performed
885 | 15348 | 2000-0067 | 2000 | 8 | HAM-US22-013.30 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-12-13 | 2005-12-13
885 | 15348 | 2000-0067 | 2000 | 8 | HAM-US22-013.30 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-12-13 | 2005-12-13
885 | 15348 | 2000-0067 | 2000 | 8 | HAM-US22-013.30 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-12-13 | 2005-12-13
885 | 15348 | 2000-0067 | 2000 | 8 | HAM-US22-013.30 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-12-13 | 2005-12-13
887 | 20980 | 2000-0075 | 2000 | 2 | OTT-SR2-23.240 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 20980 | 2000-0075 | 2000 | 2 | OTT-SR2-23.240 | LANE LINE (5 YEAR WARRANTY) | Voided
887 | 20980 | 2000-0075 | 2000 | 2 | OTT-SR2-23.240 | CENTER LINE (5 YEAR WARRANTY) | Voided
887 | 19309 | 2000-0079 | 2000 | 2 | WIL-SR49-002.05 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 19309 | 2000-0079 | 2000 | 2 | WIL-SR49-002.05 | CENTER LINE (5 YEAR WARRANTY) | Voided
880 | 4388 | 2000-0091 | 2000 | 6 | GRE-US35-026.20 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-07-20 | 2009-07-20
887 | 4388 | 2000-0091 | 2000 | 6 | GRE-US35-026.20 | EDGE LINE (5 YEAR WARRANTY) | 2002-07-20 | 2009-07-20
887 | 4388 | 2000-0091 | 2000 | 6 | GRE-US35-026.20 | LANE LINE (5 YEAR WARRANTY) | 2002-07-20 | 2009-07-20
887 | 4388 | 2000-0091 | 2000 | 6 | GRE-US35-026.20 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2002-07-20 | 2009-07-20
894 | 16440 | 2000-0106 | 2000 | 1 | HAN-SR613-20.331 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2000-11-29 | 2007-11-29
887 | 13348 | 2000-0109 | 2000 | 10 | MOE-SR800-35.170 | EDGE LINE (5 YEAR WARRANTY) | Assumed Expired
887 | 13348 | 2000-0109 | 2000 | 10 | MOE-SR800-35.170 | LANE LINE (5 YEAR WARRANTY) | Assumed Expired
887 | 13348 | 2000-0109 | 2000 | 10 | MOE-SR800-35.170 | CENTER LINE (5 YEAR WARRANTY) | Assumed Expired
885 | 20768 | 2000-0111 | 2000 | 5 | MUS-US22-006.10 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-10-13 | 2005-10-13
885 | 20768 | 2000-0111 | 2000 | 5 | MUS-US22-006.10 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-10-13 | 2005-10-13
885 | 20768 | 2000-0111 | 2000 | 5 | MUS-US22-006.10 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-10-13 | 2005-10-13
885 | 20768 | 2000-0111 | 2000 | 5 | MUS-US22-006.10 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-10-13 | 2005-10-13
887 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | LANE LINE (5 YEAR WARRANTY) | Voided
887 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | CENTER LINE (5 YEAR WARRANTY) | Voided
892 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | SURFACE PREPARATION USING HYDRO-DEMOLITION WITH WARRANTY | Voided
892 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USING HYDRO-DEMOLITION WITH WARRANTY | Voided
892 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | MICRO-SILICA MODIFIED CONCRETE OVERLAY (VARIABLE THICKNESS), MATERIAL ONLY WITH WARRANTY | Voided
892 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | HAND CHIPPING WITH WARRANTY | Voided
892 | 19339 | 2000-0112 | 2000 | 2 | OTT-SR53-011.83 | FULL DEPTH REPAIR WITH WARRANTY | Voided
880 | 17045 | 2000-0114 | 2000 | 9 | ROS-US23-000.00 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2000-12-12 | 2005-12-12
887 | 17045 | 2000-0114 | 2000 | 9 | ROS-US23-000.00 | EDGE LINE (5 YEAR WARRANTY) | 2000-12-12 | 2005-12-12
887 | 17045 | 2000-0114 | 2000 | 9 | ROS-US23-000.00 | LANE LINE (5 YEAR WARRANTY) | 2000-12-12 | 2005-12-12
887 | 17045 | 2000-0114 | 2000 | 9 | ROS-US23-000.00 | CENTER LINE (5 YEAR WARRANTY) | 2000-12-12 | 2005-12-12
887 | 17045 | 2000-0114 | 2000 | 9 | ROS-US23-000.00 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2000-12-12 | 2005-12-12
893 | 8831 | 2000-0116 | 2000 | 4 | STA-SR44-21.050 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-08-08 | 2008-08-08
887 | 19308 | 2000-0118 | 2000 | 2 | WIL-US6-000.00 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 19308 | 2000-0118 | 2000 | 2 | WIL-US6-000.00 | CENTER LINE (5 YEAR WARRANTY) | Voided
885 | 15992 | 2000-0119 | 2000 | 1 | WYA-SR37-14.806 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-07-14 | 2005-07-14
885 | 15992 | 2000-0119 | 2000 | 1 | WYA-SR37-14.806 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-07-14 | 2005-07-14
885 | 15992 | 2000-0119 | 2000 | 1 | WYA-SR37-14.806 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-07-14 | 2005-07-14
885 | 15992 | 2000-0119 | 2000 | 1 | WYA-SR37-14.806 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-07-14 | 2005-07-14
893 | 15992 | 2000-0119 | 2000 | 1 | WYA-SR37-14.806 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2000-07-14 | 2005-07-14
880 | 16299 | 2000-0136 | 2000 | 5 | MUS-SR16-007.16 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-11-13 | 2009-11-13
893 | 16299 | 2000-0136 | 2000 | 5 | MUS-SR16-007.16 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-11-13 | 2009-11-13
893 | 17071 | 2000-0138 | 2000 | 1 | ALL-SR81-00.821 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2000-11-02 | 2007-11-02
887 | 14524 | 2000-0150 | 2000 | 10 | NOB-SR78-09.185 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 14524 | 2000-0150 | 2000 | 10 | NOB-SR78-09.185 | CENTER LINE (3 YEAR WARRANTY) | Voided
887 | 11365 | 2000-0151 | 2000 | 3 | RIC-IR71-20.220 | EDGE LINE (5 YEAR WARRANTY) | 2002-11-26 | 2009-11-26
887 | 11365 | 2000-0151 | 2000 | 3 | RIC-IR71-20.220 | LANE LINE (5 YEAR WARRANTY) | 2002-11-26 | 2009-11-26
887 | 11365 | 2000-0151 | 2000 | 3 | RIC-IR71-20.220 | CENTER LINE (5 YEAR WARRANTY) | 2002-11-26 | 2009-11-26
887 | 11365 | 2000-0151 | 2000 | 3 | RIC-IR71-20.220 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2002-11-26 | 2009-11-26
880 | 11365 | 2000-0151 | 2000 | 3 | RIC-IR71-20.220 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-11-26 | 2009-11-26
887 | 16924 | 2000-0154 | 2000 | 3 | ASD-US250-016.48 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 16924 | 2000-0154 | 2000 | 3 | ASD-US250-016.48 | LANE LINE (3 YEAR WARRANTY) | Voided
887 | 16924 | 2000-0154 | 2000 | 3 | ASD-US250-016.48 | CENTER LINE (3 YEAR WARRANTY) | Voided
887 | 16924 | 2000-0154 | 2000 | 3 | ASD-US250-016.48 | CHANNELIZING LINE (3 YEAR WARRANTY) | Voided
885 | 19349 | 2000-0165 | 2000 | 8 | CLE-SR749-000.00 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-11-20 | 2005-11-20
885 | 19349 | 2000-0165 | 2000 | 8 | CLE-SR749-000.00 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-11-20 | 2005-11-20
885 | 19349 | 2000-0165 | 2000 | 8 | CLE-SR749-000.00 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-11-20 | 2005-11-20
885 | 19349 | 2000-0165 | 2000 | 8 | CLE-SR749-000.00 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-11-20 | 2005-11-20
887 | 19349 | 2000-0165 | 2000 | 8 | CLE-SR749-000.00 | EDGE LINE (5 YEAR WARRANTY) | 2000-11-20 | 2005-11-20
887 | 19349 | 2000-0165 | 2000 | 8 | CLE-SR749-000.00 | CENTER LINE (5 YEAR WARRANTY) | 2000-11-20 | 2005-11-20
880 | 16044 | 2000-0172 | 2000 | 1 | ALL-US30-013.27 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2000-11-28 | 2005-11-28
887 | 19344 | 2000-0175 | 2000 | 8 | BUT-SR73-016.64 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 19344 | 2000-0175 | 2000 | 8 | BUT-SR73-016.64 | LANE LINE (3 YEAR WARRANTY) | Voided
887 | 19344 | 2000-0175 | 2000 | 8 | BUT-SR73-016.64 | CENTER LINE (3 YEAR WARRANTY) | Voided
887 | 19344 | 2000-0175 | 2000 | 8 | BUT-SR73-016.64 | CHANNELIZING LINE (3 YEAR WARRANTY) | Voided
885 | 15350 | 2000-0184 | 2000 | 8 | PRE-US127-003.76 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2000-10-25 | 2005-10-25
885 | 15350 | 2000-0184 | 2000 | 8 | PRE-US127-003.76 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2000-10-25 | 2005-10-25
885 | 15350 | 2000-0184 | 2000 | 8 | PRE-US127-003.76 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2000-10-25 | 2005-10-25
885 | 15350 | 2000-0184 | 2000 | 8 | PRE-US127-003.76 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2000-10-25 | 2005-10-25
887 | 19933 | 2000-0188 | 2000 | 10 | ATH-SR78-001.58 | EDGE LINE (5 YEAR WARRANTY) | Non performed
887 | 19933 | 2000-0188 | 2000 | 10 | ATH-SR78-001.58 | CENTER LINE (5 YEAR WARRANTY) | Non performed
887 | 19960 | 2000-0193 | 2000 | 10 | HOC-SR93-013.68 | EDGE LINE (5 YEAR WARRANTY) | Non performed
887 | 19960 | 2000-0193 | 2000 | 10 | HOC-SR93-013.68 | CENTER LINE (5 YEAR WARRANTY) | Non performed
887 | 19175 | 2000-0194 | 2000 | 6 | MAR-SR95-016.77 | EDGE LINE (5 YEAR WARRANTY) | Non performed
887 | 19175 | 2000-0194 | 2000 | 6 | MAR-SR95-016.77 | LANE LINE (5 YEAR WARRANTY) | Non performed
887 | 19175 | 2000-0194 | 2000 | 6 | MAR-SR95-016.77 | CENTER LINE (5 YEAR WARRANTY) | Non performed
887 | 19175 | 2000-0194 | 2000 | 6 | MAR-SR95-016.77 | CHANNELIZING LINE (5 YEAR WARRANTY) | Non performed
894 | 9176 | 2000-0197 | 2000 | 12 | CUY-IR271-009.72 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2001-11-21 | 2008-11-21
880 | 19338 | 2000-0206 | 2000 | 2 | SAN-US20-026.53 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2000-11-06 | 2005-11-06
887 | 12387 | 2000-0217 | 2000 | 6 | FRA-US33-026.12 | EDGE LINE (3 YEAR WARRANTY) | Non performed
887 | 12387 | 2000-0217 | 2000 | 6 | FRA-US33-026.12 | LANE LINE (3 YEAR WARRANTY) | Non performed
887 | 12387 | 2000-0217 | 2000 | 6 | FRA-US33-026.12 | CENTER LINE (3 YEAR WARRANTY) | Non performed
887 | 12387 | 2000-0217 | 2000 | 6 | FRA-US33-026.12 | CHANNELIZING LINE (3 YEAR WARRANTY) | Non performed
889 | 12387 | 2000-0217 | 2000 | 6 | FRA-US33-026.12 | SAWING AND SEALING ASPHALT CONCRETE PAVEMENT JOINTS WITH WARRANTY | Non performed
887 | 19393 | 2000-0223 | 2000 | 8 | PRE-SR503-001.00 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 19393 | 2000-0223 | 2000 | 8 | PRE-SR503-001.00 | CENTER LINE (3 YEAR WARRANTY) | Voided
448 | 19976 | 2000-0228 | 2000 | 10 | WAS-SR339-008.58 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY | 2000-08-25 | 2003-08-25
894 | 16380 | 2000-0229 | 2000 | 9 | BRO-SR763-16.036 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-08-15 | 2008-08-15
894 | 18122 | 2000-0232 | 2000 | 12 | CUY-IR71-013.16 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2001-01-12 | 2008-01-12
887 | 19687 | 2000-0236 | 2000 | 8 | HAM-IR275-010.57 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 19687 | 2000-0236 | 2000 | 8 | HAM-IR275-010.57 | LANE LINE (5 YEAR WARRANTY) | Voided
887 | 19687 | 2000-0236 | 2000 | 8 | HAM-IR275-010.57 | CHANNELIZING LINE (5 YEAR WARRANTY) | Voided
894 | 13171 | 2000-0237 | 2000 | 9 | HIG-SR131-06.190 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2000-10-26 | 2007-10-26
880 | 7885 | 2000-0239 | 2000 | 3 | MED-IR71-015.78 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-12-02 | 2009-12-02
887 | 7885 | 2000-0239 | 2000 | 3 | MED-IR71-015.78 | EDGE LINE (5 YEAR WARRANTY) | 2002-12-02 | 2009-12-02
887 | 7885 | 2000-0239 | 2000 | 3 | MED-IR71-015.78 | LANE LINE (5 YEAR WARRANTY) | 2002-12-02 | 2009-12-02
887 | 7885 | 2000-0239 | 2000 | 3 | MED-IR71-015.78 | CENTER LINE (5 YEAR WARRANTY) | 2002-12-02 | 2009-12-02
887 | 7885 | 2000-0239 | 2000 | 3 | MED-IR71-015.78 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2002-12-02 | 2009-12-02
887 | 19392 | 2000-0242 | 2000 | 8 | PRE-US40-000.00 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 19392 | 2000-0242 | 2000 | 8 | PRE-US40-000.00 | LANE LINE (3 YEAR WARRANTY) | Voided
887 | 19392 | 2000-0242 | 2000 | 8 | PRE-US40-000.00 | CENTER LINE (3 YEAR WARRANTY) | Voided
887 | 19392 | 2000-0242 | 2000 | 8 | PRE-US40-000.00 | CHANNELIZING LINE (3 YEAR WARRANTY) | Voided
884 | 17440 | 2000-0248 | 2000 | 10 | WAS-IR77-006.59 | VARIABLE THICKNESS PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2000-12-18 | 2007-12-18
884 | 17440 | 2000-0248 | 2000 | 10 | WAS-IR77-006.59 | 8" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2000-12-18 | 2007-12-18
884 | 17440 | 2000-0248 | 2000 | 10 | WAS-IR77-006.59 | 11" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2000-12-18 | 2007-12-18
887 | 17440 | 2000-0248 | 2000 | 10 | WAS-IR77-006.59 | EDGE LINE (5 YEAR WARRANTY) | 2000-12-18 | 2007-12-18
887 | 17440 | 2000-0248 | 2000 | 10 | WAS-IR77-006.59 | LANE LINE (5 YEAR WARRANTY) | 2000-12-18 | 2007-12-18
887 | 19660 | 2000-0251 | 2000 | 8 | CLI-SR350-000.00 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 19660 | 2000-0251 | 2000 | 8 | CLI-SR350-000.00 | CENTER LINE (3 YEAR WARRANTY) | Voided
825 | 21023 | 2000-0257 | 2000 | 5 | LIC-SR13-000.00 | CRACK SEALING WITH WARRANTY, TYPE II | 2001-05-02 | 2003-05-02
887 | 18730 | 2000-0263 | 2000 | 12 | CUY-IR90-023.93 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 18730 | 2000-0263 | 2000 | 12 | CUY-IR90-023.93 | LANE LINE (5 YEAR WARRANTY) | Voided
887 | 18730 | 2000-0263 | 2000 | 12 | CUY-IR90-023.93 | CENTER LINE (5 YEAR WARRANTY) | Voided
887 | 18730 | 2000-0263 | 2000 | 12 | CUY-IR90-023.93 | CHANNELIZING LINE (5 YEAR WARRANTY) | Voided
887 | 16738 | 2000-0273 | 2000 | 3 | LOR-SR83-06.727 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 16738 | 2000-0273 | 2000 | 3 | LOR-SR83-06.727 | CENTER LINE (3 YEAR WARRANTY) | Voided
887 | 16738 | 2000-0273 | 2000 | 3 | LOR-SR83-06.727 | CHANNELIZING LINE (3 YEAR WARRANTY) | Voided
885 | 19358 | 2000-0274 | 2000 | 2 | LUC-US20-009.54 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-08-21 | 2006-08-21
885 | 19358 | 2000-0274 | 2000 | 2 | LUC-US20-009.54 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-08-21 | 2006-08-21
885 | 19358 | 2000-0274 | 2000 | 2 | LUC-US20-009.54 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-08-21 | 2006-08-21
885 | 19358 | 2000-0274 | 2000 | 2 | LUC-US20-009.54 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-08-21 | 2006-08-21
887 | 17003 | 2000-0279 | 2000 | 6 | UNI-US33-008.74 | EDGE LINE (5 YEAR WARRANTY) | Non performed
887 | 17003 | 2000-0279 | 2000 | 6 | UNI-US33-008.74 | LANE LINE (5 YEAR WARRANTY) | Non performed
887 | 17003 | 2000-0279 | 2000 | 6 | UNI-US33-008.74 | CHANNELIZING LINE (5 YEAR WARRANTY) | Non performed
882 | 21244 | 2000-0284 | 2000 | 3 | ASD-SR604-000.00 | SINGLE CHIP SEAL WITH WARRANTY | 2000-11-24 | 2003-11-24
882 | 21212 | 2000-0286 | 2000 | 3 | CRA-SR103-009.92 | SINGLE CHIP SEAL WITH WARRANTY | 2000-09-30 | 2003-09-30
825 | 21211 | 2000-0299 | 2000 | 3 | RIC-US30-003.46 | CRACK SEALING WITH WARRANTY, TYPE II OR III | 2000-08-24 | 2002-08-24
887 | 18410 | 2000-0300 | 2000 | 2 | SEN-SR67-002.33 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 18410 | 2000-0300 | 2000 | 2 | SEN-SR67-002.33 | CENTER LINE (5 YEAR WARRANTY) | Voided
880 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2001-11-28 | 2006-11-28
887 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | EDGE LINE (5 YEAR WARRANTY) | 2001-11-28 | 2006-11-28
887 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | LANE LINE (5 YEAR WARRANTY) | 2001-11-28 | 2006-11-28
887 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | CHANNELIZING LINE (5 YEAR WARRANTY) | 2001-11-28 | 2006-11-28
885 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-11-28 | 2006-11-28
885 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-11-28 | 2006-11-28
885 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-11-28 | 2006-11-28
885 | 18286 | 2000-0302 | 2000 | 3 | ASD-US30-09.484 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-11-28 | 2006-11-28
880 | 10904 | 2000-0304 | 2000 | 9 | BRO-US62-31.640 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2001-12-12 | 2008-12-12
885 | 19494 | 2000-0306 | 2000 | 12 | CUY-US6-000.42 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-11-06 | 2006-11-06
885 | 19494 | 2000-0306 | 2000 | 12 | CUY-US6-000.42 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-11-06 | 2006-11-06
885 | 19494 | 2000-0306 | 2000 | 12 | CUY-US6-000.42 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-11-06 | 2006-11-06
885 | 19494 | 2000-0306 | 2000 | 12 | CUY-US6-000.42 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-11-06 | 2006-11-06
894 | 18744 | 2000-0308 | 2000 | 12 | CUY-IR271-004.17 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2001-10-15 | 2008-10-15
448 | 19948 | 2000-0321 | 2000 | 5 | PER-US13-020.38 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY | 2000-11-07 | 2003-11-07
884 | 13458 | 2000-0323 | 2000 | 4 | SUM-IR76-24.799 | 310 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | Voided
884 | 13458 | 2000-0323 | 2000 | 4 | SUM-IR76-24.799 | 350 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | Voided
885 | 13458 | 2000-0323 | 2000 | 4 | SUM-IR76-24.799 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | Voided
885 | 13458 | 2000-0323 | 2000 | 4 | SUM-IR76-24.799 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | Voided
885 | 13458 | 2000-0323 | 2000 | 4 | SUM-IR76-24.799 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | Voided
885 | 13458 | 2000-0323 | 2000 | 4 | SUM-IR76-24.799 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | Voided
990 | 13458 | 2000-0323 | 2000 | 4 | SUM-IR76-24.799 | AGREED LUMP SUM | Voided
446 | 16894 | 2000-0328 | 2000 | 3 | WAY-SR94-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY | Voided
887 | 16894 | 2000-0328 | 2000 | 3 | WAY-SR94-000.00 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 16894 | 2000-0328 | 2000 | 3 | WAY-SR94-000.00 | CENTER LINE (3 YEAR WARRANTY) | Voided
894 | 19451 | 2000-0330 | 2000 | 2 | WOO-IR280-003.85 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-07-25 | 2009-07-25
882 | 21243 | 2000-0333 | 2000 | 3 | ASD-SR95-010.26 | SINGLE CHIP SEAL WITH WARRANTY | 2000-09-08 | 2003-09-08
887 | 19342 | 2000-0341 | 2000 | 2 | FUL-US20-010.86 | EDGE LINE (5 YEAR WARRANTY) | Voided
887 | 19342 | 2000-0341 | 2000 | 2 | FUL-US20-010.86 | CENTER LINE (5 YEAR WARRANTY) | Voided
887 | 19402 | 2000-0353 | 2000 | 6 | MAR-US23-010.63 | EDGE LINE (5 YEAR WARRANTY) | Non performed
887 | 19402 | 2000-0353 | 2000 | 6 | MAR-US23-010.63 | LANE LINE (5 YEAR WARRANTY) | Non performed
887 | 19402 | 2000-0353 | 2000 | 6 | MAR-US23-010.63 | CHANNELIZING LINE (5 YEAR WARRANTY) | Non performed
887 | 18546 | 2000-0357 | 2000 | 4 | POR-SR5-000.19 | EDGE LINE (3 YEAR WARRANTY) | Voided
887 | 18546 | 2000-0357 | 2000 | 4 | POR-SR5-000.19 | LANE LINE (3 YEAR WARRANTY) | Voided
887 | 18546 | 2000-0357 | 2000 | 4 | POR-SR5-000.19 | CENTER LINE (3 YEAR WARRANTY) | Voided
887 | 18546 | 2000-0357 | 2000 | 4 | POR-SR5-000.19 | CHANNELIZING LINE (3 YEAR WARRANTY) | Voided
885 | 16806 | 2000-0378 | 2000 | 5 | LIC-IR70-25.685 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 16806 | 2000-0378 | 2000 | 5 | LIC-IR70-25.685 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 16806 | 2000-0378 | 2000 | 5 | LIC-IR70-25.685 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 16806 | 2000-0378 | 2000 | 5 | LIC-IR70-25.685 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 18375 | 2000-0406 | 2000 | 4 | POR-IR76-013.55 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-10-05 | 2006-10-05
885 | 18375 | 2000-0406 | 2000 | 4 | POR-IR76-013.55 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-10-05 | 2006-10-05
885 | 18375 | 2000-0406 | 2000 | 4 | POR-IR76-013.55 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-10-05 | 2006-10-05
885 | 18375 | 2000-0406 | 2000 | 4 | POR-IR76-013.55 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-10-05 | 2006-10-05
887 | 19218 | 2000-0411 | 2000 | 9 | BRO-SR774-000.00 | EDGE LINE (3 YEAR WARRANTY) | Non performed
887 | 19218 | 2000-0411 | 2000 | 9 | BRO-SR774-000.00 | CENTER LINE (3 YEAR WARRANTY) | Non performed
885 | 19963 | 2000-0425 | 2000 | 4 | MAH-IR680-000.67 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-08-01 | 2006-08-01
885 | 19963 | 2000-0425 | 2000 | 4 | MAH-IR680-000.67 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-08-01 | 2006-08-01
885 | 19963 | 2000-0425 | 2000 | 4 | MAH-IR680-000.67 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-08-01 | 2006-08-01
885 | 19963 | 2000-0425 | 2000 | 4 | MAH-IR680-000.67 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-08-01 | 2006-08-01
894 | 10213 | 2000-0427 | 2000 | 10 | MRG-SR669-00.209 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-11-13 | 2008-11-13
885 | 18746 | 2000-0444 | 2000 | 12 | LAK-IR90-000.80 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-10-21 | 2006-10-21
885 | 18746 | 2000-0444 | 2000 | 12 | LAK-IR90-000.80 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-10-21 | 2006-10-21
885 | 18746 | 2000-0444 | 2000 | 12 | LAK-IR90-000.80 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-10-21 | 2006-10-21
885 | 18746 | 2000-0444 | 2000 | 12 | LAK-IR90-000.80 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-10-21 | 2006-10-21
881 | 21242 | 2000-0445 | 2000 | 3 | LOR-SR2-003.48 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2001-07-06 | 2004-07-06
894 | 13169 | 2000-0459 | 2000 | 9 | HIG-SR28-14.045 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-10-10 | 2008-10-10
885 | 19795 | 2000-0466 | 2000 | 9 | HIG-US62-025.43 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-07-08 | 2006-07-08
885 | 19795 | 2000-0466 | 2000 | 9 | HIG-US62-025.43 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-07-08 | 2006-07-08
885 | 19795 | 2000-0466 | 2000 | 9 | HIG-US62-025.43 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-07-08 | 2006-07-08
885 | 19795 | 2000-0466 | 2000 | 9 | HIG-US62-025.43 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-07-08 | 2006-07-08
885 | 21007 | 2000-0471 | 2000 | 8 | GRE-IR675-010.25 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-05-25 | 2006-05-25
885 | 21007 | 2000-0471 | 2000 | 8 | GRE-IR675-010.25 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-05-25 | 2006-05-25
885 | 21007 | 2000-0471 | 2000 | 8 | GRE-IR675-010.25 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-05-25 | 2006-05-25
885 | 21007 | 2000-0471 | 2000 | 8 | GRE-IR675-010.25 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-05-25 | 2006-05-25
446 | 20990 | 2000-0478 | 2000 | 6 | FRA-IR270-052.16 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2001-07-30 | 2004-07-30
894 | 13590 | 2000-0487 | 2000 | 11 | JEF-SR152-14.688 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-08-21 | 2008-08-21
894 | 12917 | 2000-0488 | 2000 | 9 | ROS-SR159-000.42 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-10-17 | 2009-10-17
893 | 17413 | 2000-0502 | 2000 | 7 | LOG-SR273-007.36 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-06-14 | 2008-06-14
894 | 13204 | 2000-0503 | 2000 | 10 | MEG-SR124-012.52 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-11-07 | 2008-11-07
446 | 17068 | 2000-0505 | 2000 | 7 | MOT-IR70-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H, PG76-22 WITH SUPPLEMENT 1059 WARRANTY | 2001-10-08 | 2004-10-08
885 | 15936 | 2000-0511 | 2000 | 11 | HAS-US22-017.48 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-12-19 | 2006-12-19
885 | 15936 | 2000-0511 | 2000 | 11 | HAS-US22-017.48 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-12-19 | 2006-12-19
885 | 15936 | 2000-0511 | 2000 | 11 | HAS-US22-017.48 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-12-19 | 2006-12-19
885 | 15936 | 2000-0511 | 2000 | 11 | HAS-US22-017.48 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-12-19 | 2006-12-19
894 | 15936 | 2000-0511 | 2000 | 11 | HAS-US22-017.48 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-12-19 | 2006-12-19
446 | 21605 | 2000-0512 | 2000 | 6 | PIC-US23-012.92 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2001-07-25 | 2004-07-25
885 | 10055 | 2000-0524 | 2000 | 4 | ATB-SR11-024.62 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2002-06-21 | 2007-06-21
885 | 10055 | 2000-0524 | 2000 | 4 | ATB-SR11-024.62 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2002-06-21 | 2007-06-21
885 | 10055 | 2000-0524 | 2000 | 4 | ATB-SR11-024.62 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2002-06-21 | 2007-06-21
885 | 10055 | 2000-0524 | 2000 | 4 | ATB-SR11-024.62 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2002-06-21 | 2007-06-21
893 | 10055 | 2000-0524 | 2000 | 4 | ATB-SR11-024.62 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-06-21 | 2007-06-21
885 | 19502 | 2000-0526 | 2000 | 12 | CUY-SR237-004.84 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2002-07-22 | 2007-07-22
885 | 19502 | 2000-0526 | 2000 | 12 | CUY-SR237-004.84 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2002-07-22 | 2007-07-22
885 | 19502 | 2000-0526 | 2000 | 12 | CUY-SR237-004.84 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2002-07-22 | 2007-07-22
885 | 19502 | 2000-0526 | 2000 | 12 | CUY-SR237-004.84 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2002-07-22 | 2007-07-22
894 | 17411 | 2000-0527 | 2000 | 7 | DAR-SR47-004.69 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-08-17 | 2008-08-17
885 | 16105 | 2000-0533 | 2000 | 5 | LIC-SR661-000.24 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2002-10-31 | 2007-10-31
885 | 16105 | 2000-0533 | 2000 | 5 | LIC-SR661-000.24 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2002-10-31 | 2007-10-31
885 | 16105 | 2000-0533 | 2000 | 5 | LIC-SR661-000.24 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2002-10-31 | 2007-10-31
885 | 16105 | 2000-0533 | 2000 | 5 | LIC-SR661-000.24 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2002-10-31 | 2007-10-31
894 | 16105 | 2000-0533 | 2000 | 5 | LIC-SR661-000.24 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-10-31 | 2007-10-31
885 | 11608 | 2000-0539 | 2000 | 4 | SUM-IR77-11.971 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-10-15 | 2006-10-15
885 | 11608 | 2000-0539 | 2000 | 4 | SUM-IR77-11.971 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-10-15 | 2006-10-15
885 | 11608 | 2000-0539 | 2000 | 4 | SUM-IR77-11.971 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-10-15 | 2006-10-15
885 | 11608 | 2000-0539 | 2000 | 4 | SUM-IR77-11.971 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-10-15 | 2006-10-15
893 | 11608 | 2000-0539 | 2000 | 4 | SUM-IR77-11.971 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-10-15 | 2006-10-15
446 | 11738 | 2000-0558 | 2000 | 12 | CUY-IR90-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2002-11-15 | 2009-11-15
880 | 11738 | 2000-0558 | 2000 | 12 | CUY-IR90-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-11-15 | 2009-11-15
885 | 18739 | 2000-0559 | 2000 | 12 | CUY-IR90-008.92 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-08-09 | 2006-08-09
885 | 18739 | 2000-0559 | 2000 | 12 | CUY-IR90-008.92 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-08-09 | 2006-08-09
885 | 18739 | 2000-0559 | 2000 | 12 | CUY-IR90-008.92 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-08-09 | 2006-08-09
885 | 18739 | 2000-0559 | 2000 | 12 | CUY-IR90-008.92 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-08-09 | 2006-08-09
880 | 19146 | 2000-0563 | 2000 | 9 | SCI-US23-005.51 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2002-02-05 | 2007-02-05
990 | 19146 | 2000-0563 | 2000 | 9 | SCI-US23-005.51 | AGREED LUMP SUM | 2002-02-05 | 2007-02-05
894 | 17452 | 2000-0564 | 2000 | 7 | SHE-SR274-008.96 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-11-12 | 2008-11-12
893 | 17452 | 2000-0564 | 2000 | 7 | SHE-SR274-008.96 | SPECIAL - STRUCTURAL CONCRETE WITH WARRANTY | 2001-11-12 | 2008-11-12
893 | 16572 | 2000-0566 | 2000 | 4 | SUM-IR77-41.954 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2001-11-08 | 2008-11-08
894 | 20787 | 2000-0568 | 2000 | 2 | WOO-IR75-000.73 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-12-06 | 2008-12-06
880 | 19767 | 2000-0569 | 2000 | 2 | WOO-IR75-019.92 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2001-11-19 | 2006-11-19
893 | 12961 | 2000-0570 | 2000 | 1 | WYA-SR231-06.160 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-09-18 | 2008-09-18
880 | 9078 | 2000-0577 | 2000 | 6 | FAY-US35-002.57 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2003-08-01 | 2010-08-01
690 | 19905 | 2000-3001 | 2000 | 10 | NOB-IR77-006.22 | SPECIAL - MISC.: | 2001-12-31 | 2008-12-31
990 | 19905 | 2000-3001 | 2000 | 10 | NOB-IR77-006.22 | AGREED LUMP SUM | 2001-12-31 | 2008-12-31
690 | 18200 | 2000-3002 | 2000 | 3 | MED-IR271-000.00 | SPECIAL - MISC.: | 2001-11-16 | 2006-11-16
690 | 18899 | 2000-3003 | 2000 | 8 | PRE-IR70-000.00 | SPECIAL - MISC.: | 2001-12-19 | 2006-12-19
690 | 19394 | 2000-3004 | 2000 | 8 | GRE-US35-000.00 | SPECIAL - MISC.: | 2001-11-26 | 2008-11-26
893 | 20917 | 2000-3007 | 2000 | 1 | PAU-SR613-022.02 | SPECIAL - STRUCTURE, MISC.: | 2001-05-10 | 2008-05-10
530 | 20411 | 2000-3008 | 2000 | 4 | STA-IR77-011.59 | SPECIAL - STRUCTURE, MISC.: | Assumed Expired
894 | 21082 | 2000-3010 | 2000 | 1 | ALL-US30-018.18 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2001-12-11 | 2008-12-11
880 | 19786 | 2000-3012 | 2000 | 8 | HAM-IR275-032.27 | SPECIAL - ASPHALT PAVEMENT (5 YEAR WARRANTY) | 2003-07-31 | 2008-07-31
885 | 21152 | 2000-3014 | 2000 | 1 | HAN-SR103-016.57 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-11-01 | 2006-11-01
885 | 21152 | 2000-3014 | 2000 | 1 | HAN-SR103-016.57 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-11-01 | 2006-11-01
885 | 21152 | 2000-3014 | 2000 | 1 | HAN-SR103-016.57 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-11-01 | 2006-11-01
885 | 21152 | 2000-3014 | 2000 | 1 | HAN-SR103-016.57 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-11-01 | 2006-11-01
894 | 21152 | 2000-3014 | 2000 | 1 | HAN-SR103-016.57 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2001-11-01 | 2006-11-01
880 | 17891 | 2000-3015 | 2000 | 3 | LOR-IR90-010.76 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) | 2003-02-12 | 2010-02-12
825 | 20221 | 2000-8002 | 2000 | 3 | RIC-IR71-000.00 | CRACK SEALING WITH WARRANTY, TYPE II OR III | 2000-08-02 | 2002-08-02
825 | 20220 | 2000-8003 | 2000 | 3 | WAY-IR71-000.00 | CRACK SEALING WITH WARRANTY, TYPE II OR III | 2000-09-30 | 2002-09-30
446 | 20994 | 2001-0006 | 2001 | 6 | FAY-IR71-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2001-08-31 | 2004-08-31
885 | 12836 | 2001-0008 | 2001 | 4 | STA-IR77-05.938 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2002-04-28 | 2007-04-28
885 | 12836 | 2001-0008 | 2001 | 4 | STA-IR77-05.938 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2002-04-28 | 2007-04-28
885 | 12836 | 2001-0008 | 2001 | 4 | STA-IR77-05.938 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2002-04-28 | 2007-04-28
885 | 12836 | 2001-0008 | 2001 | 4 | STA-IR77-05.938 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2002-04-28 | 2007-04-28
885 | 14005 | 2001-0022 | 2001 | 6 | FRA-IR70-013.22 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 14005 | 2001-0022 | 2001 | 6 | FRA-IR70-013.22 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 14005 | 2001-0022 | 2001 | 6 | FRA-IR70-013.22 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 14005 | 2001-0022 | 2001 | 6 | FRA-IR70-013.22 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-07-31 | 2006-07-31
885 | 19361 | 2001-0026 | 2001 | 6 | MAR-US23-018.15 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-11-27 | 2006-11-27
885 | 19361 | 2001-0026 | 2001 | 6 | MAR-US23-018.15 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-11-27 | 2006-11-27
885 | 19361 | 2001-0026 | 2001 | 6 | MAR-US23-018.15 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-11-27 | 2006-11-27
885 | 19361 | 2001-0026 | 2001 | 6 | MAR-US23-018.15 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-11-27 | 2006-11-27
880 | 16055 | 2001-0039 | 2001 | 1 | VAN-US30-021.18 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2002-06-07 | 2007-06-07
894 | 12887 | 2001-0054 | 2001 | 9 | ADA-SR73-16.320 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-11-21 | 2009-11-21
894 | 12909 | 2001-0057 | 2001 | 9 | HIG-SR753-00.140 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-09-05 | 2008-09-05
893 | 17066 | 2001-0060 | 2001 | 7 | MIA-SR41-006.26 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-10-02 | 2008-10-02
880 | 18922 | 2001-0083 | 2001 | 1 | HAN-SR15-021.52 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-06-14 | 2009-06-14
894 | 18922 | 2001-0083 | 2001 | 1 | HAN-SR15-021.52 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-06-14 | 2009-06-14
885 | 18019 | 2001-0088 | 2001 | 6 | PIC-SR138-006.32 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | Voided
885 | 18019 | 2001-0088 | 2001 | 6 | PIC-SR138-006.32 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | Voided
885 | 18019 | 2001-0088 | 2001 | 6 | PIC-SR138-006.32 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | Voided
885 | 18019 | 2001-0088 | 2001 | 6 | PIC-SR138-006.32 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | Voided
880 | 19509 | 2001-0096 | 2001 | 12 | CUY-SR176-012.76 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2002-06-07 | 2007-06-07
450 | 19509 | 2001-0096 | 2001 | 12 | CUY-SR176-012.76 | SPECIAL - CONCRETE BASE JOINT, CLEANED AND FILLED | 2002-06-07 | 2007-06-07
885 | 12339 | 2001-0107 | 2001 | 12 | CUY-IR90-006.21 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2002-05-15 | 2007-05-15
885 | 12339 | 2001-0107 | 2001 | 12 | CUY-IR90-006.21 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2002-05-15 | 2007-05-15
885 | 12339 | 2001-0107 | 2001 | 12 | CUY-IR90-006.21 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2002-05-15 | 2007-05-15
885 | 12339 | 2001-0107 | 2001 | 12 | CUY-IR90-006.21 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2002-05-15 | 2007-05-15
446 | 20800 | 2001-0108 | 2001 | 12 | CUY-IR90-013.41 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2002-07-18 | 2007-07-18
880 | 20800 | 2001-0108 | 2001 | 12 | CUY-IR90-013.41 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2002-07-18 | 2007-07-18
889 | 20800 | 2001-0108 | 2001 | 12 | CUY-IR90-013.41 | SAWING AND SEALING ASPHALT CONCRETE PAVEMENT JOINTS WITH WARRANTY | 2002-07-18 | 2007-07-18
893 | 13507 | 2001-0110 | 2001 | 7 | DAR-US127-019.77 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2001-11-21 | 2008-11-21
892 | 16446 | 2001-0113 | 2001 | 8 | HAM-US52-030.59 | SURFACE PREPARATION USING HYDRO-DEMOLITION WITH WARRANTY | 2001-07-27 | 2004-07-27
892 | 16446 | 2001-0113 | 2001 | 8 | HAM-US52-030.59 | MICRO-SILICA MODIFIED CONCRETE OVERLAY USING HYDRO-DEMOLITION WITH WARRANTY | 2001-07-27 | 2004-07-27
892 | 16446 | 2001-0113 | 2001 | 8 | HAM-US52-030.59 | MICRO-SILICA MODIFIED CONCRETE OVERLAY (VARIABLE THICKNESS), MATERIAL ONLY WITH WARRANTY | 2001-07-27 | 2004-07-27
892 | 16446 | 2001-0113 | 2001 | 8 | HAM-US52-030.59 | HAND CHIPPING WITH WARRANTY | 2001-07-27 | 2004-07-27
892 | 16446 | 2001-0113 | 2001 | 8 | HAM-US52-030.59 | TEST SLAB | 2001-07-27 | 2004-07-27
892 | 16446 | 2001-0113 | 2001 | 8 | HAM-US52-030.59 | FULL DEPTH REPAIR WITH WARRANTY | 2001-07-27 | 2004-07-27
885 | 17226 | 2001-0114 | 2001 | 8 | HAM-IR75-014.26 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-12-12 | 2006-12-12
885 | 17226 | 2001-0114 | 2001 | 8 | HAM-IR75-014.26 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-12-12 | 2006-12-12
885 | 17226 | 2001-0114 | 2001 | 8 | HAM-IR75-014.26 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-12-12 | 2006-12-12
885 | 17226 | 2001-0114 | 2001 | 8 | HAM-IR75-014.26 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-12-12 | 2006-12-12
880 | 11378 | 2001-0116 | 2001 | 3 | RIC-IR71-013.66 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-12-13 | 2009-12-13
894 | 11378 | 2001-0116 | 2001 | 3 | RIC-IR71-013.66 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2002-12-13 | 2009-12-13
885 | 13226 | 2001-0118 | 2001 | 9 | SCI-US52-32.686 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2002-01-08 | 2007-01-08
885 | 13226 | 2001-0118 | 2001 | 9 | SCI-US52-32.686 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2002-01-08 | 2007-01-08
885 | 13226 | 2001-0118 | 2001 | 9 | SCI-US52-32.686 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2002-01-08 | 2007-01-08
885 | 13226 | 2001-0118 | 2001 | 9 | SCI-US52-32.686 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2002-01-08 | 2007-01-08
894 | 13226 | 2001-0118 | 2001 | 9 | SCI-US52-32.686 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-01-08 | 2007-01-08
894 | 18385 | 2001-0119 | 2001 | 4 | SUM-IR77-024.19 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2003-06-10 | 2010-06-10
894 | 18385 | 2001-0119 | 2001 | 4 | SUM-IR77-024.19 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-06-10 | 2010-06-10
894 | 22496 | 2001-0135 | 2001 | 1 | WYA-US23-12.429 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-08-22 | 2009-08-22
880 | 16293 | 2001-0136 | 2001 | 5 | FAI-US33-007.31 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2003-11-14 | 2010-11-14
893 | 16293 | 2001-0136 | 2001 | 5 | FAI-US33-007.31 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2003-11-14 | 2010-11-14
885 | 18715 | 2001-0137 | 2001 | 4 | ATB-SR534-019.35 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-10-25 | 2006-10-25
885 | 18715 | 2001-0137 | 2001 | 4 | ATB-SR534-019.35 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-10-25 | 2006-10-25
885 | 18715 | 2001-0137 | 2001 | 4 | ATB-SR534-019.35 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-10-25 | 2006-10-25
885 | 18715 | 2001-0137 | 2001 | 4 | ATB-SR534-019.35 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-10-25 | 2006-10-25
894 | 18715 | 2001-0137 | 2001 | 4 | ATB-SR534-019.35 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-10-25 | 2006-10-25
893 | 16511 | 2001-0140 | 2001 | 6 | DEL-US23-010.15 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-12-18 | 2008-12-18
880 | 16281 | 2001-0141 | 2001 | 3 | ERI-US250-08.763 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-10-31 | 2009-10-31
880 | 6912 | 2001-0142 | 2001 | 6 | FAY-US35-007.51 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2003-08-01 | 2010-08-01
884 | 19738 | 2001-0145 | 2001 | 10 | MEG-SR124-031.57 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2003-06-25 | 2010-06-25
894 | 19738 | 2001-0145 | 2001 | 10 | MEG-SR124-031.57 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2003-06-25 | 2010-06-25
884 | 19738 | 2001-0145 | 2001 | 10 | MEG-SR124-031.57 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN | 2003-06-25 | 2010-06-25
446 | 17099 | 2001-0154 | 2001 | 7 | AUG-SR29-000.00 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2001-12-01 | 2004-12-01
885 | 17357 | 2001-0155 | 2001 | 8 | BUT-SR4-009.28 | SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY | 2001-10-26 | 2006-10-26
885 | 17357 | 2001-0155 | 2001 | 8 | BUT-SR4-009.28 | FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY | 2001-10-26 | 2006-10-26
885 | 17357 | 2001-0155 | 2001 | 8 | BUT-SR4-009.28 | FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY | 2001-10-26 | 2006-10-26
885 | 17357 | 2001-0155 | 2001 | 8 | BUT-SR4-009.28 | FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY | 2001-10-26 | 2006-10-26
893 | 8950 | 2001-0165 | 2001 | 4 | SUM-SR77-29.515 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2002-09-16 | 2009-09-16
883 | 22599 | 2001-0167 | 2001 | 3 | ASD-SR60-001.49 | CRACK SEALING WITH WARRANTY, MISC.: | 2001-09-27 | 2003-09-27
894 | 11858 | 2001-0178 | 2001 | 9 | SCI-US23-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-10-16 | 2013-10-16
884 | 10289 | 2001-0199 | 2001 | 1 | WYA-US30-28.009 | 260 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | Assumed Expired
894 | 10289 | 2001-0199 | 2001 | 1 | WYA-US30-28.009 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | Assumed Expired
894 | 10289 | 2001-0199 | 2001 | 1 | WYA-US30-28.009 | SPECIAL - HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | Assumed Expired
894 | 18224 | 2001-0200 | 2001 | 3 | ASD-US250-023.45 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-04-26 | 2009-04-26
894 | 12342 | 2001-0204 | 2001 | 12 | CUY-IR271-20.503 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2003-04-18 | 2010-04-18
880 | 19514 | 2001-0205 | 2001 | 12 | CUY-US422-018.53 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2002-11-12 | 2007-11-12
894 | 13147 | 2001-0206 | 2001 | 7 | DAR-SR705-015.99 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2001-11-23 | 2008-11-23
446 | 20985 | 2001-0214 | 2001 | 6 | UNI-US33-012.59 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2001-11-13 | 2004-11-13
882 | 22787 | 2001-0220 | 2001 | 2 | SEN-SR19-006.07 | SINGLE CHIP SEAL WITH WARRANTY | 2001-10-15 | 2004-10-15
446 | 21258 | 2001-0225 | 2001 | 6 | FRA-SR104-010.61 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY | 2001-09-20 | 2004-09-20
884 | 19718 | 2001-0229 | 2001 | 10 | MEG-SR124-022.72 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2004-10-14 | 2011-10-14
894 | 19718 | 2001-0229 | 2001 | 10 | MEG-SR124-022.72 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-10-14 | 2011-10-14
884 | 18288 | 2001-0246 | 2001 | 10 | ATH-US33-40.981 | 225 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2004-10-22 | 2011-10-22
894 | 18288 | 2001-0246 | 2001 | 10 | ATH-US33-40.981 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2004-10-22 | 2011-10-22
884 | 18288 | 2001-0246 | 2001 | 10 | ATH-US33-40.981 | 225 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN | 2004-10-22 | 2011-10-22
894 | 13166 | 2001-0251 | 2001 | 9 | JAC-SR279-000.71 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-07-23 | 2009-07-23
894 | 13974 | 2001-0256 | 2001 | 4 | MAH-IR76-000.86 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-12-08 | 2010-12-08
880 | 20229 | 2001-0282 | 2001 | 12 | MED-US42-001.89 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2002-11-19 | 2007-11-19
880 | 19768 | 2001-0291 | 2001 | 2 | WOO-IR75-000.00 | ASPHALT CONCRETE (5 YEAR WARRANTY) | 2002-01-17 | 2007-01-17
880 | 20228 | 2001-0309 | 2001 | 12 | LOR-SR10-000.00 | ASPHALT CONCRETE (5 YEAR WARRANTY) | Assumed Expired
448 | 16845 | 2001-0341 | 2001 | 7 | AUG-SR66-011.86 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY | 2001-10-19 | 2004-10-19
858 | 21811 | 2001-0362 | 2001 | 1 | WYA-US23-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2001-12-12 | 2004-12-12
884 | 19719 | 2001-0403 | 2001 | 10 | MEG-SR124-026.66 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2004-10-14 | 2011-10-14
894 | 19719 | 2001-0403 | 2001 | 10 | MEG-SR124-026.66 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-10-14 | 2011-10-14
884 | 19719 | 2001-0403 | 2001 | 10 | MEG-SR124-026.66 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN | 2004-10-14 | 2011-10-14
893 | 19303 | 2001-0424 | 2001 | 1 | ALL-SR65-011.37 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-07-24 | 2009-07-24
884 | 18287 | 2001-0425 | 2001 | 10 | ATH-US33-30.981 | 225 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2005-02-23 | 2012-02-23
884 | 18287 | 2001-0425 | 2001 | 10 | ATH-US33-30.981 | 250 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2005-02-23 | 2012-02-23
894 | 18287 | 2001-0425 | 2001 | 10 | ATH-US33-30.981 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-02-23 | 2012-02-23
884 | 18287 | 2001-0425 | 2001 | 10 | ATH-US33-30.981 | 225 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN | 2005-02-23 | 2012-02-23
894 | 17106 | 2001-0430 | 2001 | 8 | WAR-SR73-008.79 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-08-07 | 2009-08-07
894 | 15438 | 2001-0446 | 2001 | 9 | JAC-SR32-27.631 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-04-24 | 2013-04-24
880 | 16367 | 2001-0454 | 2001 | 4 | STA-IR77-017.61 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2003-10-07 | 2010-10-07
894 | 16367 | 2001-0454 | 2001 | 4 | STA-IR77-017.61 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-10-07 | 2010-10-07
858 | 17448 | 2001-0468 | 2001 | 7 | CLA-IR70-006.34 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2005-02-08 | 2012-02-08
894 | 17448 | 2001-0468 | 2001 | 7 | CLA-IR70-006.34 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-02-08 | 2012-02-08
880 | 14016 | 2001-0517 | 2001 | 3 | WAY-IR71-000.28 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2002-11-22 | 2009-11-22
894 | 14016 | 2001-0517 | 2001 | 3 | WAY-IR71-000.28 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2002-11-22 | 2009-11-22
893 | 11933 | 2001-0540 | 2001 | 4 | MAH-US224-000.08 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-04-29 | 2010-04-29
893 | 18712 | 2001-0543 | 2001 | 4 | TRU-SR5-006.45 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-07-14 | 2010-07-14
858 | 18249 | 2001-0560 | 2001 | 7 | MOT-IR75-29.305 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2005-07-18 | 2012-07-18
880 | 18249 | 2001-0560 | 2001 | 7 | MOT-IR75-29.305 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2005-07-18 | 2012-07-18
885 | 18722 | 2001-3000 | 2001 | 4 | MAH-SR11-016.04 | SPECIAL - SURFACE PREPARATION, FIELD PAINTING OF EX. STEEL W/PRIME, INTERMEDIATE & FINISH COATS W/WARRANTY AS PER SS885 | 2002-11-08 | 2007-11-08
894 | 18722 | 2001-3000 | 2001 | 4 | MAH-SR11-016.04 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2002-11-08 | 2007-11-08
894 | 21053 | 2001-3001 | 2001 | 10 | ATH-US33-010.41 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2002-10-18 | 2009-10-18
885 | 22163 | 2001-3002 | 2001 | 4 | TRU-IR80-009.08 | SPECIAL - SURFACE PREPARATION, FIELD PAINTING OF EX. STEEL W/PRIME, INTERMEDIATE & FINISH COATS W/WARRANTY AS PER SS885 | 2002-07-10 | 2007-07-10
892 | 22163 | 2001-3002 | 2001 | 4 | TRU-IR80-009.08 | SPECIAL - BRIDGE DECK CONCRETE OVERLAYS WITH WARRANTY | 2002-07-10 | 2007-07-10
892 | 22163 | 2001-3002 | 2001 | 4 | TRU-IR80-009.08 | MICRO-SILICA MODIFIED CONCRETE OVERLAY (VARIABLE THICKNESS), MATERIAL ONLY WITH WARRANTY | 2002-07-10 | 2007-07-10
880 | 12761 | 2001-3003 | 2001 | 11 | TUS-IR77-003.94 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) | 2002-08-26 | 2009-08-26
885 | 19899 | 2001-3005 | 2001 | 4 | ATB-SR11-023.33 | SPECIAL - SURFACE PREPARATION, FIELD PAINTING OF EX. STEEL W/PRIME, INTERMEDIATE & FINISH COATS W/WARRANTY AS PER SS885 | 2002-05-29 | 2007-05-29
894 | 19899 | 2001-3005 | 2001 | 4 | ATB-SR11-023.33 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2002-05-29 | 2007-05-29
894 | 20761 | 2001-3007 | 2001 | 2 | SAN-US6-014.76 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2002-01-07 | 2009-01-07
894 | 20762 | 2001-3008 | 2001 | 2 | SAN-US20-014.86 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2002-01-07 | 2009-01-07
880 | 19705 | 2001-3009 | 2001 | 8 | HAM-IR71-011.08 | SPECIAL - ASPHALT PAVEMENT (5 YEAR WARRANTY) | 2002-03-14 | 2007-03-14
885 | 19705 | 2001-3009 | 2001 | 8 | HAM-IR71-011.08 | SPECIAL - SURFACE PREPARATION, FIELD PAINTING OF EX. STEEL W/PRIME, INTERMEDIATE & FINISH COATS W/WARRANTY AS PER SS885 | 2002-03-14 | 2007-03-14
885 | 19854 | 2001-3010 | 2001 | 4 | POR-US224-000.00 | SPECIAL - SURFACE PREPARATION, FIELD PAINTING OF EX. STEEL W/PRIME, INTERMEDIATE & FINISH COATS W/WARRANTY AS PER SS885 | 2002-07-30 | 2007-07-30
892 | 19854 | 2001-3010 | 2001 | 4 | POR-US224-000.00 | SPECIAL - BRIDGE DECK CONCRETE OVERLAYS WITH WARRANTY | 2002-07-30 | 2007-07-30
894 | 19854 | 2001-3010 | 2001 | 4 | POR-US224-000.00 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2002-07-30 | 2007-07-30
892 | 19854 | 2001-3010 | 2001 | 4 | POR-US224-000.00 | MICRO-SILICA MODIFIED CONCRETE OVERLAY (VARIABLE THICKNESS), MATERIAL ONLY WITH WARRANTY | 2002-07-30 | 2007-07-30
889 | 18391 | 2002-0007 | 2002 | 12 | LAK-SR2-013.05 | SAWING AND SEALING ASPHALT CONCRETE PAVEMENT JOINTS WITH WARRANTY | 2004-01-12 | 2006-01-12
894 | 11385 | 2002-0026 | 2002 | 3 | LOR-IR90-013.20 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2003-11-19 | 2010-11-19
893 | 23839 | 2002-0032 | 2002 | 8 | HAM-IR275-029.79 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-12-15 | 2010-12-15
880 | 16284 | 2002-0033 | 2002 | 3 | CRA-US30-33.500 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-08-04 | 2012-08-04
894 | 16284 | 2002-0033 | 2002 | 3 | CRA-US30-33.500 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-08-04 | 2012-08-04
894 | 4354 | 2002-0035 | 2002 | 6 | FRA-IR670-002.61 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-09-19 | 2010-09-19
880 | 16283 | 2002-0036 | 2002 | 3 | CRA-US30-24.000 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-08-04 | 2012-08-04
894 | 16283 | 2002-0036 | 2002 | 3 | CRA-US30-24.000 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-08-04 | 2012-08-04
894 | 18986 | 2002-0040 | 2002 | 10 | GAL-SR279-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-11-05 | 2009-11-05
884 | 18687 | 2002-0045 | 2002 | 4 | POR-IR76-001.09 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2003-08-22 | 2010-08-22
884 | 18687 | 2002-0045 | 2002 | 4 | POR-IR76-001.09 | 14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2003-08-22 | 2010-08-22
894 | 18687 | 2002-0045 | 2002 | 4 | POR-IR76-001.09 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-08-22 | 2010-08-22
894 | 13281 | 2002-0068 | 2002 | 5 | FAI-US33-000.41 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-10-05 | 2011-10-05
880 | 4666 | 2002-0069 | 2002 | 6 | FRA-IR670-003.17 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2003-09-19 | 2010-09-19
894 | 18721 | 2002-0070 | 2002 | 4 | ATB-IR90-019.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-11-03 | 2010-11-03
880 | 18721 | 2002-0070 | 2002 | 4 | ATB-IR90-019.56 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2003-11-03 | 2010-11-03
894 | 18688 | 2002-0080 | 2002 | 4 | STA-US30-029.58 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-10-23 | 2009-10-23
894 | 16294 | 2002-0110 | 2002 | 5 | FAI-US33-013.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-11-22 | 2011-11-22
990 | 16294 | 2002-0110 | 2002 | 5 | FAI-US33-013.25 | FORCE ACCOUNT | 2004-11-22 | 2011-11-22
880 | 16294 | 2002-0110 | 2002 | 5 | FAI-US33-013.25 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2004-11-22 | 2011-11-22
894 | 19433 | 2002-0119 | 2002 | 5 | GUE-SR209-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-09-30 | 2009-09-30
894 | 13481 | 2002-0122 | 2002 | 10 | NOB-SR821-007.86 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-10-31 | 2009-10-31
894 | 19491 | 2002-0144 | 2002 | 3 | LOR-SR57-018.16 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-01-04 | 2012-01-04
894 | 16670 | 2002-0150 | 2002 | 6 | FRA-IR270-048.47 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-11-25 | 2010-11-25
893 | 10914 | 2002-0172 | 2002 | 8 | CLE-IR275-009.79 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-11-01 | 2010-11-01
894 | 19059 | 2002-0196 | 2002 | 10 | HOC-SR56-012.55 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-09-26 | 2010-09-26
881 | 22753 | 2002-0222 | 2002 | 2 | OTT-SR163-004.01 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2003-01-30 | 2006-01-30
882 | 22755 | 2002-0224 | 2002 | 2 | SEN-SR18-023.56 | SINGLE CHIP SEAL WITH WARRANTY | 2003-01-30 | 2006-01-30
858 | 19799 | 2002-0229 | 2002 | 7 | MER-US127-014.67 | ASPHALT CONCRETE SURFACE COURSE, 9.5 MM, TYPE B (448) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2002-10-25 | 2005-10-25
894 | 22114 | 2002-0231 | 2002 | 4 | POR-SR82-010.67 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2002-12-23 | 2009-12-23
888 | 22698 | 2002-0349 | 2002 | 10 | ATH-US33-001.87 | PORTLAND CEMENT CONCRETE PAVEMENT, 8" THICK (NON-REINFORCED PER 452) | Assumed Expired
893 | 19920 | 2002-0395 | 2002 | 4 | TRU-SR45-020.18 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-06-25 | 2012-06-25
894 | 8861 | 2002-0421 | 2002 | 2 | HAN-IR75-024.02 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-05-05 | 2012-05-05
880 | 16295 | 2002-0446 | 2002 | 5 | FAI-US33-017.44 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-04-07 | 2012-04-07
855 | 21609 | 2002-0467 | 2002 | 4 | STA-IR77-012.76 | 4" ASPHALT TREATED FREE DRAINING BASE | 2003-10-31 | 2010-10-31
880 | 21609 | 2002-0467 | 2002 | 4 | STA-IR77-012.76 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2003-10-31 | 2010-10-31
894 | 21609 | 2002-0467 | 2002 | 4 | STA-IR77-012.76 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-10-31 | 2010-10-31
880 | 18393 | 2002-0485 | 2002 | 12 | CUY-IR480-012.76 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2003-11-19 | 2010-11-19
894 | 18579 | 2002-0486 | 2002 | 3 | RIC-US30-011.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | Non performed
442 | 23882 | 2002-0488 | 2002 | 6 | FRA-IR70-011.21 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2003-08-27 | 2006-08-27
880 | 16282 | 2002-0509 | 2002 | 3 | CRA-US30-15.865 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-08-04 | 2012-08-04
894 | 16282 | 2002-0509 | 2002 | 3 | CRA-US30-15.865 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-08-04 | 2012-08-04
858 | 19673 | 2002-0534 | 2002 | 12 | CUY-IR90-029.92 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2005-11-01 | 2008-11-01
894 | 19951 | 2002-0545 | 2002 | 4 | SUM-SR21-000.26 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2003-11-03 | 2010-11-03
894 | 17461 | 2002-0569 | 2002 | 7 | SHE-IR75-002.35 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | Assumed Expired
894 | 22174 | 2002-3000 | 2002 | 4 | ATB-SR11-025.16 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2004-09-05 | 2011-09-05
894 | 22229 | 2002-3001 | 2002 | 4 | SUM-IR77-015.47 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2003-08-31 | 2010-08-31
894 | 18718 | 2002-3004 | 2002 | 4 | SUM-SR21-001.79 | SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY | 2003-09-12 | 2010-09-12
880 | 20996 | 2002-3008 | 2002 | 11 | TUS-IR77-007.55 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) | 2004-05-15 | 2011-05-15
880 | 16992 | 2002-8005 | 2002 | 6 | FRA-IR670-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2003-10-22 | 2010-10-22
880 | 8314 | 2003-0001 | 2003 | 5 | LIC-SR79-006.66 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-08-23 | 2012-08-23
880 | 22261 | 2003-0004 | 2003 | 4 | ATB-IR90-0000.0 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2004-10-25 | 2011-10-25
880 | 23057 | 2003-0046 | 2003 | 5 | FAI-US33-019.79 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-10-26 | 2012-10-26
894 | 23057 | 2003-0046 | 2003 | 5 | FAI-US33-019.79 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-10-26 | 2012-10-26
882 | 24118 | 2003-0061 | 2003 | 2 | D02-SR0-000.00 | SINGLE CHIP SEAL WITH WARRANTY | 2003-07-31 | 2006-07-31
880 | 23129 | 2003-0080 | 2003 | 12 | LAK-IR90-006.71 | ASPHALT CONCRETE (7 YEAR WARRANTY) | Assumed Expired
893 | 21012 | 2003-0091 | 2003 | 8 | BUT-SR73-004.44 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-09-26 | 2010-09-26
894 | 19070 | 2003-0100 | 2003 | 7 | MOT-IR75-31.842 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-08-04 | 2012-08-04
894 | 22359 | 2003-0107 | 2003 | 6 | FRA-IR270-004.97 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-06-24 | 2011-06-24
442 | 15659 | 2003-0117 | 2003 | 1 | PAU-US30-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2003-08-21 | 2006-08-21
884 | 22364 | 2003-0118 | 2003 | 4 | POR-SR43-008.14 | 9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2004-06-25 | 2011-06-25
894 | 22364 | 2003-0118 | 2003 | 4 | POR-SR43-008.14 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2004-06-25 | 2011-06-25
893 | 20337 | 2003-0119 | 2003 | 8 | PRE-US127-010.51 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2003-09-26 | 2010-09-26
442 | 22704 | 2003-0122 | 2003 | 2 | WOO-IR75-032.68 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-01-12 | 2007-01-12
442 | 22704 | 2003-0122 | 2003 | 2 | WOO-IR75-032.68 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2004-01-12 | 2007-01-12
894 | 6225 | 2003-0134 | 2003 | 6 | FAY-IR71-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-07-21 | 2011-07-21
894 | 6225 | 2003-0134 | 2003 | 6 | FAY-IR71-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2004-07-21 | 2011-07-21
893 | 6225 | 2003-0134 | 2003 | 6 | FAY-IR71-000.00 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2004-07-21 | 2011-07-21
880 | 6225 | 2003-0134 | 2003 | 6 | FAY-IR71-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2004-07-21 | 2011-07-21
880 | 6225 | 2003-0134 | 2003 | 6 | FAY-IR71-000.00 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) | 2004-07-21 | 2011-07-21
893 | 20400 | 2003-0142 | 2003 | 8 | HAM-SR128-010.06 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2003-10-06 | 2010-10-06
880 | 4804 | 2003-0154 | 2003 | 9 | SCI-SR335-003.78 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-05-27 | 2012-05-27
894 | 11723 | 2003-0207 | 2003 | 5 | GUE-SR209-011.50 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-11-18 | 2011-11-18
893 | 17621 | 2003-0260 | 2003 | 8 | HAM-US22-011.40 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-11-03 | 2012-11-03
442 | 24711 | 2003-0268 | 2003 | 9 | ROS-US35-010.20 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2003-10-17 | 2006-10-17
894 | 19642 | 2003-0285 | 2003 | 9 | LAW-SR7-007.25 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2007-11-21 | 2014-11-21
880 | 19642 | 2003-0285 | 2003 | 9 | LAW-SR7-007.25 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-11-21 | 2014-11-21
854 | 75269 | 2003-0326 | 2003 | 11 | CAR-SR39-010.23 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2004-01-30 | 2007-01-30
880 | 20410 | 2003-0333 | 2003 | 4 | STA-IR77-009.46 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2005-11-16 | 2012-11-16
894 | 20410 | 2003-0333 | 2003 | 4 | STA-IR77-009.46 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-11-16 | 2012-11-16
854 | 75427 | 2003-0338 | 2003 | 7 | SHE-IR75-011.49 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY | 2003-09-25 | 2006-09-25
874 | 75429 | 2003-0339 | 2003 | 7 | SHE-IR75-016.05 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY | 2003-09-25 | 2006-09-25
881 | 75430 | 2003-0342 | 2003 | 7 | AUG-IR75-000.00 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2003-09-11 | 2006-09-11
882 | 24647 | 2003-0351 | 2003 | 3 | D03-SR0-000000 | SINGLE CHIP SEAL WITH WARRANTY | 2003-09-02 | 2005-09-02
881 | 24646 | 2003-0352 | 2003 | 3 | D03-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2003-10-08 | 2005-10-08
882 | 25832 | 2003-0398 | 2003 | 9 | SCI-SR348-000.00 | SINGLE CHIP SEAL WITH WARRANTY | 2003-09-26 | 2006-09-26
442 | 25174 | 2003-0407 | 2003 | 9 | SCI-US52-031.89 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2003-10-24 | 2008-10-24
881 | 24117 | 2003-0453 | 2003 | 2 | D02-VA0-000000 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2004-11-15 | 2007-11-15
442 | 21452 | 2003-0456 | 2003 | 11 | TUS-IR77-020.73 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2004-09-13 | 2007-09-13
884 | 16671 | 2003-0463 | 2003 | 6 | FRA-IR270-000.60 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN | 2004-11-23 | 2011-11-23
884 | 18696 | 2003-0464 | 2003 | 4 | MAH-IR76-003.08 | 11" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2005-12-08 | 2012-12-08
884 | 18696 | 2003-0464 | 2003 | 4 | MAH-IR76-003.08 | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2005-12-08 | 2012-12-08
880 | 18632 | 2003-0465 | 2003 | 3 | RIC-IR71-006.39 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2004-11-15 | 2011-11-15
894 | 18632 | 2003-0465 | 2003 | 3 | RIC-IR71-006.39 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2004-11-15 | 2011-11-15
442 | 23728 | 2003-0476 | 2003 | 2 | SAN-US6-014.61 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2005-09-12 | 2008-09-12
856 | 23728 | 2003-0476 | 2003 | 2 | SAN-US6-014.61 | STONE MASTIC ASPHALT CONCRETE SURFACE COURSE (PG76-22M) WITH SUPPLEMENT 1059 WARRANTY | 2005-09-12 | 2008-09-12
882 | 75163 | 2003-0479 | 2003 | 2 | D02-VA0-000000 | SINGLE CHIP SEAL WITH WARRANTY | 2004-07-29 | 2007-07-29
442 | 21722 | 2003-0494 | 2003 | 10 | HOC-US33-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-06-29 | 2007-06-29
856 | 25431 | 2003-0496 | 2003 | 2 | SAN-US20-000.02 | STONE MATRIX ASPHALT CONCRETE, 12.5MM, PG76-22M, (446) | 2005-09-08 | 2012-09-08
893 | 5872 | 2003-0509 | 2003 | 8 | BUT-SR129-014.25 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2006-11-04 | 2013-11-04
894 | 11044 | 2003-0511 | 2003 | 4 | TRU-SR82-025.24 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-11-18 | 2012-11-18
894 | 21004 | 2003-0534 | 2003 | 4 | POR-IR76-009.50 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2002-07-30 | 2009-07-30
894 | 21004 | 2003-0534 | 2003 | 4 | POR-IR76-009.50 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2002-07-30 | 2009-07-30
858 | 12725 | 2003-0536 | 2003 | 7 | MOT-SR4-019.14 | ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446), AS PER PLAN | Assumed Expired
442 | 21633 | 2003-0543 | 2003 | 5 | LIC-IR70-015.74 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-09-08 | 2007-09-08
894 | 13421 | 2003-0565 | 2003 | 5 | LIC-US40-012.63 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-04-30 | 2011-04-30
442 | 16073 | 2003-0569 | 2003 | 1 | WYA-US23-010.24 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-12-20 | 2007-12-20
442 | 75437 | 2003-0580 | 2003 | 9 | PIK-US23-005.27 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-08-18 | 2007-08-18
882 | 75437 | 2003-0580 | 2003 | 9 | PIK-US23-005.27 | SINGLE CHIP SEAL WITH WARRANTY | 2004-08-18 | 2007-08-18
894 | 19627 | 2003-0588 | 2003 | 5 | GUE-SR723-000.38 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2004-08-13 | 2011-08-13
442 | 21481 | 2003-0608 | 2003 | 9 | SCI-US52-015.50 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-11-23 | 2007-11-23
893 | 22340 | 2004-0002 | 2004 | 4 | ATB-US20-002.01 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-07-08 | 2012-07-08
442 | 21425 | 2004-0010 | 2004 | 9 | LAW-US52-011.85 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-10-20 | 2007-10-20
882 | 21425 | 2004-0010 | 2004 | 9 | LAW-US52-011.85 | SINGLE CHIP SEAL WITH WARRANTY | 2004-10-20 | 2007-10-20
442 | 17094 | 2004-0012 | 2004 | 7 | MER-SR29-013.32 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2004-11-16 | 2007-11-16
882 | 76027 | 2004-0035 | 2004 | 9 | JAC-SR233-000.14 | DOUBLE CHIP SEAL WITH WARRANTY | 2004-07-24 | 2007-07-24
881 | 76028 | 2004-0038 | 2004 | 9 | PIK-SR220-009.70 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2004-05-17 | 2007-05-17
894 | 25880 | 2004-0044 | 2004 | 3 | WAY-US30-011.86 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-05-10 | 2013-05-10
881 | 24671 | 2004-0047 | 2004 | 4 | D04-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2004-08-24 | 2006-08-24
881 | 24560 | 2004-0061 | 2004 | 2 | D02-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2004-08-31 | 2007-08-31
880 | 18631 | 2004-0082 | 2004 | 3 | WAY-US30-009.18 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2004-11-24 | 2011-11-24
894 | 18631 | 2004-0082 | 2004 | 3 | WAY-US30-009.18 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2004-11-24 | 2011-11-24
894 | 77003 | 2004-0163 | 2004 | 6 | FRA-SR161-25.900 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2007-10-24 | 2014-10-24
894 | 77003 | 2004-0163 | 2004 | 6 | FRA-SR161-25.900 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2007-10-24 | 2014-10-24
893 | 19723 | 2004-0164 | 2004 | 8 | BUT-SR4-022.59 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2004-12-16 | 2011-12-16
448 | 25883 | 2004-0167 | 2004 | 6 | D06-VA0-000000 | ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY | 2004-09-27 | 2007-09-27
881 | 25883 | 2004-0167 | 2004 | 6 | D06-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2004-09-27 | 2007-09-27
881 | 76935 | 2004-0231 | 2004 | 5 | MUS-IR70-000.76 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2005-10-06 | 2008-10-06
881 | 76935 | 2004-0231 | 2004 | 5 | MUS-IR70-000.76 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2005-10-06 | 2008-10-06
990 | 76935 | 2004-0231 | 2004 | 5 | MUS-IR70-000.76 | AGREED LUMP SUM | 2005-10-06 | 2008-10-06
881 | 25403 | 2004-0240 | 2004 | 7 | LOG-US33-010.71 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | Assumed Expired
881 | 25403 | 2004-0240 | 2004 | 7 | LOG-US33-010.71 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
881 | 75955 | 2004-0243 | 2004 | 7 | MOT-IR75-000.00 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
894 | 77118 | 2004-0294 | 2004 | 6 | CLA-IR70-025.11 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | Voided
880 | 77118 | 2004-0294 | 2004 | 6 | CLA-IR70-025.11 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | Voided
894 | 23675 | 2004-0302 | 2004 | 4 | MAH-IR680-009.92 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-12-03 | 2012-12-03
880 | 23482 | 2004-0350 | 2004 | 4 | STA-IR77-017.93 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2007-09-06 | 2014-09-06
894 | 13411 | 2004-0353 | 2004 | 5 | COS-US36-007.01 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-11-04 | 2012-11-04
881 | 19431 | 2004-0355 | 2004 | 6 | DEL-US36-016.57 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2005-10-02 | 2008-10-02
854 | 76991 | 2004-0356 | 2004 | 6 | D06-VA0-000.00 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY | 2004-09-21 | 2007-09-21
874 | 76991 | 2004-0356 | 2004 | 6 | D06-VA0-000.00 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2004-09-21 | 2007-09-21
874 | 76686 | 2004-0364 | 2004 | 7 | MOT-IR75-003.77 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired
854 | 76818 | 2004-0376 | 2004 | 3 | LOR-US20-013.57 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired
874 | 76817 | 2004-0380 | 2004 | 3 | WAY-US30-023.16 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired
881 | 76820 | 2004-0381 | 2004 | 3 | WAY-SR3-010.13 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
882 | 24651 | 2004-0419 | 2004 | 3 | D03-SR303-000.00 | SINGLE CHIP SEAL WITH WARRANTY | Assumed Expired
881 | 24650 | 2004-0421 | 2004 | 3 | D03-US30-003.82 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
442 | 19893 | 2004-0434 | 2004 | 9 | ROS-SR104-008.64 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2004-12-15 | 2007-12-15
881 | 22511 | 2004-0456 | 2004 | 10 | NOB-IR77-001.56 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2005-04-25 | 2008-04-25
881 | 21744 | 2004-0502 | 2004 | 12 | CUY-IR71-005.72 | MICROSURFACING WITH WARRANTY, SINGLE COURSE, AS PER PLAN | Assumed Expired
881 | 21744 | 2004-0502 | 2004 | 12 | CUY-IR71-005.72 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE, AS PER PLAN | Assumed Expired
442 | 23405 | 2004-0511 | 2004 | 9 | ROS-US35-022.72 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2006-01-04 | 2009-01-04
442 | 23805 | 2004-0517 | 2004 | 3 | ERI-SR2-030.46 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired
442 | 21730 | 2004-0520 | 2004 | 9 | JAC-SR32-017.41 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2005-11-08 | 2008-11-08
882 | 21730 | 2004-0520 | 2004 | 9 | JAC-SR32-017.41 | SINGLE CHIP SEAL WITH WARRANTY | 2005-11-08 | 2008-11-08
442 | 77459 | 2004-0522 | 2004 | 9 | ROS-US23-009.36 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2005-06-22 | 2008-06-22
894 | 21610 | 2004-0532 | 2004 | 4 | STA-IR77-014.80 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-12-13 | 2012-12-13
880 | 21610 | 2004-0532 | 2004 | 4 | STA-IR77-014.80 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2005-12-13 | 2012-12-13
880 | 18492 | 2004-0533 | 2004 | 9 | ROS-SR207-000.00 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-10-25 | 2014-10-25
894 | 18492 | 2004-0533 | 2004 | 9 | ROS-SR207-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2007-10-25 | 2014-10-25
894 | 18492 | 2004-0533 | 2004 | 9 | ROS-SR207-000.00 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2007-10-25 | 2014-10-25
892 | 19069 | 2004-0555 | 2004 | 7 | MOT-IR70-22.890 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | Assumed Expired
893 | 75122 | 2004-0559 | 2004 | 8 | HAM-SR561-007.00 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-11-07 | 2012-11-07
442 | 24441 | 2004-0562 | 2004 | 7 | MOT-IR75-006.16 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
442 | 21801 | 2004-0581 | 2004 | 8 | HAM-IR74-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired
880 | 16372 | 2004-0582 | 2004 | 4 | SUM-IR77-001.40 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2005-10-11 | 2012-10-11
894 | 16372 | 2004-0582 | 2004 | 4 | SUM-IR77-001.40 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-10-11 | 2012-10-11
880 | 19956 | 2004-0583 | 2004 | 3 | MRW-IR71-019.54 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-11-12 | 2013-11-12
894 | 19956 | 2004-0583 | 2004 | 3 | MRW-IR71-019.54 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2006-11-12 | 2013-11-12
898 | 23956 | 2004-0584 | 2004 | 2 | OTT-SR2-028.47 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) | 2007-06-30 | 2014-06-30
894 | 21005 | 2004-0633 | 2004 | 4 | TRU-SR5-012.50 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-11-07 | 2012-11-07
442 | 76564 | 2004-3002 | 2004 | 6 | FAY-SR41-022.18 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | Assumed Expired
881 | 77577 | 2004-5020 | 2004 | 7 | MOT-IR75-010.44 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE, AS PER PLAN | Assumed Expired
442 | 17097 | 2004-8000 | 2004 | 7 | CLA-SR4-005.56 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2005-06-20 | 2012-06-20
894 | 17097 | 2004-8000 | 2004 | 7 | CLA-SR4-005.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-06-20 | 2012-06-20
880 | 77302 | 2005-0003 | 2005 | 1 | HAN-US30-04.828 | SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY) | 2007-11-09 | 2014-11-09
880 | 77302 | 2005-0003 | 2005 | 1 | HAN-US30-04.828 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-11-09 | 2014-11-09
442 | 21700 | 2005-0006 | 2005 | 12 | CUY-IR90-004.57 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
884 | 25523 | 2005-0007 | 2005 | 8 | CLE-IR275-013.79 | 10" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-10-31 | 2013-10-31
884 | 25523 | 2005-0007 | 2005 | 8 | CLE-IR275-013.79 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-10-31 | 2013-10-31
884 | 25523 | 2005-0007 | 2005 | 8 | CLE-IR275-013.79 | PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), MISC.: | 2006-10-31 | 2013-10-31
893 | 25523 | 2005-0007 | 2005 | 8 | CLE-IR275-013.79 | CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-10-31 | 2013-10-31
881 | 77701 | 2005-0026 | 2005 | 10 | VIN-SR124-005.74 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
881 | 77700 | 2005-0028 | 2005 | 10 | ATH-SR144-000.00 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
882 | 77301 | 2005-0042 | 2005 | 9 | LAW-SR141-016.37 | SINGLE CHIP SEAL WITH WARRANTY | 2005-07-21 | 2008-07-21
894 | 14017 | 2005-0048 | 2005 | 3 | WAY-IR0071-007.04 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2006-12-16 | 2013-12-16
894 | 14017 | 2005-0048 | 2005 | 3 | WAY-IR0071-007.04 | SPECIAL - HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-12-16 | 2013-12-16
880 | 14017 | 2005-0048 | 2005 | 3 | WAY-IR0071-007.04 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-12-16 | 2013-12-16
880 | 24355 | 2005-0077 | 2005 | 3 | ASD-US250-012.56 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2005-12-01 | 2012-12-01
880 | 24591 | 2005-0108 | 2005 | 4 | ATB-IR90-003.70 | ASPHALT CONCRETE (7 YEAR WARRANTY) | Voided
884 | 24591 | 2005-0108 | 2005 | 4 | ATB-IR90-003.70 | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | Voided
881 | 25886 | 2005-0111 | 2005 | 6 | D06-VA0-000000 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2005-09-12 | 2008-09-12
881 | 25886 | 2005-0111 | 2005 | 6 | D06-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2005-09-12 | 2008-09-12
882 | 25886 | 2005-0111 | 2005 | 6 | D06-VA0-000000 | SINGLE CHIP SEAL WITH WARRANTY | 2005-09-12 | 2008-09-12
894 | 19940 | 2005-0122 | 2005 | 4 | STA-SR183-003.26 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2005-12-27 | 2012-12-27
854 | 76969 | 2005-0127 | 2005 | 2 | D02-VA0-000000 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY | 2005-08-24 | 2008-08-24
442 | 23005 | 2005-0150 | 2005 | 9 | ROS-US23-016.34 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2006-01-04 | 2009-01-04
894 | 23565 | 2005-0173 | 2005 | 10 | WAS-US50-004.40 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2008-05-13 | 2015-05-13
881 | 78479 | 2005-0177 | 2005 | 9 | BRO-SR32-011.11 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2005-06-24 | 2008-06-24
881 | 78479 | 2005-0177 | 2005 | 9 | BRO-SR32-011.11 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2005-06-24 | 2008-06-24
894 | 25714 | 2005-0274 | 2005 | 6 | FRA-IR70-007.94 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2005-09-22 | 2012-09-22
442 | 13389 | 2005-0280 | 2005 | 9 | JAC-US35-013.23 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2005-11-08 | 2008-11-08
880 | 4082 | 2005-0312 | 2005 | 3 | MED-SR18-016.03 | ASPHALT CONCRETE (7 YEAR WARRANTY) | Non performed
894 | 21450 | 2005-0316 | 2005 | 4 | SUM-IR271-008.02 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2008-10-24 | 2015-10-24
880 | 14018 | 2005-0343 | 2005 | 3 | MED-IR71-009.56 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-12-14 | 2013-12-14
894 | 14018 | 2005-0343 | 2005 | 3 | MED-IR71-009.56 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2006-12-14 | 2013-12-14
894 | 14018 | 2005-0343 | 2005 | 3 | MED-IR71-009.56 | SPECIAL - HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-12-14 | 2013-12-14
894 | 7904 | 2005-0358 | 2005 | 4 | TRU-SR534-015.06 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-05-10 | 2013-05-10
854 | 25887 | 2005-0381 | 2005 | 6 | D06-VA0-000000 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY | 2006-08-11 | 2009-08-11
892 | 22478 | 2005-0390 | 2005 | 4 | POR-SR14-013.39 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2007-08-13 | 2014-08-13
442 | 21802 | 2005-0415 | 2005 | 9 | PIK-US23-003.50 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2006-11-22 | 2009-11-22
882 | 25751 | 2005-0420 | 2005 | 3 | D03-SR0-000000 | SINGLE CHIP SEAL WITH WARRANTY | Assumed Expired
881 | 25750 | 2005-0421 | 2005 | 3 | D03-SR0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
884 | 22935 | 2005-0465 | 2005 | 7 | MOT-IR70-017.04 | 14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-12-19 | 2013-12-19
892 | 22935 | 2005-0465 | 2005 | 7 | MOT-IR70-017.04 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2006-12-19 | 2013-12-19
892 | 22935 | 2005-0465 | 2005 | 7 | MOT-IR70-017.04 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2006-12-19 | 2013-12-19
892 | 15278 | 2005-0500 | 2005 | 8 | GRE-SR725-003.95 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2006-11-17 | 2008-11-17
882 | 78961 | 2005-0513 | 2005 | 9 | ROS-SR772-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2006-08-11 | 2009-08-11
884 | 5774 | 2005-0518 | 2005 | 12 | LAK-IR90-006.71 | 9.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-12-21 | 2013-12-21
884 | 5774 | 2005-0518 | 2005 | 12 | LAK-IR90-006.71 | 12.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-12-21 | 2013-12-21
884 | 5774 | 2005-0518 | 2005 | 12 | LAK-IR90-006.71 | 13.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-12-21 | 2013-12-21
892 | 23976 | 2005-0524 | 2005 | 8 | GRE-IR71-002.49 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2006-10-31 | 2008-10-31
881 | 24559 | 2005-0547 | 2005 | 2 | D02-SR0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2006-08-29 | 2009-08-29
892 | 24346 | 2005-0558 | 2005 | 7 | MIA-IR75-017.49 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired
880 | 20412 | 2005-0583 | 2005 | 4 | STA-IR77-010.33 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2006-12-13 | 2013-12-13
894 | 20412 | 2005-0583 | 2005 | 4 | STA-IR77-010.33 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2006-12-13 | 2013-12-13
894 | 20412 | 2005-0583 | 2005 | 4 | STA-IR77-010.33 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2006-12-13 | 2013-12-13
882 | 78962 | 2005-0588 | 2005 | 9 | ADA-SR73-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2006-08-10 | 2009-08-10
442 | 75476 | 2005-0607 | 2005 | 12 | CUY-IR480-021.88 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
442 | 19883 | 2005-0614 | 2005 | 9 | SCI-US23-002.39 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2006-12-12 | 2009-12-12
884 | 76160 | 2005-3000 | 2005 | 10 | WAS-IR77-006.59 | SPECIAL - PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-11-27 | 2013-11-27
884 | 76160 | 2005-3000 | 2005 | 10 | WAS-IR77-006.59 | 11" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2006-11-27 | 2013-11-27
884 | 6080 | 2006-0002 | 2006 | 4 | MAH-IR80-000.97 | 13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-09-15 | 2016-09-15
892 | 6080 | 2006-0002 | 2006 | 4 | MAH-IR80-000.97 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2009-09-15 | 2016-09-15
990 | 6080 | 2006-0002 | 2006 | 4 | MAH-IR80-000.97 | AGREED LUMP SUM | 2009-09-15 | 2016-09-15
892 | 75882 | 2006-0004 | 2006 | 8 | HAM-US22-015.84 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired
880 | 17067 | 2006-0036 | 2006 | 7 | MOT-US35-015.07 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2006-12-14 | 2013-12-14
880 | 24337 | 2006-0087 | 2006 | 1 | DEF-US24-007.96 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-11-07 | 2015-11-07
892 | 22517 | 2006-0095 | 2006 | 2 | LUC-IR475-010.90 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2006-11-20 | 2008-11-20
880 | 21751 | 2006-0117 | 2006 | 12 | CUY-IR480-015.81 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2007-04-10 | 2014-04-10
442 | 22218 | 2006-0122 | 2006 | 12 | CUY-IR480-019.23 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
442 | 25459 | 2006-0134 | 2006 | 9 | ROS-US35-004.38 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2006-12-18 | 2009-12-18
880 | 24486 | 2006-0150 | 2006 | 5 | FRA-SR161-023.20 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-10-21 | 2015-10-21
885 | 24486 | 2006-0150 | 2006 | 5 | FRA-SR161-023.20 | FINAL INSPECTION REPAIR | 2008-10-21 | 2015-10-21
894 | 24486 | 2006-0150 | 2006 | 5 | FRA-SR161-023.20 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2008-10-21 | 2015-10-21
880 | 16514 | 2006-0151 | 2006 | 4 | SUM-IR77-021.79 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-11-06 | 2015-11-06
894 | 16514 | 2006-0151 | 2006 | 4 | SUM-IR77-021.79 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2008-11-06 | 2015-11-06
885 | 18951 | 2006-0246 | 2006 | 3 | D03-VA0-000000 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed
885 | 18951 | 2006-0246 | 2006 | 3 | D03-VA0-000000 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed
885 | 18951 | 2006-0246 | 2006 | 3 | D03-VA0-000000 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed
885 | 18951 | 2006-0246 | 2006 | 3 | D03-VA0-000000 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Non performed
885 | 18951 | 2006-0246 | 2006 | 3 | D03-VA0-000000 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed
885 | 18951 | 2006-0246 | 2006 | 3 | D03-VA0-000000 | FINAL INSPECTION REPAIR | Non performed
442 | 21927 | 2006-0249 | 2006 | 9 | ROS-US35-014.41 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2007-07-03 | 2010-07-03
881 | 75780 | 2006-0285 | 2006 | 7 | MOT-IR70-000.00 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
880 | 75657 | 2006-0349 | 2006 | 3 | MED-IR71-006.06 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-12-14 | 2014-12-14
894 | 75657 | 2006-0349 | 2006 | 3 | MED-IR71-006.06 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2007-12-14 | 2014-12-14
442 | 80904 | 2006-0398 | 2006 | 9 | ROS-US35-017.83 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2007-07-03 | 2010-07-03
881 | 25753 | 2006-0409 | 2006 | 3 | D03-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
880 | 78569 | 2006-0413 | 2006 | 8 | CLI-SR73-012.03 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2007-11-12 | 2014-11-12
888 | 78569 | 2006-0413 | 2006 | 8 | CLI-SR73-012.03 | PORTLAND CEMENT CONCRETE PAVEMENT, 10" THICK (NON-REINFORCEDPER 452) | 2007-11-12 | 2014-11-12
880 | 22386 | 2006-0414 | 2006 | 8 | HAM-IR275-021.52 | ASPHALT CONCRETE (7 YEAR WARRANTY) | Non performed
880 | 22386 | 2006-0414 | 2006 | 8 | HAM-IR275-021.52 | ASPHALT CONCRETE (5 YEAR WARRANTY) | Non performed
882 | 25754 | 2006-0424 | 2006 | 3 | D03-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | Assumed Expired
442 | 19047 | 2006-0433 | 2006 | 1 | DEF-US24-012.03 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2008-12-06 | 2015-12-06
880 | 19047 | 2006-0433 | 2006 | 1 | DEF-US24-012.03 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-12-06 | 2015-12-06
442 | 25530 | 2006-0435 | 2006 | 9 | JAC-US35-001.69 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2007-12-14 | 2010-12-14
892 | 24508 | 2006-0467 | 2006 | 4 | SUM-SR8-015.63 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2009-11-06 | 2011-11-06
892 | 20422 | 2006-0541 | 2006 | 9 | SCI-SR140-012.80 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2007-05-12 | 2009-05-12
888 | 23060 | 2006-8005 | 2006 | 4 | ATB-LR0-000000 | PORTLAND CEMENT CONCRETE PAVEMENT, 8" THICK (NON-REINFORCED PER 452) | #N/A | #N/A
442 | 25520 | 2007-0009 | 2007 | 9 | LAW-US52-022.16 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2007-11-02 | 2010-11-02
442 | 77834 | 2007-0039 | 2007 | 9 | ROS-US23-017.03 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2007-11-19 | 2010-11-19
882 | 81128 | 2007-0053 | 2007 | 4 | TRU-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
424 | 25548 | 2007-0056 | 2007 | 11 | COL-US30-031.30 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
884 | 24336 | 2007-0078 | 2007 | 1 | PAU-US24-012.30 | 12.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-10-29 | 2019-10-29
884 | 19181 | 2007-0080 | 2007 | 12 | GEA-US422-018.31 | 11" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-10-09 | 2016-10-09
894 | 23752 | 2007-0089 | 2007 | 4 | MAH-US62-000.10 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2007-10-06 | 2009-10-06
882 | 25650 | 2007-0095 | 2007 | 2 | SEN-SR19-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
884 | 24334 | 2007-0110 | 2007 | 1 | PAU-US24-000.00 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2009-10-29 | 2016-10-29
882 | 25836 | 2007-0113 | 2007 | 9 | BRO-SR774-003.24 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2007-07-26 | 2009-07-26
424 | 81415 | 2007-0126 | 2007 | 9 | BRO-SR32-005.80 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | 2007-07-17 | 2010-07-17
880 | 77221 | 2007-0138 | 2007 | 5 | LIC-SR161-006.65 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-07-31 | 2016-07-31
894 | 77221 | 2007-0138 | 2007 | 5 | LIC-SR161-006.65 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN | 2009-07-31 | 2016-07-31
874 | 79313 | 2007-0142 | 2007 | 6 | D06-VA0-000000 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY | 2007-09-25 | 2010-09-25
880 | 23312 | 2007-0167 | 2007 | 2 | WOO-US20-012.36 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-12-21 | 2014-12-21
442 | 25462 | 2007-0176 | 2007 | 2 | OTT-SR2-023.27 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2008-05-09 | 2013-05-09
882 | 25806 | 2007-0266 | 2007 | 6 | DEL-SR656-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2008-09-08 | 2010-09-08
892 | 16054 | 2007-0277 | 2007 | 3 | LOR-SR301-40.673 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired
882 | 25600 | 2007-0280 | 2007 | 6 | PIC-SR316-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2007-09-11 | 2009-09-11
882 | 25600 | 2007-0280 | 2007 | 6 | PIC-SR316-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY | 2007-09-11 | 2009-09-11
888 | 19389 | 2007-0281 | 2007 | 8 | PRE-US127-018.81 | PORTLAND CEMENT CONCRETE PAVEMENT, 12" THICK (REINFORCED PER 451) | #N/A | #N/A
882 | 79949 | 2007-0340 | 2007 | 3 | D03-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
882 | 79949 | 2007-0340 | 2007 | 3 | D03-VA0-000000 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
880 | 75927 | 2007-0387 | 2007 | 7 | MOT-IR75-013.11 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-12-19 | 2015-12-19
990 | 75927 | 2007-0387 | 2007 | 7 | MOT-IR75-013.11 | AGREED UNIT PRICE | 2008-12-19 | 2015-12-19
882 | 81964 | 2007-0399 | 2007 | 2 | D02-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
882 | 78194 | 2007-0417 | 2007 | 9 | ADA-SR52-022.97 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2008-07-07 | 2010-07-07
894 | 23109 | 2007-0449 | 2007 | 3 | HUR-US250-018.39 | HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY | 2009-09-25 | 2011-09-25
880 | 24664 | 2007-0480 | 2007 | 8 | BUT-IR75-003.76 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2010-11-09 | 2017-11-09
892 | 24664 | 2007-0480 | 2007 | 8 | BUT-IR75-003.76 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2010-11-09 | 2017-11-09
884 | 24664 | 2007-0480 | 2007 | 8 | BUT-IR75-003.76 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 2010-11-09 | 2017-11-09
442 | 80022 | 2007-0510 | 2007 | 9 | JAC-SR32-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2008-11-06 | 2011-11-06
881 | 25756 | 2007-0550 | 2007 | 3 | D03-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | Assumed Expired
442 | 22200 | 2008-0007 | 2008 | 12 | CUY-IR271-000.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
442 | 78981 | 2008-0022 | 2008 | 5 | LIC-IR70-023.84 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
892 | 12928 | 2008-0031 | 2008 | 9 | SCI-SR522-000.98 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired
442 | 23827 | 2008-0057 | 2008 | 7 | AUG-US33-013.10 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
424 | 25864 | 2008-0058 | 2008 | 9 | BRO-SR32-005.80 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
885 | 76681 | 2008-0107 | 2008 | 1 | DEF-SR281-001.23 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed
885 | 76681 | 2008-0107 | 2008 | 1 | DEF-SR281-001.23 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed
885 | 76681 | 2008-0107 | 2008 | 1 | DEF-SR281-001.23 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed
885 | 76681 | 2008-0107 | 2008 | 1 | DEF-SR281-001.23 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Non performed
885 | 76681 | 2008-0107 | 2008 | 1 | DEF-SR281-001.23 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed
885 | 76681 | 2008-0107 | 2008 | 1 | DEF-SR281-001.23 | FINAL INSPECTION REPAIR | Non performed
442 | 25461 | 2008-0125 | 2008 | 2 | WOO-IR75-000.71 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | #N/A | #N/A
874 | 75276 | 2008-0162 | 2008 | 6 | D06-VA0-000000 | ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY | 2008-09-25 | 2011-09-25
690 | 23261 | 2008-0185 | 2008 | 4 | SUM-SR82-004.14 | SPECIAL - MISC.: | Assumed Expired
880 | 22222 | 2008-0211 | 2008 | 12 | CUY-IR77-001.89 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 2009-11-24 | 2016-11-24
880 | 82497 | 2008-0214 | 2008 | 1 | DEF-US24-010.73 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2008-12-14 | 2015-12-14
881 | 82310 | 2008-0215 | 2008 | 6 | D06-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2008-08-08 | 2010-08-08
880 | 75971 | 2008-0246 | 2008 | 8 | BUT-IR75-005.91 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-11-01 | 2016-11-01
442 | 22985 | 2008-0247 | 2008 | 9 | LAW-US52-005.00 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2009-11-24 | 2012-11-24
880 | 75315 | 2008-0286 | 2008 | 7 | CLA-IR70-020.92 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2009-09-09 | 2016-09-09
442 | 23824 | 2008-0305 | 2008 | 7 | MOT-SR4-021.02 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | Assumed Expired
892 | 75457 | 2008-0323 | 2008 | 9 | BRO-US68-025.54 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired
442 | 25609 | 2008-0336 | 2008 | 9 | JAC-US35-008.35 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY | 2008-11-06 | 2011-11-06
885 | 81567 | 2008-0340 | 2008 | 2 | LUC-IR475-014.53 | FINAL INSPECTION REPAIR | Non performed
882 | 79086 | 2008-0369 | 2008 | 5 | GUE-SR265-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
885 | 21709 | 2008-0371 | 2008 | 11 | HAS-US22-017.17 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed
885 | 21709 | 2008-0371 | 2008 | 11 | HAS-US22-017.17 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed
885 | 21709 | 2008-0371 | 2008 | 11 | HAS-US22-017.17 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed
885 | 21709 | 2008-0371 | 2008 | 11 | HAS-US22-017.17 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Non performed
885 | 21709 | 2008-0371 | 2008 | 11 | HAS-US22-017.17 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed
885 | 21709 | 2008-0371 | 2008 | 11 | HAS-US22-017.17 | FINAL INSPECTION REPAIR | Non performed
882 | 84000 | 2008-0399 | 2008 | 5 | GUE-SR821-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
882 | 81436 | 2008-0408 | 2008 | 5 | MUS-SR340-000.00 | DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
892 | 24868 | 2008-0421 | 2008 | 3 | LOR-IR90-012.42 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY | 2009-11-03 | 2011-11-03
885 | 22784 | 2008-0428 | 2008 | 11 | TUS-US36-018.00 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY | Non performed
885 | 22784 | 2008-0428 | 2008 | 11 | TUS-US36-018.00 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY | Non performed
885 | 22784 | 2008-0428 | 2008 | 11 | TUS-US36-018.00 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY | Non performed
885 | 22784 | 2008-0428 | 2008 | 11 | TUS-US36-018.00 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY | Non performed
885 | 22784 | 2008-0428 | 2008 | 11 | TUS-US36-018.00 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | Non performed
885 | 22784 | 2008-0428 | 2008 | 11 | TUS-US36-018.00 | FINAL INSPECTION REPAIR | Non performed
442 | 83671 | 2008-0445 | 2008 | 5 | GUE-IR70-010.54 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | #N/A | #N/A
882 | 80050 | 2008-0477 | 2008 | 3 | D03-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2009-06-03 | 2011-06-03
892 | 78570 | 2008-0507 | 2008 | 8 | CLI-SR73-008.34 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2011-11-02 | 2013-11-02
888 | 78570 | 2008-0507 | 2008 | 8 | CLI-SR73-008.34 | PORTLAND CEMENT CONCRETE PAVEMENT, 10" THICK (NON-REINFORCEDPER 452) | 2011-11-02 | 2013-11-02
442 | 24507 | 2008-0581 | 2008 | 4 | SUM-SR8-013.30 | ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY | 2010-10-29 | 2012-10-29
888 | 13486 | 2008-0597 | 2008 | 12 | LAK-SR2-003.32 | PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK (NON-REINFORCED PER 452) | #N/A | #N/A
888 | 13486 | 2008-0597 | 2008 | 12 | LAK-SR2-003.32 | PORTLAND CEMENT CONCRETE PAVEMENT | #N/A | #N/A
882 | 75446 | 2008-0632 | 2008 | 9 | HIG-SR247-004.17 | CHIP SEAL, MISC.: | Assumed Expired
892 | 84212 | 2008-6001 | 2008 | 9 | ROS-US23-015.30 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | Assumed Expired
424 | 77350 | 2009-0008 | 2009 | 11 | BEL-SR7-008.70 | FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN | #N/A | #N/A
882 | 83603 | 2009-0089 | 2009 | 2 | SEN-SR19-009.58 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
882 | 75906 | 2009-0157 | 2009 | 8 | PRE-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Assumed Expired
880 | 10754 | 2009-0171 | 2009 | 8 | WAR-IR75-003.40 | ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN | 11/12/11 & 8/7/12 | 11/21/18 & 8/7/19
884 | 10754 | 2009-0171 | 2009 | 8 | WAR-IR75-003.40 | 12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY) | 11/12/11 & 8/7/12 | 11/21/18 & 8/7/19
896 | 80446 | 2009-0201 | 2009 | 2 | HEN-US24-015.85 | PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK (7 YEAR WARRANTY) | 2012-09-28 | 2019-09-28
888 | 78571 | 2009-0244 | 2009 | 8 | CLI-SR73-006.52 | PORTLAND CEMENT CONCRETE PAVEMENT, 10" THICK (NON-REINFORCEDPER 452) | #N/A | #N/A
882 | 78164 | 2009-0283 | 2009 | 9 | JAC-SR139-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2009-09-15 | 2011-09-15
882 | 79967 | 2009-0334 | 2009 | 9 | D09-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2009-09-21 | 2011-09-21
881 | 82122 | 2009-0364 | 2009 | 6 | FRA-US40-004.45 | MICROSURFACING WITH WARRANTY, SINGLE COURSE, AS PER PLAN | Assumed Expired
882 | 80055 | 2009-0410 | 2009 | 3 | HUR-SR269-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2010-07-26 | 2012-07-26
880 | 25199 | 2009-0460 | 2009 | 4 | ATB-IR90-014.25 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2012-06-28 | 2019-06-28
888 | 76825 | 2009-3005 | 2009 | 11 | BEL-IR70-007.61 | PORTLAND CEMENT CONCRETE PAVEMENT | #N/A | #N/A
896 | 80444 | 2009-8015 | 2009 | 2 | LUC-US24-006.19 | PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK (7 YEAR WARRANTY) | 2012-09-28 | 2019-09-28
882 | 76000 | 2010-0104 | 2010 | 2 | WIL-SR49-016.54 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2010-11-08 | 2012-11-08
881 | 83732 | 2010-0120 | 2010 | 6 | D06-VA0-000000 | MICROSURFACING WITH WARRANTY, MULTIPLE COURSE | 2010-09-23 | 2013-09-23
882 | 83732 | 2010-0120 | 2010 | 6 | D06-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2010-09-23 | 2013-09-23
882 | 87398 | 2010-0278 | 2010 | 9 | JAC-LR0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | 2010-10-15 | 2012-10-15
882 | 79969 | 2010-0459 | 2010 | 9 | D09-VA0-000000 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2011-08-04 | 2013-08-04
892 | 23995 | 2010-1040 | 2010 | 2 | LUC-CR505-000.28 | QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN | 2012-07-13 | 2014-07-13
880 | 25869 | 2010-1078 | 2010 | 4 | ATB-IR90-022.06 | ASPHALT CONCRETE (7 YEAR WARRANTY) | 2013-08-29 | 2020-08-29
888 | 81587 | 2010-3002 | 2010 | 11 | HAS-US250-011.72 | PORTLAND CEMENT CONCRETE PAVEMENT | #N/A | #N/A
881 | 82220 | 2010-8033 | 2010 | 3 | WAY-SR585-002.56 | MICROSURFACING WITH WARRANTY, SINGLE COURSE | 2010-10-04 | 2012-10-04
882 | 82222 | 2010-8044 | 2010 | 3 | RIC-SR181-000.00 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY | 2011-08-05 | 2013-08-05
882 | 88477 | 2011-0158 | 2011 | 2 | FUL-SR120-002.26 | SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN | Under Construction
888 | 78166 | 2011-0364 | 2011 | 6 | MRW-SR229-005.30 | PORTLAND CEMENT CONCRETE PAVEMENT, 8" THICK (NON-REINFORCED PER 452) | #N/A | #N/A
Item | PID | Project Number | Proj Year | Dist | County-Route-Section | Item (Full) Description | Warranty Start Date | Warranty End Date
Warranty data from CMS |  |  |  | Date Run: | 2010-04-28
Query: Warranty on CAS-TAS 6-2007 (CAS-TAS),

## Pivot Table of CMS Data
Pivot Table
Item (Full) Description
10" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
11" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
12" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN
12.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
13" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
13.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
14" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
225 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
225 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN
250 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
260 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
310 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
350 MM PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
4" ASPHALT TREATED FREE DRAINING BASE
8" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
9" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), AS PER PLAN
9.5" PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
AGREED LUMP SUM
ASPHALT CONCRETE (5 YEAR WARRANTY)
ASPHALT CONCRETE (7 YEAR WARRANTY)
ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY
ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN
ASPHALT CONCRETE SURFACE COURSE, 12.5 MM, TYPE B (446), AS PER PLAN
ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY
ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE A (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN
ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY
ASPHALT CONCRETE SURFACE COURSE, 12.5MM, TYPE B (446) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN
ASPHALT CONCRETE SURFACE COURSE, 9.5 MM, TYPE B (448) WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN
ASPHALT CONCRETE SURFACE COURSE, TYPE 1, PG64-22 WITH SUPPLEMENT 1059 WARRANTY
ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN
ASPHALT CONCRETE SURFACE COURSE, TYPE 1H WITH SUPPLEMENT 1059 WARRANTY
ASPHALT CONCRETE SURFACE COURSE, TYPE 1H, PG76-22 WITH SUPPLEMENT 1059 WARRANTY
ASPHALT CONCRETE WITH WARRANTY (7 YEARS), AS PER PLAN
CENTER LINE (3 YEAR WARRANTY)
CENTER LINE (5 YEAR WARRANTY)
CHANNELIZING LINE
CHANNELIZING LINE (3 YEAR WARRANTY)
CHANNELIZING LINE (5 YEAR WARRANTY)
CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY
CLASS S CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN
CRACK SEALING WITH WARRANTY, MISC.:
CRACK SEALING WITH WARRANTY, TYPE II
CRACK SEALING WITH WARRANTY, TYPE II OR III
EDGE LINE
EDGE LINE (3 YEAR WARRANTY)
EDGE LINE (5 YEAR WARRANTY)
FIELD PAINTING OF EXISTING STEEL, FINISH COAT, WITH WARRANTY
FIELD PAINTING OF EXISTING STEEL, INTERMEDIATE COAT, WITH WARRANTY
FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY
FIELD PAINTING OF EXISTING STEEL, PRIME COAT, WITH WARRANTY
FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT, WITH WARRANTY
FIELD PAINTING STRUCTURAL STEEL, FINISH COAT, WITH WARRANTY
FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT, WITH WARRANTY
FINAL INSPECTION REPAIR
FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY
FINE GRADED POLYMER ASPHALT CONCRETE, TYPE B, WITH SUPPLEMENT 1059 WARRANTY, AS PER PLAN
FORCE ACCOUNT
FULL DEPTH REPAIR WITH WARRANTY
GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL
HAND CHIPPING WITH WARRANTY
HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY, AS PER PLAN
HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY
LANE LINE
LANE LINE (3 YEAR WARRANTY)
LANE LINE (5 YEAR WARRANTY)
MICRO-SILICA MODIFIED CONCRETE OVERLAY (VARIABLE THICKNESS), MATERIAL ONLY WITH WARRANTY
MICRO-SILICA MODIFIED CONCRETE OVERLAY (VARIABLE THICKNESS),MATERIAL ONLY WITH WARRANTY
MICRO-SILICA MODIFIED CONCRETE OVERLAY USING HYDRO-DEMOLITION WITH WARRANTY
MICRO-SURFACING
MICROSURFACING WITH WARRANTY, MULTIPLE COURSE
MICROSURFACING WITH WARRANTY, MULTIPLE COURSE, AS PER PLAN
MICROSURFACING WITH WARRANTY, SINGLE COURSE
MICROSURFACING WITH WARRANTY, SINGLE COURSE, AS PER PLAN
PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY), MISC.:
PORTLAND CEMENT CONCRETE PAVEMENT, 8" THICK (NON-REINFORCED PER 452)
QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK)
QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY
QC/QA CONCRETE, CLASS QSC2, SUPERSTRUCTURE (DECK) WITH WARRANTY, AS PER PLAN
SAWING AND SEALING ASPHALT CONCRETE PAVEMENT JOINTS WITH WARRANTY
SIGNALIZATION, MISC.:
SINGLE CHIP SEAL WITH TWO YEAR WARRANTY
SINGLE CHIP SEAL WITH WARRANTY
SPECIAL - ASPHALT CONCRETE MISC.:
SPECIAL - ASPHALT CONCRETE, MISC.:
SPECIAL - ASPHALT PAVEMENT (5 YEAR WARRANTY)
SPECIAL - ASPHALT PAVEMENT (7 YEAR WARRANTY)
SPECIAL - BRIDGE DECK CONCRETE OVERLAYS WITH WARRANTY
SPECIAL - CONCRETE BASE JOINT, CLEANED AND FILLED
SPECIAL - HIGH PERFORMANCE CONCRETE WITH WARRANTY
SPECIAL - HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY
SPECIAL - MICROSURFACING WITH WARRANTY, RUT FILL COURSE
SPECIAL - MISC.:
SPECIAL - STRUCTURAL CONCRETE WITH WARRANTY
SPECIAL - STRUCTURE, MISC.:
SPECIAL - STRUCTURE, MISC.:
SPECIAL - SURFACE PREPARATION, FIELD PAINTING OF EX. STEEL W/PRIME, INTERMEDIATE & FINISH COATS W/WARRANTY AS PER SS885
STONE MASTIC ASPHALT CONCRETE SURFACE COURSE (PG76-22M) WITH SUPPLEMENT 1059 WARRANTY
STONE MATRIX ASPHALT CONCRETE, 12.5MM, PG76-22M, (446)
SURFACE PREPARATION OF EXISTING STEEL WITH WARRANTY
SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL, WITH WARRANTY
SURFACE PREPARATION USING HYDRO-DEMOLITION WITH WARRANTY
TEST SLAB
ULTRATHIN BONDED ASPHALT CONCRETE, WITH SUPPLEMENT 1059 WARRANTY
VARIABLE THICKNESS PORTLAND CEMENT CONCRETE PAVEMENT (7 YEAR WARRANTY)
SINGLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN
DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY, AS PER PLAN
SPECIAL - HIGH PERFORMANCE CONCRETE, FOR BRIDGE DECK WITH WARRANTY
PORTLAND CEMENT CONCRETE PAVEMENT, 11.5" THICK (NON-REINFORCED PER 452)
PORTLAND CEMENT CONCRETE PAVEMENT
PORTLAND CEMENT CONCRETE PAVEMENT, 12" THICK (REINFORCED PER 451)
DOUBLE CHIP SEAL WITH TWO YEAR WARRANTY
Grand Total