## Inspection Checklist
Form: | CA-Q-000_NewHeaderTemplate
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
Item 202 Removal of Structures and Obstructions
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Waste | [6 empty] | 0
| Is a waste agreement from an approved landfill or the property owner of land used for the waste area in project records? | 105.16 |  | Never |  |  | 0
| If Regulated Wastes were encountered: Was the activity stopped, and the Engineer notified, until direction for disposal were given? Review the discussion in the MOP Section 202. Document waste removal activities in the Comments Section below. | 203.04 / MOP Sec. 202 |  | Required |  |  | 0
All Removal Items / Miscellaneous Item Removal | [6 empty] | 0
| Except in areas to be excavated or of subsequent work, all resulting cavities, voids, holes, trenches, and pits are backfilled with either embankment material or Structural Backfill Type 1, and compacted in accordance with Item 203? | 202.02 |  | Required |  |  | 0
| All materials removed or excavated were either reused in the work, stored, or disposed according to 105.16 and 105.17? | 202.02 |  | Never |  |  | 0
| For miscellaneous items not listed elsewhere: The item was removed, or abandoned, as designated in the plans? | 202.02 |  | Never |  |  | 0
Structures, Portion of Structures Removed | [6 empty] | 0
| The bridge, culvert, wall, approach slab, concrete slope protection, or other structure is removed to the limits shown in the plans? | 202.03 |  | Required |  |  | 0
| The structure is removed to at least 1 foot below proposed grade, or to the proposed stream bottom if within a stream? | 202.03 |  | Never |  |  | 0
| For partial removal of a structure, was the portion remaining undamaged? | 202.03 |  | Required if Non Conform |  |  | 0
| If present, asphalt wearing course removed separately and prior to bridge deck removal? | 202.03 |  |  |  |  | 0
| Work performed in accordance with the Contractor's demolition shop drawings? | 501.05 |  | Never |  |  | 0
Pipes Removed | [6 empty] | 0
| Pipe or culvert removed and stored, or disposed as indicated in plans? | 202.04 |  | Required |  |  | 0
| Water pipes tested for containing asbestos and, if positive, properly removed and disposed? | 202.04 |  |  |  |  | 0
| Openings in manhole and catch basin walls and abandoned pipe ends are sealed with plugs, stoppers or bulkheads? | 202.04 |  | Required if Non Conform |  |  | 0
Pavements, Walks, Curbs, Steps, Gutters, Traffic Dividers Removed | [6 empty] | 0
| Pavement layers or courses removed as indicated in plans? | 202.05 |  | Required |  |  | 0
| Concrete walks and steps removed as indicated in plans? | 202.05 |  |  |  |  | 0
| Concrete curbs and gutters or stone curbs removed as indicated in plans? | 202.05 |  |  |  |  | 0
| Concrete traffic dividers removed as indicated in plans? | 202.05 |  |  |  |  | 0
| If designated in the plans, removed material was stored? | 202.05 |  |  |  |  | 0
Buildings Demolished | [6 empty] | 0
| Notice of Possession and Approval to Proceed are in project record? | 202.06 |  | Never |  |  | 0
| All foundations, floors, basement walls, concrete slabs, and/or cisterns are removed to at least 1 foot below the surrounding grade? | 202.06 |  | Required |  |  | 0
| All tanks, partitions, materials, and debris are completely removed from basements? | 202.06 |  |  |  |  | 0
| Floor slabs above pits, cisterns and wells are removed, and basement slabs to be left in place are broken up, and all drains sealed? | 202.06 |  | Required |  |  | 0
Septic Tanks, Privy Vaults Removed | [6 empty] | 0
| Tanks and vaults are emptied and contents disposed in accordance with state and local requirements? | 202.07 |  | Required if Non Conform |  |  | 0
| Above grade tanks are completely removed? | 202.07 |  |  |  |  | 0
| Below grade tanks have tops removed, walls removed to 3 feet below subgrade or 1 foot below final grade, and all drains sealed? | 202.07 |  | Required |  |  | 0
Underground Storage Tanks Removed | [6 empty] | 0
| Underground storage tanks are removed in accordance with the “Bureau of Underground Storage Tank Regulations of the Division of Fire Marshal”; Ohio EPA; and applicable federal, state and local regulations? | 202.08 |  | Required |  |  | 0
Guardrail, Fence, Bridge Railing Removed | [6 empty] | 0
| Guardrail, including anchor and terminal assemblies, posts, signs, and delineators, are removed and disposed or stored as indicated in the plans? | 202.09 |  | Required |  |  | 0
| Fence removed and disposed or stored for reuse as indicated in the plans? | 202.09 |  |  |  |  | 0
| Replacement guardrail and fence materials available prior to removing existing? | 202.09 |  | Never |  |  | 0
Manholes, Catch Basins, Inlets, Vaults Removed or Abandoned | [6 empty] | 0
| Manholes, catch basins, vaults and inlets are removed and disposed? | 202.10 / 202.11 |  | Required |  |  | 0
| Manholes, catch basins and inlets designated to be abandoned are removed to at least 1 foot below finished subgrade or final ground surface? | 202.10 / 202.11 |  |  |  |  | 0
| For abandoned manholes, catch basins, and vaults, inlet and outlet pipes are connected together or sealed as designated in the plans? | 202.10 / 202.11 |  | Required if Non Conform
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.