## Inspection Checklist
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
257 Diamond Grinding Portland Cement Concrete Pavement
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Equipment | [6 empty] | 0
| Grinding equipment is self-propelled with a minimum 3 feet wide grinding head? Document equipment Manufacturer and Model. | 257.02 |  |  | Required |  | 0
| Equipment is capable of grinding and texturing in the longitudinal direction without causing spalls or damage? | 257.02 |  |  |  |  | 0
| Equipment has a wheelbase of 12.0 feet & the center of the grinding head is within 3.0 feet forward from the center of the back wheels? | 257.02 |  |  |  |  | 0
| Profiler is an inertial-based non-contact profiler? | 257.02 / S1058 |  |  |  |  | 0
| Profiler and Operator are approved by the Department? The Engineer has copy of approval letter? | 257.02 / S1058 |  |  |  |  | 0
Grinding/Profiling | [6 empty] | 0
| Grinding residue is removed before it is blown by traffic or wind? | 257.02 |  |  |  |  | 0
| Residue is not a nuisance to public or in gutters/drains? | 257.02 |  |  |  |  | 0
| Ramps and transitions are milled from the mainline edge? Positive drainage & acceptable ride established? | 257.03 |  |  |  |  | 0
| Contractor ran initial profile testing to aid in evaluating the grinding methods and equipment? | 257.03 |  |  |  |  | 0
| Contractor runs daily profiles of each day's grinding the next working day? | 257.03 |  |  |  |  | 0
| Pavement surface is true to grade and consists of a longitudinal corduroy-type texture? | 257.04 |  |  |  |  | 0
| Peaks of the ridges are 1/16 inch higher than the grooves with 53 to 57 evenly spaced grooves per foot? | 257.04 |  |  |  |  | 0
| The profiler wheel path is run parallel to the centerline of the pavement around 3 feet from lane edge? | 257.04 |  |  |  |  | 0
| Ground surface does not exceed an IRI of 95 inches per mile? ProVAL is used to obtain profile and smoothness measurements? | 257.04 |  |  |  |  | 0
| Ground surface localized surface deviations do not exceed 0.4 inches in 25 feet? | 257.04 |  |  |  |  | 0
| Profile measurement starts and stops within 1.0 foot of existing pavement, pressure relief joint, or approach slab? | 257.04 |  |  |  |  | 0
| Faulting at joints and cracks is eliminated & riding characteristics are restored within 1/16 inch? | 257.03 / 257.04 |  | Required if No |  |  | 0
| Transverse slope is uniform, no depressions or misalignment of slope >1/4 inch in 12 feet? Document results. | 257.04 |  | Required if No | Required |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.