## Inspection Checklist
Form: | CA-Q-000_NewHeaderTemplate
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
424 Fine Graded Polymer Asphalt Concrete
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Construction - General | [6 empty] | 0
| Does the JMF match the project material requirements? Document approved JMF Number. | 401.02 / MOP |  |  | Required |  | 0
| Is the FQCS Certified on OMM List? Document FQCS Name. | 403.03 |  |  | Required |  | 0
Weather Limitations | [6 empty] | 0
| Is the existing pavement surface dry? | 401.06 |  |  |  |  | 0
| Is the air temperature and surface temperature ≥ 60° F? Document temp. | 424.05 |  |  | Required |  | 0
Hauling | [6 empty] | 0
| Is the haul distance from the asphalt plant to the project less than 50 miles? | 401.11 |  |  |  |  | 0
| Are trucks fully covered with waterproof tight fitting tarps to protect from wind and rain? | 401.11 |  |  |  |  | 0
| Are truck beds insulated when required? (Temp. < 50° F) (Haul distance is > 20 miles) | 401.11 |  |  |  |  | 0
| Have any trucks leaking fuel, hydraulic fluid, oil etc. been removed from the operation until they are corrected? | 401.11 |  |  |  |  | 0
| Does a tarp cover the asphalt when the truck pulls up to the paver? | 401.11 |  |  |  |  | 0
| Are truck tailgates un-chained when dumping into hopper to avoid segregation? | 401.11 |  |  |  |  | 0
| Have any trucks with material sticking to the bed been removed from the operation or corrected? | 401.11 |  |  |  |  | 0
| Are the trucks cleaning out beds at a satisfactory location off the pavement? | 401.11 |  |  |  |  | 0
Spreading and Finishing | [6 empty] | 0
| Is the existing pavement clean? (no dust, loose pavement scabs, oil/fuel contamination) | 401.14 |  |  |  |  | 0
| Are vertical faces of curb, manholes, structures, etc. covered with a thick coating liquid asphalt material? | 401.14 |  |  |  |  | 0
| Are trucks delivering the mix to the paver continuously and at a uniform rate? | 401.15 |  |  |  |  | 0
| Are the trucks emptying without bumping the paver? | 401.15 |  |  |  |  | 0
| Is the mix within spec temperature range? 335° F - 370° F for HMA 300° F - 340° F for WMA Document mix laydown temperature a minimum of 4 times per day. | 424.04 |  |  | Required |  | 0
| Is aggregate uniformly coated when delivered to the paver? | 401.15 |  |  |  |  | 0
| Is the mat compacted thickness correct? Document thickness placed. | 401.15 |  |  | Required |  | 0
| Are automatic screed controls being used? | 401.12 |  |  |  |  | 0
| Does the paver have auger and tunnel extensions mounted to within ~ 18 in. max of the end gate for the planned paving width? | 401.15 |  |  |  |  | 0
| If the paver is leaving any unusual marks, streaks, tears or shadows in the mat, was it addressed and corrected? | 401.15 |  | Required if No |  |  | 0
| Is the mixture uniform texture, i.e. no segregation? (coarse or fine areas) | 401.15 |  | Required if No |  |  | 0
| Is the mat free of any signs of segregation, tenderness, raveling, flushing, rutting, holes, debris? | 401.15 |  | Required if No |  |  | 0
| For surface course: are gutters sealed with 4” band of asphalt binder? | 401.15 |  |  |  |  | 0
| Is the yield within ±5%? Calculate and document yield 4 times daily at a minimum. Attach CA-FP-4 | 401.15 / 401.19 |  |  | Required |  | 0
Compaction | [6 empty] | 0
| Does rolling start at the edge and move longitudinally and parallel to the centerline? | 401.16 |  |  |  |  | 0
| Is each roller pass overlapped by 1/2 width? | 401.16 |  |  |  |  | 0
| Do the rollers obtain full coverage and are roller marks are removed? | 401.16 |  |  |  |  | 0
| Has the roller train made complete coverage of the mat before mat temps reach 175° F? | [5 empty] | 0
Joints | [6 empty] | 0
| What point of reference is provided to drive the paver? (string line, skip paint, lines etc..) Document reference used. | 401.17 |  |  | Required |  | 0
| Is the unconfined joint placed straight? | 401.17 |  |  |  |  | 0
| Are corrections made to joints that are rounded or not straight prior to closing the joint? | 401.17 |  |  |  |  | 0
| Are joints set up at the proper height above the adjacent construction to receive maximum compaction? (~1/4” per 1” of compacted mat thickness) | 401.17 |  |  |  |  | 0
| Cold longitudinal joints - Are all are sealed with PG binder or SS875 Asphaltic Joint Adhesive? | 401.17 / 702.01 / 702.13 / 702.04 |  |  |  |  | 0
| Cold longitudinal joints - Is there 100 coverage and ½ in. overlap on application of joint adhesive? | 401.17 / 702.01 / 702.13 / 702.04 |  |  |  |  | 0
| Does the confined joint pass lap the unconfined edge by 1"-1.5"? | 401.17 |  |  |  |  | 0
| Are longitudinal joints staggered per Std. Dwg.. BP 3.1 or stepped 6" minimum for phased construction joints? Specify. | BP 3.1 / 401.17 |  |  |  |  | 0
| When making a longitudinal joint it is rolled first? | 401.16 |  |  |  |  | 0
| Is the adjacent lane placed within 24 hours whenever traffic is permitted to cross the edge of the mat? | 401.17 |  |  |  |  | 0
| Cold transverse joints - Are all cut to vertical and sealed (PG Binder, Rubberized Asphalt/SBR Asphalt Emulsion or tack material)? Is there 100% coverage? | 401.17 / 702.01 / 702.13 / 702.04 |  |  |  |  | 0
| Hot Joints – Are delivery trucks alternating between two pavers? | 401.17 |  |  |  |  | 0
448 Density Startup | [6 empty] | 0
| What gauge is the gauge Type, Model, ID Number? Only nuclear or PQI 300/301/380 are acceptable. | S1055 |  |  | Required |  | 0
| Was the nuclear gauge standard count or the PQI gauge upper and lower limit determined? Witness and document readings. | S1055 |  |  | Required |  | 0
| Was the gauge inspected to verify that no offset was entered into gauge? | S1055 |  |  |  |  | 0
| Was the minimum target density determined within the first 4hrs of production or after any mix changes? Attach TE-Min Density Target form. | S1055 |  |  |  |  | 0
| Was the gauge startup readings and companion cores witnessed by the Inspector? | S1055 |  |  |  |  | 0
| What was the roller pattern and pass count to obtain maximum unit weight for minimum density target? | S1055 |  |  | Required |  | 0
| Was the same roller pattern used to compact mix until the minimum density target was determined? | S1055 |  |  |  |  | 0
448 Density Production | [6 empty] | 0
| Did the contractor take QC readings every 1000 feet alternating L/C/R? Attach daily TE Mat Density QC QA form. | S1055 |  |  |  |  | 0
| Did the Inspector witness a minimum two QA tests at random locations daily? (Two QA tests are minimum additional checks should be made) Document QA test results. | S1055 |  |  | Required |  | 0
| Was the gauge inspected to verify that no offset was entered into gauge for each QA check? | S1055 |  |  |  |  | 0
| Did the QA results require a density deduction? | S1055 |  |  |  |  | 0
Compaction requirements when 448 density specification does not apply | [6 empty] | 0
| Intermediate & Surface Course – Is a three-wheel roller used in breakdown position? | 401.13 / 401.16 |  |  |  |  | 0
| Variable Course – Is a steel wheel roller and a pneumatic tire roller being used? | 401.13 / 401.16 |  |  |  |  | 0
| Is a vibratory roller being used only when course thickness ≥1.5 inches? (Typical lift thickness is 3/4" to 1" no vibratory rollers allowed) | 401.13 / 401.16 |  |  |  |  | 0
| Does the roller train conform to the specifications? (two rollers minimum) | 401.13 / 401.16 / 424.06 |  |  |  |  | 0
| Is the maximum capacity (yd2/hr.) of the roller train calculated? Is it converted to (Tons/hr.)? Provide calculations CA-FP-3. | 401.13 / 401.16 |  |  |  |  | 0
| Is the spreading rate of placement calculated (Tons/hr.)? Provide calculation CA-FP-3. | 401.13 / 401.16 |  |  |  |  | 0
| Is the spreading rate of placement less than twice the roller train capacity? Provide calculation CA-FP-3. | 424.06 |  |  |  |  | 0
Anti-Segregation Equipment / Night Paving | [6 empty] | 0
| Is a MTV/MTD or remix paver being used when required? Document device manufacturer and model number. | 401.12 |  |  | Required |  | 0
| Is Contractor using a paver hopper insert with minimum capacity of 10 tons? | 401.12 |  |  |  |  | 0
| Was a 1000ft. minimum test strip performed for the fist day of paving the JMF? | 401.12 |  |  |  |  | 0
| Was the test strip evaluated for physical segregation and transverse temperature differentials less than 35 °F? Attach form CA-FP-5. | 401.12 |  |  |  |  | 0
| Did the test strip pass evaluation? | 401.12 |  |  |  |  | 0
| Has mat been monitored for physical segregation and thermal differentials? Document results minimum 4 times per day. | 401.12 |  |  | Required |  | 0
| Was the lighting system approved before use? | 401.15 |  |  |  |  | 0
| Did the lighting system provide the required luminance? (5 foot-candles at equipment/1 f-c @ 25 feet. At coring provide 5 f-c @ coring and 1 f-c @ 10 feet) | 401.15 |  |  |  |  | 0
| Is the pavement reviewed & inspected during daylight? | MOP |  |  |  |  | 0
Surface Tolerances | [6 empty] | 0
| Have bumps been checked for compliance with 1/4 inch in 10 feet? | 401.19 |  |  |  |  | 0
| Is a longitudinal profile specified in plans? If yes, has it been tabulated and checked for 1/2 inch tolerance to specified profile prior to placing surface course? | 401.19 |  |  |  |  | 0
| Is transverse slope specified in typical sections? If yes, is it in compliance with 3/8 inch in 10 feet? | 401.19 |  |  |  |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.