## Inspection Checklist
Form: | CA-Q-0451_20170120
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
451 Reinforced Portland Cement Concrete Pavement
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| Does the JMF match the material requirements? Document the approved JMF. | 451.01 |  |  | Required |  | 0
| If the bid item requires QC/QA concrete has the QC plan been approved? | 451.03 |  |  |  |  | 0
| Is QA testing performed per CMS 455? | 451.03 |  |  |  |  | 0
| Has the Contractor submitted an acceptable Hiperpav analysis in (.hp3) digital format that does not predict early age cracking? | 451.09 |  |  |  |  | 0
| Has the file been checked in Hiperpav per S1033 to ensure that the appropriate project conditions, weather conditions, and strategy are input? | 451.09 |  |  |  |  | 0
Equipment | [6 empty] | 0
| Paving machine is self propelled and has internal vibrators? Roller vibratory screeds are not acceptable for typical placements. Document Equipment. | 451.04 |  |  | Required |  | 0
| Paving train is capable of uniformly distributing and consolidating concrete at the delivery rate? | 451.04 |  |  |  |  | 0
Fixed Forms | [6 empty] | 0
| Is the paving equipment capable of operating on the forms without displacement of forms? | 451.04A |  |  |  |  | 0
| Are the forms steel and of depth equal to the specified pavement thickness? Document thickness. | 451.04A |  |  | Required |  | 0
| Are the form sections at least 10 ft. in length without horizontal joints in the height of the form? Built up forms can only be used on small projects < 2000SY. | 451.04A |  |  |  |  | 0
| Are forms clean, straight and oiled prior to each use? | 451.04A |  |  |  |  | 0
| Are forms set to the proper grade and alignment? 1/8in. in 10 ft. Top face 1/4in. in 10 ft. Vertical face Document check locations and results. | 451.05 | Required |  | Required |  | 0
| Are forms placed on uniformly on compacted material? | 451.05 |  |  |  |  | 0
| Are forms securely pinned to the subbase? 3 pins in 10 ft. minimum | 451.06 A |  |  |  |  | 0
| Has the subbase been checked for proper cross slope or trimmed with automatic trimmer? | 451.06 A |  |  |  |  | 0
| The removal of forms is not causing any damage to the concrete. | 451.12 |  |  |  |  | 0
Slip Form Paving | [6 empty] | 0
| Are vibrators operating at 7000 to 11,000 impulses per minute and set so they are not making contact with any reinforcing steel or dowels, etc.? | 451.04B |  |  |  |  | 0
| Do the vibrators start and stop with paver starts and stops? | 451.04B |  |  |  |  | 0
| Is the paver providing an unsegregated mat with no displacement of coarse aggregate? | 451.04B |  |  |  |  | 0
| Does the paver have an operating vibration monitoring system? Not required for shoulders, gores or projects less than 10,000SY. | 451.04B |  |  |  |  | 0
| Has the previous paving days vibration monitoring report been submitted and reviewed for compliance? | 451.04B |  |  |  |  | 0
| Is the paver accurately controlling the finished grade to the preset grade line? Document locations checked for finished grade. | 451.04B | Required |  | Required |  | 0
| Has the subbase been checked for proper cross slope and trimmed with automatic trimmer? | 451.06 B | Required |  | Required |  | 0
Dowels | [6 empty] | 0
| Proper diameter dowels used? 1 in. dowel for T < 8.5 in. 1.25 in. dowel for 8.5 in. < T ≤10 in. 1.5 in. dowel for T > 10 in. | Table 451.09-1 |  |  |  |  | 0
| Dowels bars and basket assemblies are epoxy coated? | 451.02 / 709.00 / 709.13 |  |  |  |  | 0
| Proper number of dowels and spacing provided? Document number and spacing. | 451.09 B / BP-2.2 |  |  | Required |  | 0
Dowel Baskets | [6 empty] | 0
| Dowel baskets anchored to base using approved method? At least 8 pins (½ in. D. x 18 in. long) driven at angle? Power-driven fasteners/pins/clips allowed on concrete or stabilized base. | 451.09 B |  |  |  |  | 0
| Dowels in baskets are parallel to the subbase? Document check locations and results. | 451.09 B / BP-2.2 | Required |  | Required |  | 0
| Dowels in baskets are positioned at mid-slab? Document check locations and results. | 451.09 B / BP-2.2 | Required |  | Required |  | 0
| Free end of dowels coated with new light form oil within 2 hours of paving? | 451.09 B |  |  |  |  | 0
| Shipping wires removed immediately prior to paving? | 451.09 B |  |  |  |  | 0
| At expansion joints, PFEJ board fits tight, caps installed & dowels oiled? | 451.09 C |  |  |  |  | 0
| Dowel basket exposure to weather and sunlight limited to 180 days? | 709.13 |  |  |  |  | 0
Dowel Bar Inserter | [6 empty] | 0
| Does the slip form paver with DBI meet project requirements? Document equipment. | 451.09B |  |  | Required |  | 0
| Does the Contractor have a MIT Scan-2 or other approved equipment and trained personnel? Document equipment calibration date and document personnel training. | 451.09B |  |  | Required |  | 0
| Has the Contractor turned in a plan with standard protocol for paving direction, naming conventions, and how exceptions will be handled? | 451.09B |  |  |  |  | 0
| Has the Contractor provided software to analyze equipment output files? | 451.09B |  |  |  |  | 0
| Has the Contractor performed an acceptable minimum 500 ft. test section? Each JS < JST 90% meet Acceptance Table 451.09-2 No dowel exceeds rejection tolerances Document test section location and results. | Table 451.09-2,3 | Required |  | Required |  | 0
| Has the Contractor measured every 10th joint on the project for compliance? If more than 10% exceed acceptance but are less than rejection increase scanning to every 5th joint. | 451.09B |  |  |  |  | 0
| Has the Contractor submitted previous day's scan results and are they acceptable? If results are not acceptable additional scanning should be performed and paving may need to cease. | 451.09 |  |  |  |  | 0
| Do all scanned joints meet acceptance requirement? If no, repairs must be done per the approved corrective action plan. Document locations and repairs. | 451.09B | Required if Non Conform | Required if Non Conform | Required if Non Conform |  | 0
Tiebars | [6 empty] | 0
| Epoxy coated tiebars or epoxy coated hook bolts in longitudinal joints spaced at 30 in. centers? 6 bars per 15 ft. slab 8 bars per 21 ft. slab | 451.09 A / BP-2.1, Table A |  |  |  |  | 0
| Tiebars or hook bolts epoxy coated? | 451.02 / 451.09 A / 709.00 |  |  |  |  | 0
| Tiebars are #5 x 30 in.? | 451.09 A / BP-2.1, Table A |  |  |  |  | 0
| Hook bolts are 6 in. & 8 in. w/ 2 in. leg, 9/16 in. D. and coupling 1-7/8 in., or wiggle bolt (12 in. x 9/16 in. D.)? | 451.09 A / BP-2.1, Table A |  |  |  |  | 0
| Tiebars installed by mechanical equipment or secured by chairs? Document installation method. | 451.09 A |  |  | Required |  | 0
| Tiebars being installed at mid-depth at longitudinal joints? | 451.09 A / BP-2.1 |  |  |  |  | 0
| Tiebars placed minimum distance from centerline of dowel basket (transverse joint)? 15 in. min for 15 ft. slabs 21 in. min for 21 ft. slabs | BP-2.1 |  |  |  |  | 0
Reinforcing Steel - 451 ONLY | [6 empty] | 0
| Steel wire mesh W4 or D4 at 12 in. spacing longitudinally and W8.5 or D8.5 at 6 in. spacing transversely? | 451.08 / BP-1.1 |  |  |  |  | 0
| Mesh free from dirt, oil, paint, grease, etc.? | 451.08 |  |  |  |  | 0
| Mesh placed 2-1/2 in. to T/3 +1 foot below slab surface? Document check locations and results. | BP-1.1 | Required |  | Required |  | 0
| Mesh placed 12 in.±2 in. - from transverse joint? Document check locations and results. | BP-1.1 | Required |  | Required |  | 0
| Mesh placed 2 in. from edge of pavement? Document check locations and results. | BP-1.1 | Required |  | Required |  | 0
| Mesh placed in two layer operation: Bottom layer is struck off and mesh placed in final position? Document check locations and results. | 451.08 | Required |  | Required |  | 0
| Mesh placed ahead of paver: Mesh is securely anchored and at correct depth? Document check locations and results. | 451.08 | Required |  | Required |  | 0
| Mesh placed in one operation: Mechanical or vibratory method depresses mesh to correct depth? Document check locations and results. | 451.08 | Required |  | Required |  | 0
Concrete Placement | [6 empty] | 0
| Contractor has a separate spreader in the paving train when width of pavement is ≥ 12-feet and plan qty > 10,000 SY? Spreader may be waived when using slip form paver with dowel bar inserter but concrete must be placed uniformly. | 451.07 |  |  |  |  | 0
| Dowel basket assemblies vibrated by separate internal vibrator? | 451.07 |  |  |  |  | 0
| Have previous pavement placements attained beam breaks of 500 psi AND at least 3 days cure time prior to using for finishing equipment operations? Note: allowance is for finishing equipment only. | 451.07 |  |  |  |  | 0
| Subbase material is not frozen and free of frost? | 451.07 |  |  |  |  | 0
| Subbase has been thoroughly moistened prior to paving? | 451.07 |  |  |  |  | 0
| When paving on asphalt, the asphalt is coated with curing compound at 1gal/150SF? | 451.07 |  |  |  |  | 0
| Concrete is spread uniformly full width of the pavement? | 451.07 / MOP |  |  |  |  | 0
| Does the Contractor have an approved lighting system if placing after dark? | 451.07 |  |  |  |  | 0
| IF Air Temp ≤ 35° F is Concrete Temp 50 - 80°F? IF Air Temp > 35° F is Concrete Temp < 95°F? Document temps 4 times/day min. | 451.07 |  |  | Required |  | 0
Concrete Finishing | [6 empty] | 0
| No water added to the pavement surface? | 451.1 |  |  |  |  | 0
| Pavement edges are rounded with edging tool (1/8 in. at joints & 1/2 in. outside lane)? | 451.10 / BP-2.1 |  |  |  |  | 0
| Surface textured with broom finish? | 451.1 |  |  |  |  | 0
| Surface tined in longitudinal direction & straight? (3/4 in. Spaced, 1/8 in. Deep, 1/8 in. Wide). Transverse tining is only to be used in small areas, shoulders and gores as approved by the Engineer. | 451.1 |  |  |  |  | 0
| Station numbers impressed in fresh concrete? | 451.1 |  |  |  |  | 0
Concrete Curing | [6 empty] | 0
| Self propelled curing machine with wind protection and shielding used? | 451.11 |  |  |  |  | 0
| Curing compound is white pigmented and properly agitated? | 451.11 / 705.07 / MOP |  |  |  |  | 0
| Curing compound applied uniformly after water sheen has disappeared? | 451.11 |  |  |  |  | 0
| Pavement edges sprayed with curing compound/after form removal (Fixed Form Construction)? | 451.11 |  |  |  |  | 0
| Curing compound rate check? Attach calculation (1gal/150SF min.) | 451.11 |  |  | Required |  | 0
| Pavement protected from freezing for seven days or 600 psi beam break? | 451.11 |  |  |  |  | 0
| Pavement cured for seven days before opening to traffic or after 5 days with 600 psi beam break? | 451.17 |  |  |  |  | 0
Sawing/Joint Seal | [6 empty] | 0
| Contractor has a standby saw when cutting contraction joints? | 451.09 D |  |  |  |  | 0
| Sawing depth checked to assure compliance with the specifications? 1/4 in. ± 1/16 in. x T/4 for T ≤ 10 in. 1/4 in. ± 1/16 in. x T/3 for T > 10 in. Document locations checked and results. | 451.09 D / BP-2.2 | Required |  | Required |  | 0
| If using early entry saw: 1/8 in. W x 2-1/4 in. to 2-1/2 in. deep Document locations checked and results. | 451.09 D | Required |  | Required |  | 0
| Saw cuts straight and perpendicular to the pavement edge and without damage to the concrete? | 451.09 |  |  |  |  | 0
| Construction joints are placed at end of each days paving or when paving in suspended for 30 minutes or more? Locate construction joints at contraction joint location or no closer than 10ft to the adjacent contraction joint. Document location. | 451.09 | Required |  |  |  | 0
| Expansion joints provided and sealed before opening to traffic? Use when pressure relief joint not provided at bridge structures or as shown on plans. | 451.09 / 451.16 |  |  |  |  | 0
Concrete Testing | [6 empty] | 0
| Concrete tests are performed at the point of placement? | MOP |  |  |  |  | 0
| Paver train is not resulting in segregation of the mixture or loss of air content? Check air content in front of and behind the paver at the same location and compare at least once per day. Document results. | 451.04A |  |  | Required |  | 0
| Air, slump and yield tests recorded every 7500 SY when beams are made? This is required for concrete without QC/QA. Air = 7 ± 2% Slump = 1 to 3 in. Yield = ± 1% | MOP / 499.03 | Required |  | Required |  | 0
| Contractor Technician testing material per approved QC plan? This is required for concrete with QC/QA. | 455.04 |  |  |  |  | 0
| Inspector running side-by-side Air / Slump testing with technician for at least 10% of the tests? Air Comparison = ± 1% Slump Comparison = ± 1 in. Document results and comparison. | 455.05 | Required |  | Required |  | 0
| Two concrete test beams made every 7500 square yards? Document beam results and locations. | 451.07 | Required |  | Required |  | 0
| 10-ft. straight edge being used to check surface trueness after finishing (1/8 in. in 10 feet or 1/4 in. in 10 feet)? | 451.1 |  |  |  |  | 0
| Slip Form Pavement thickness checks made during paving. Thickness cannot vary from typical section by more than 1/4 in. at longitudinal joints and 1/2 in. outside edge. Document check locations and results. | 451.04 B / MOP | Required |  | Required |  | 0
| Cores taken for pavement area in 2000 SY sublots using Supplement 1064? Document core locations. | 451.18 | Required |  |  |  | 0
Smoothness | [6 empty] | 0
| Surface variations measured for 1/8 inch in 10 feet or 1/4 inch in 10 feet for ramps? | 451.13 |  |  |  |  | 0
| If PN 420 applies has surface profile been measured? | PN420 |  |  |  |  | 0
| Has corrective action plan been submitted and approved? Document any repair locations and methods. | 451.13 |  |  | Required |  | 0
Opening to Traffic | [6 empty] | 0
| Has pavement been evaluated for acceptance, (repair plan submitted and approved) if required? | 451.17 |  |  |  |  | 0
| Before opening to traffic: 600 psi beam break with 5 day cure? OR 7 days elapsed? Note: Pavement can be opened in 3 days with 600 psi beam break with the use of high early strength concrete | 451.17 |  |  |  |  | 0
| Are there any pavement thickness deficiencies? If yes, please document the locations and how they are rectified. | 451.18 |  |  | Required if Yes |  | 0
| Are there any pavement strength deficiencies? If yes, please document the locations and how they are rectified. | 451.18 |  |  | Required if Yes |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.