## Inspection Checklist
Form: | CA-Q-0608_20170120
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
608 Walks, Curb Ramps, and Steps
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Concrete and Asphalt Walks - Fixed Form Construction | [6 empty] | 0
| Excavated to required depth and width that includes allowance for forms? | 608.03 A |  |  |  |  | 0
| Fixed forms are wood or metal? Document type used. | 608.03 B |  |  | Required |  | 0
| Fixed forms extend full depth of concrete? | 608.03 B |  |  |  |  | 0
| Forms do not deform/deflect under pressure? | 608.03 B |  |  |  |  | 0
Slip Formed Construction | [6 empty] | 0
| Slip form paver mold conforms to required sidewalk cross-section. | 608.03 A / 609.04 C |  |  |  |  | 0
| Slip form paver set to line, grade, and slope. | 608.03 A / 609.04 C |  |  |  |  | 0
| Concrete is extruded without slumping. | 608.03 A / 609.04 C |  |  |  |  | 0
Placing and Finishing Concrete | [6 empty] | 0
| Document approved JMF and concrete class. | 608.02 |  |  | Required |  | 0
| Subgrade is moistened prior to concrete placement? | 608.03 C |  |  |  |  | 0
| All edges finished with 1/4 in. radius tool. | 608.03 C |  |  |  |  | 0
| Joints are formed or saw cut 1/8 in. wide x 1/4 x thickness at 5 feet spacing? | 608.03 C |  |  |  |  | 0
| 1-inch wide expansion joint filler used at fixed structures for full depth of walk? | 608.03 C |  |  |  |  | 0
| 1-inch wide expansion joint filler used at back of curbs (on 250-feet R or smaller)? | 608.03 C |  |  |  |  | 0
| Sidewalk transverse slope is ≤ 2%? Document locations checked and results. | 608.03 D | Document location |  | Document results |  | 0
| Final finish has sandy texture and no water added during finishing? | 608.03 C |  |  |  |  | 0
| Uniform film of white curing membrane applied? | 608.03 E / 451.10 |  |  |  |  | 0
Asphalt Walks - Excavation and Forms | [6 empty] | 0
| Excavated to required depth and width that includes allowance for forms? | 608.04 A / 608.03 A |  |  |  |  | 0
| Fixed forms are wood or metal? Document type used. | 608.04 A / 608.03 A |  |  | Required |  | 0
| 4-inches of 304 aggregate base placed and compacted? | 608.04 B |  |  |  |  | 0
| Fixed forms extend full depth of asphalt and do not deform/deflect under pressure? | 608.04 A / 608.03 A |  |  |  |  | 0
Asphalt Walks - Asphalt Placement and Compaction | [6 empty] | 0
| 441 Type I has approved JMF. Document JMF | 608.02 |  |  | Required |  | 0
| 441 Type I is placed in one or more lifts based on final thickness? | 608.04 C |  |  |  |  | 0
| Asphalt is compacted using approved method? | 608.04 C |  |  |  |  | 0
| Sidewalk transverse slope verified? Document locations checked and results. | 608.03 D | Document location |  | Document results |  | 0
Crushed Aggregate Walks - Excavation and Forms | [6 empty] | 0
| Excavated to required depth and width that includes allowance for forms? | 608.05 A / 608.03A |  |  |  |  | 0
| Fixed forms are wood or metal? Document type used. | 608.05 B |  |  | Required |  | 0
| Forms same depth as loose material? | 608.05 B |  |  |  |  | 0
| Forms are backed with compacted soil level with top of walk? | 608.05 B |  |  |  |  | 0
| Crushed aggregate meets 703.10 grading? | 608.02 |  |  |  |  | 0
Concrete Steps - Excavation and Forms | [6 empty] | 0
| Excavated to required depth and width that includes allowance for forms? | 608.06 A / 608.03 A |  |  |  |  | 0
| Fixed forms are wood or metal? Document type used. | 608.06 A / 608.03 B |  |  | Required |  | 0
Concrete Steps - Placing, Finishing, Curing | [6 empty] | 0
| Concrete has approved JMF? Document JMF. | 608.02 |  |  | Required |  | 0
| Reinforcing steel (if required) is placed per plan? Document number, size, clearance, etc. | 608.02 |  |  | Required |  | 0
| Concrete is vibrated; no water is added to the surface during finishing? | 608.06 A |  |  |  |  | 0
| Treads are finished to a “sandy texture” with 1% slope? Document slope check. | 608.06B |  |  | Required |  | 0
| Uniform film of white curing membrane applied? | 608.06 D / 603.03 E |  |  |  |  | 0
Curb Ramps - Excavation and Forms | [6 empty] | 0
| Excavated to required depth and width that includes allowance for forms? | 608.07 / 608.03 A |  |  |  |  | 0
| Fixed forms are wood or metal? Document type used. | 608.07 / 608.03 B |  |  | Required |  | 0
| Fixed forms extend full depth of concrete? | 608.07 / 608.03 B |  |  |  |  | 0
| Grade pins/stakes are set to control required slopes? | SCD / BP-7.1 |  |  |  |  | 0
Curb Ramps - Placing and Finishing | [6 empty] | 0
| Concrete has approved JMF? Document JMF | 608.07 / 608.02 |  |  | Required |  | 0
| Subgrade is moistened prior to concrete placement? | 608.07 / 608.03 C |  |  |  |  | 0
| Concrete is deposited in single layer? | 608.07 / 608.03 C |  |  |  |  | 0
| Concrete is struck off and finished to grade and with required slope with no water added? | 608.07 / 608.03 C / SCD BP-7.1 |  |  |  |  | 0
| Detectable warnings are placed per manufacturer's instructions? Provide placement details. | SCD / BP-7.1 |  |  | Required |  | 0
| Detectable warning 5yr warranty letter received? | 608.07 |  |  |  |  | 0
| All edges finished with 1/4 inch radius tool? | 608.03 C |  |  |  |  | 0
| Joints are formed or saw cut 1/8 in. wide x 1/4 x T deep? | 608.03 C |  |  |  |  | 0
| 1/2 in. expansion joint filler used around new curb ramps placed in existing walks? | SCD / BP-7.1 |  |  |  |  | 0
| Final slopes are checked for conformance to Standard Drawing? Document slope measurements. | SCD / BP-7.1 |  |  | Required |  | 0
| Finished ramp surface is rougher than adjoining walk with coarse broom striations placed perpendicular to ramp slope? | 608.07 |  |  |  |  | 0
| Uniform film of white curing membrane applied? | 608.06 D / 603.03 E |  |  |  |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.