## Inspection Checklist
Form: | CA-Q-0609_20170120
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
609 Curbing, Concrete Medians, and Traffic Islands
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Stone Curb | [6 empty] | 0
| Stone type meets requirement? Document stone type. | 609.02 |  |  | Required |  | 0
| 95% greater than 5 feet and not less than 42 inches (except closure pieces)? | 609.03 |  |  |  |  | 0
| Straight edge on top and exposed face and ends dressed at right angles? | 609.03 |  |  |  |  | 0
| Subgrade is compacted and 3 inches minimum of aggregate placed? | 609.03 |  |  |  |  | 0
| Batter set correctly at 1 in 20? | 609.03 |  |  |  |  | 0
| Curb in curves set in concrete per spec? | 609.03B |  |  |  |  | 0
| Construction of joints per spec? | 609.03C |  |  |  |  | 0
Cast-in-Place Concrete Curb and Combination Curb and Gutter | [6 empty] | 0
| Do form dimensions or slip form shoe meet required curb dimensions? If slip formed, measure finished curb dimensions. | 609.04 |  |  |  |  | 0
| Concrete has approved JMF. Document JMF/concrete class. | 609.02 |  |  | Required |  | 0
| Subgrade is moistened prior to concrete placement? | 609.04A |  |  |  |  | 0
| Steel forms used and set to line and grade? If curb radius is 200 feet or less the use of flexible steel or wood form allowed. Document this use. | 609.04A |  |  |  |  | 0
| If used, is slip form paver set to line, grade, and slope? | 609.04A |  |  |  |  | 0
| Are tie bars placed if required? | 609.04B |  |  |  |  | 0
| Joints sawed, grooved, or formed by metal plates? 1/4 in. joint @ 10 ft. spacing. 2 in. depth for curb and gutter. 1/5 X curb height for standing curb. Match joints if integral with concrete pavement. Document joint depth. | 609.04A |  |  | Required |  | 0
| Joint spacing measured? Document joint spacing. | 609.04A |  |  | Required |  | 0
| Slip form equipment consistently providing desired shape with no edge slumping? | 609.04C |  |  |  |  | 0
| Finishing uniform with no water added to the surface? | 609.04C |  |  |  |  | 0
| Uniform white curing compound placed? | 609.04E |  |  |  |  | 0
Asphalt Concrete Curb | [6 empty] | 0
| Tack coat applied at proper application rate (0.05 gal/see for Method A)? | 609.05 |  |  |  |  | 0
| Asphalt Concrete JMF recorded? Document JMF and material type. | 609.05 |  |  | Required |  | 0
| Placement Method A or Method B used? Document method used. | 609.05 |  |  | Required |  | 0
Concrete Median and Traffic Island | [6 empty] | 0
| Do form dimensions or slip form shoe meet required curb dimensions? If slip formed, measure finished curb dimensions. | 609.06 |  |  |  |  | 0
| Concrete has approved JMF? Document JMF/concrete class. | 609.02 |  |  | Required |  | 0
| Subgrade is moistened prior to concrete placement? | 609.06B |  |  |  |  | 0
| Steel forms used and set to line and grade? If curb radius is 200 or less the use of flexible steel or wood form allowed. Document this use. | 609.06A |  |  |  |  | 0
| Slip form paver set to line, grade, and slope. | 609.06A |  |  |  |  | 0
| Joints sawed, grooved, or formed by metal plates? 1/4 in. joint @ 10-ft. spacing. 2 in. minimum depth. Match joints if integral with concrete pavement. Document joint depth. | 609.06A |  |  | Required |  | 0
| Joint spacing measured. Document joint spacing. | 609.06A |  |  | Required |  | 0
| Slip form equipment consistently providing desired shape with no edge slumping? | 609.06C |  |  |  |  | 0
| Finishing uniform with no water added to the surface? | 609.06D |  |  |  |  | 0
| Uniform white curing compound placed? | 609.06E |  |  |  |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.