## Inspection Checklist
Ohio Department of Transportation, Division of Construction Management | [6 empty] | Y
Inspection Quality Checklist | [6 empty] | N
Item 626 Barrier Reflectors
Header Section
Alt ID |  | Co/Rt/Sec |  | Cont ID
Name |  | Date Inspected |  | PLN
Checklist Section
Check if Inspected | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
Construction
| Did the Engineer approve the layout before installation of the reflectors? | 626.03
| Did the Contractor furnish reflectors at the beginning and the end of all barrier runs and at least one additional point evenly spaced between the termini? | 626.03
| Was the reflectors spaced at 100 feet on tangents and on curves of less than 5 degrees? | 626.03
| Was the reflectors spaced at 50 feet for curves of greater than 5 degrees? | 626.03
| On concrete barriers, retaining walls, and bridge parapets, did the Contractor place the top of the reflector so its height is 26 inches above the near edge of pavement, except that the top of the reflector is at least 3 inches below the top of the concrete barrier? | 626.04
| Is the guardrail blockout reflector installed on top of the blockout or on the side of the blockout away from traffic? | 626.04
| Is the guardrail blockout reflector installed on the top or side of the blockout nearest the edge of pavement? | 626.04
| Is the guardrail blockout reflector installed so that the reflective surface is above the guardrail? | 626.04
| For guardrail blockout reflectors that are installed on top of the blockout, is the reflective face angled approximately 5 degrees towards the nearest travel lane? | 626.04
| Is the reflector face clean and free of dust, dirt, adhesive, or any foreign material after installation? | 626.04
| Except if mounted on a guardrail blockout, is the reflective face of one-way reflectors rotated upward from the vertical (or plumb) position 2 to 3 degrees to facilitate "rain washing" of the reflector face? | 626.04
Construction cont'd
| Are barrier reflectors the same color as the adjacent edge line? | 626.04
| Did the Contractor use one-way and bi-directional barrier reflectors in accordance with the table in 626.04? | 626.04
Comments Section
Inspection Guidance / Instruction Section
Provide comments for non-compliant work.
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check

## Sheet1
626.02 |  | Materials. Furnish materials conforming to:
Barrier Reflectors............................................................................. 726.01
Conform to the manufacturer's recommendations for corrosion resistant fasteners, brackets, or adhesives.
Use barrier reflectors that are mountable on guardrail blockouts, concrete barriers, retaining walls, and bridge parapets. For wall or parapet mount, the barrier reflector may not extend further than 5 inches (125 mm) in a horizontal direction towards the traffic lanes.
626.03 | Layout. Lay out all locations to ensure proper placement. The Engineer will approve the layout before installation of the reflectors.
Furnish reflectors at the beginning and the end of all barrier runs and at least one additional point evenly spaced between the termini. Space the reflectors at 100 feet (30 m) on tangents and on curves of less than 5 degrees (more than 350 m radius). Space the reflectors at 50 feet (15 m) for curves of greater than 5 degrees (350 m radius or less).
The Contractor may vary the spacing on tangents and curves of less than 5 degrees (more than 350 m radius) from 65 feet to 125 feet (20 m to 40 m) in the final 250 feet (80 m) to achieve even spacing of the reflectors.
If using a buffer end section or similar device on the end of the guardrail, place the first reflector so that it is visible to approaching traffic.
If tying guardrails, barriers, retaining walls, or bridge parapets together in a continuous run, use the total length of the run for determining the number and location of reflectors.
If installing a run of rail or barrier that is at varying distances from the edge of pavement, place a reflector where the run first approaches closest to the pavement. If this results in spacing greater than 125 feet (40 m), or 65 feet (20 m) in cases where 50-foot (15 m) standard spacing is required, install an additional reflector. If a nonreflectorized impact attenuator is in place, place an additional reflector on the face of the attenuator nearest to, and directed toward, approaching traffic.
626.04 | Installation. Attach the reflector with a suitable corrosion resistant fastener or adhesive conforming to the manufacturer's recommendations.
On concrete barriers, retaining walls, and bridge parapets, place the top of the reflector so its height is 26 inches (650 mm) above the near edge of pavement, except that the top of the reflector is at least 3 inches (75 mm) below the top of the concrete barrier.
Install guardrail blockout reflectors on top of the blockout or on the side of the blockout away from traffic. Install guardrail blockout reflectors on the top or side of the blockout nearest the edge of pavement. Install the guardrail blockout reflector so that the reflective surface is above the guardrail.
For guardrail blockout reflectors that are installed on top of the blockout, angle the reflective face approximately 5 degrees towards the nearest travel lane.
Remove loose concrete, rust, dirt, and other loose material from the surface of the concrete barrier using a wire brush. Remove dust created by wire brushing before applying adhesive. Apply adhesive to clean and moisture-free surfaces according to the manufacturer's recommendations.
Ensure that the reflector face is clean and free of dust, dirt, adhesive, or any foreign material after installation.
Except if mounted on a guardrail blockout, rotate the reflective face of one-way reflectors upward from the vertical (or plumb) position 2 to 3 degrees to facilitate "rain washing" of the reflector face.
When replacing reflectors on a concrete surface, locate the new reflector approximately 3 inches (75 mm) horizontally in either direction from the old location.
Use barrier reflectors that are the same color as the adjacent edge line.
Use one-way and bi-directional barrier reflectors in accordance with the following guidelines:
BARRIER REFLECTORS
COLOR & DIRECTION | One-Way Reflector | Bi-Directional Reflector
| Left Edge | Right Edge | Left Edge | Right Edge
Two-Lane, Two-Way |  |  | NA | W/W
Interchange Ramp |  |  | Y/R** | W/R
Multilane Undivided |  |  | NA | W/W
Multilane Divided
Multilane Divided with median barrier* |  | W | Y/Y
Multilane Divided without median barrier | NA | W
* concrete wall, guardrail or cable rail
** if median concrete wall is present
The Department will classify the reflectors as follows:
Mounting Location
Concrete barrier, retaining walls, or bridge parapets
Type 1 | Barrier Reflector
Guardrail
Type 2 | Corrosion Resistant Metal Guardrail Blockout Reflector
Type 3 | Acrylic or Polycarbonate Plastic Guardrail Blockout Reflector
Type 4 | Spring Loaded Guardrail Blockout Reflector
Type 5 | L-Type Guardrail Blockout Reflector