## Summary
Inefficiency Cost Summary
Project: | ODOT XXXXXX
Ct-Rt-Sec: | -
Ref # | Item # | Description | Inefficiency Cost
28 | 203E12000 | Excavation w/o Embankment | 16930.4019
31 | 509E12000 | Concrete Walk As Per Plan | 21822.7038
0
0
0
0
0
0
0
0
|  | Total : | 38753.1057

## Sheet2
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1: | Typical Excavation Crew
| 28 | 203E12000 | Excavation w/o Embankment | CY | [5 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[10 empty] | Operator A | 1 | 26.79 | 26.79 | 8.99 | 8.99
| Baseline - Uninterrupted Production | [8 empty] | Operator B | 1 | 26.21 | 26.21 | 8.99 | 8.99
[10 empty] | Labor Foreman | 1 | 23.89 | 23.89 | 6.09 | 6.09
[10 empty] | Laborers (2) | 2 | 22.44 | 44.88 | 6.09 | 12.18
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | 2017-07-18 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 370 | CY | 8 | 46.25 | A1250 |  |  | 0 | 0 | 0 | 0 | 0
1 | 2017-07-19 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 402 | CY | 8 | 50.25 | A3420 |  | Total Manhours/Crew Hours: | 5 |  | 121.77 |  | 36.25
1 | 2017-07-20 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 371 | CY | 6 | 61.8333 | A3460
1 | 2017-07-21 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 355 | CY | 8.5 | 41.7647 | A4512
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 121.77
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 36.25
[13 empty] | Plus….. | 22% | 26.7894
[13 empty] | Plus….. | 38% | 60.0476
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 244.857
4 | [9 empty] | Equipment | Total Hours | Daily Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 1498 | CY | 30.5 | 200.098 |  |  | Cat 325 Excavator | 1 | 53.58 | 39.9 |  | 93.48
[7 empty] | ( a ) |  |  | Loader | 0.5 | 22.21 | 20.55 |  | 21.38
|  |  | Ave Base Uninterryupted | 374.5 | CY | 7.625 | 49.1148 |  |  | JD 710 Backhoe | 0.5 | 29.66 | 25.2 |  | 27.43
[10 empty] | Pickup Truck | 1 | 5 | 0 |  | 5
[10 empty] | Survey Van | 1 | 3.75 | 6.45 |  | 10.2
0
0
0
[11 empty] | Total Equip Costs……………. |  |  |  | 157.49
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 402.347
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
| 2017-08-25 | 1 | Sta. 73 + 78 LT & RT | 210 | CY | 8 | 26.25 | A3456 | Issue 2 | 46.55% |  | 3.7243 | Crew #1: | 402.347 | 1498.4606
| 2017-08-26 | 2 | Sta. 73 + 78 LT & RT | 200 | CY | 9 | 22.2222 | A3457 | Issue 3 | 54.75% |  | 4.9279 | Crew #1: | 402.347 | 1982.7273
| 2017-08-27 | 3 | Sta. 73 + 78 LT & RT | 256 | CY | 8 | 32 | A3458 | Issue 4 | 34.85% |  | 2.7877 | Crew #1: | 402.347 | 1121.6296
| 2017-08-28 | 4 | Sta. 73 + 78 LT & RT | 235 | CY | 8.5 | 27.6471 | A3459 | Issue 5 | 43.71% |  | 3.7153 | Crew #1: | 402.347 | 1494.8346
| 2017-08-29 | 5 | Sta. 73 + 78 LT & RT | 245 | CY | 8 | 30.625 | A3460 | Issue 6 | 37.65% |  | 3.0117 | Crew #1: | 402.347 | 1211.7413
| 2017-08-30 | 6 | Sta. 73 + 78 LT & RT | 278 | CY | 8 | 34.75 | A3461 | Issue 7 | 29.25% |  | 2.3398 | Crew #1: | 402.347 | 941.406
| 2017-08-31 | 7 | Sta. 73 + 78 LT & RT | 258 | CY | 8.5 | 30.3529 | A3462 | Issue 8 | 38.2% |  | 3.247 | Crew #1: | 402.347 | 1306.4191
| 2017-09-01 | 8 | Sta. 73 + 78 LT & RT | 236 | CY | 8.5 | 27.7647 | A3463 | Issue 9 | 43.47% |  | 3.6949 | Crew #1: | 402.347 | 1486.6426
| 2017-09-02 | 9 | Sta. 73 + 78 LT & RT | 259 | CY | 8.5 | 30.4706 | A3464 | Issue 10 | 37.96% |  | 3.2266 | Crew #1: | 402.347 | 1298.2271
| 2017-09-03 | 10 | Sta. 73 + 78 LT & RT | 254 | CY | 9 | 28.2222 | A3465 | Issue 11 | 42.54% |  | 3.8284 | Crew #1: | 402.347 | 1540.3605
| 2017-09-04 | 11 | Sta. 73 + 78 LT & RT | 258 | CY | 9 | 28.6667 | A3466 | Issue 12 | 41.63% |  | 3.747 | Crew #1: | 402.347 | 1507.5926
| 2017-09-05 | 12 | Sta. 73 + 78 LT & RT | 254 | CY | 9 | 28.2222 | A3467 | Issue 13 | 42.54% |  | 3.8284 | Crew #1: | 402.347 | 1540.3605
|  |  | Total Interrupted…………………… | 2943 | CY | 102 | [6 empty] | Total Cost……………………… |  | 16930.4019

## Sheet3
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1: | Typical Concrete Crew
| 31 | 509E12000 | Concrete Walk As Per Plan | SY | [5 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[12 empty] | 26.79 | 0 | 8.99 | 0
| Baseline - Uninterrupted Production | [8 empty] | Operator B | 1 | 26.21 | 26.21 | 8.99 | 8.99
[10 empty] | Labor Foreman | 1 | 23.89 | 23.89 | 6.09 | 6.09
[10 empty] | Laborers (5) | 5 | 22.44 | 112.2 | 6.09 | 30.45
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | 2017-07-18 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 370 | SY | 8 | 46.25 | A1250 |  |  | 0 | 0 | 0 | 0 | 0
1 | 2017-07-19 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 402 | SY | 8 | 50.25 | A3420 |  | Total Manhours/Crew Hours: | 7 |  | 162.3 |  | 45.53
1 | 2017-07-20 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 371 | SY | 6 | 61.8333 | A3460
1 | 2017-07-21 | Sta. 33 + 75 - Sta. 30 + 50 RT (S. side Syc. Towne Plaza) |  | 355 | SY | 8.5 | 41.7647 | A4512
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 162.3
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 45.53
[13 empty] | Plus….. | 22% | 35.706
[13 empty] | Plus….. | 38% | 78.9754
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 322.5114
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 1498 | SY | 30.5 | 200.098 |  |  | Cat 325 Excavator | 1 | 53.58 | 39.9 |  | 93.48
[7 empty] | ( a ) |  |  | Loader | 1 | 22.21 | 20.55 |  | 42.76
|  |  | Ave Base Uninterryupted | 374.5 | SY | 7.625 | 49.1148 |  |  | JD 710 Backhoe | 1 | 29.66 | 25.2 |  | 54.86
[10 empty] | Pickup Truck | 1 | 5 | 0 |  | 5
[12 empty] | 3.75 | 6.45 |  | 0
0
0
0
[11 empty] | Total Equip Costs……………. |  |  |  | 196.1
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 518.6114
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
| 2017-08-25 | 1 | Sta. 73 + 78 LT & RT | 210 | SY | 8 | 26.25 | A3456 | Issue 2 | 46.55% |  | 3.7243 | Crew #1: | 518.6114 | 1931.464
| 2017-08-26 | 2 | Sta. 73 + 78 LT & RT | 200 | SY | 9 | 22.2222 | A3457 | Issue 3 | 54.75% |  | 4.9279 | Crew #1: | 518.6114 | 2555.6671
| 2017-08-27 | 3 | Sta. 73 + 78 LT & RT | 256 | SY | 8 | 32 | A3458 | Issue 4 | 34.85% |  | 2.7877 | Crew #1: | 518.6114 | 1445.7418
| 2017-08-28 | 4 | Sta. 73 + 78 LT & RT | 235 | SY | 8.5 | 27.6471 | A3459 | Issue 5 | 43.71% |  | 3.7153 | Crew #1: | 518.6114 | 1926.7902
| 2017-08-29 | 5 | Sta. 73 + 78 LT & RT | 245 | SY | 8 | 30.625 | A3460 | Issue 6 | 37.65% |  | 3.0117 | Crew #1: | 518.6114 | 1561.8927
| 2017-08-30 | 6 | Sta. 73 + 78 LT & RT | 278 | SY | 8 | 34.75 | A3461 | Issue 7 | 29.25% |  | 2.3398 | Crew #1: | 518.6114 | 1213.4399
| 2017-08-31 | 7 | Sta. 73 + 78 LT & RT | 258 | SY | 8.5 | 30.3529 | A3462 | Issue 8 | 38.2% |  | 3.247 | Crew #1: | 518.6114 | 1683.9291
| 2017-09-01 | 8 | Sta. 73 + 78 LT & RT | 236 | SY | 8.5 | 27.7647 | A3463 | Issue 9 | 43.47% |  | 3.6949 | Crew #1: | 518.6114 | 1916.231
| 2017-09-02 | 9 | Sta. 73 + 78 LT & RT | 259 | SY | 8.5 | 30.4706 | A3464 | Issue 10 | 37.96% |  | 3.2266 | Crew #1: | 518.6114 | 1673.37
| 2017-09-03 | 10 | Sta. 73 + 78 LT & RT | 254 | SY | 9 | 28.2222 | A3465 | Issue 11 | 42.54% |  | 3.8284 | Crew #1: | 518.6114 | 1985.4715
| 2017-09-04 | 11 | Sta. 73 + 78 LT & RT | 258 | SY | 9 | 28.6667 | A3466 | Issue 12 | 41.63% |  | 3.747 | Crew #1: | 518.6114 | 1943.2348
| 2017-09-05 | 12 | Sta. 73 + 78 LT & RT | 254 | SY | 9 | 28.2222 | A3467 | Issue 13 | 42.54% |  | 3.8284 | Crew #1: | 518.6114 | 1985.4715
|  |  | Total Interrupted…………………… | 2943 | SY | 102 | [6 empty] | Total Cost……………………… |  | 21822.7038

## Sheet4
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0

## Sheet5
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0

## Sheet6
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0

## Sheet7
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0

## Sheet8
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0

## Sheet9
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0

## Sheet10
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0

## Sheet11
| Project: | ODOT XXXXXX
| Ct-Rt-Sec: | -
| Ref # | Item # | Description | Unit | [5 empty] | Crew #1:
[10 empty] | Classification | Mhrs./ Crew-Hr. | Rate Paid | Wage Amount | Fringes / Hour | Total Fringes
[11 empty] | 0 | 0 | 0 | 0 | 0
| Baseline - Uninterrupted Production | [9 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
| Date | Location |  | Quanity | Unit | Actual Crew Hrs | Production Unit/Hour | Schedule Activity ID |  |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0
1 | [10 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | Total Manhours/Crew Hours: | 0 |  | 0 |  | 0
1
1
[10 empty] | Labor Tax Beakdown: |  |  | Total Wages…… |  | 0
[10 empty] | Unemployment,FICA,WC…. | 22% |  | Total Fringes…… |  | 0
[13 empty] | Plus….. | 22% | 0
[13 empty] | Plus….. | 38% | 0
22%
[10 empty] | Overhead & Profit % | 38% |  | Total Labor Costs…… |  | 0
4 | [9 empty] | Equipment | Total Hours | Rental Rate | Operating Costs |  | Total Amount
|  |  | Total Base Uninterrupted…….. | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
[7 empty] | ( a ) |  |  |  | 0 | 0 | 0 |  | 0
|  |  | Ave Base Uninterryupted | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | 0 | 0 | 0 |  | 0
[11 empty] | Total Equip Costs……………. |  |  |  | 0
[10 empty] | Total Cost per Crew Hr. …………………………………………………………………………………………………………………… |  |  |  |  | 0
| Impacted - Interrupdted Production | [8 empty] | Inefficiency Costs
[7 empty] | ( b ) |  |  | (a - b ) / a
| Date | Ineff # | Location | Quantitiy | Unit | Actual Crew-Hrs | Production Unit/Hr. | Schedule Activity ID | Interference Description | % Loss |  | Crew Hrs. | Crew # | TotalCost / Crew-Hour | Ineff Costs
|  |  | Total Interrupted…………………… | 0 | 0 | 0 | [6 empty] | Total Cost……………………… |  | 0