LPA Documentation Checklist

Documentation should support an audit. If it isn’t documented, it didn’t happen.

- Daily Diary. The daily diary should be up to date and contain the following information:

  - All work performed by the contractor

  - List of equipment

  - Project personnel and hours worked

  - Pay quantities. Check to see that they match the calculated values and how the pay quantity is determined.

  - Daily weather conditions (weather affects the majority of work performed and is needed to determine time extensions based upon weather delays)

  - Special notes and instructions to the contractor

  - Any unusual events occurring on or adjacent to the project, even those not related to construction

- Measurements

  - Measurements should be shown either in the daily diary or some other form of documentation. The inspector must indicate that the measurement is an actual field measurement. Even if the measurement is a plan dimension, note that the dimension has been field verified.

  - If the measurements in the diary are transferred from other documentation, has the engineer indicated where to find that documentation?

- Calculations

  - Do the calculations use the measured or plan dimensions? This should be indicated; field verification is required.

  - Note whether a tape is included with the calculations.

  - All calculations should include item of work, location, date and initials.

- Materials

  - Is the inspector getting necessary documentation for the materials records? Documentation should provide for quality, quantity, and basis for payment.

  - How is the project manager organizing the materials documentation?

  - The project engineer must approve all materials and solve any deficiencies.

- Tickets

  - Each tickets must include: JMF, date, location, item and initials

  - Any sequence of tickets that are not in order or have tickets missing need to have a calculator tape verifying the accumulative total.

- Change Orders / Pricing for extra work

- Claims / Dispute Resolution

- Testing and Results

- Traffic

- Inspections

- Schedule and Completion Date / Time Extensions / Liquidated Damages

- Any plan changes

- Timeliness of payments

- Railroad or Utility Force Account

- Prevailing Wage, EEO, DBE (if applicable)