## Instructions
Asphalt Binder Price Adjustment Calculation Spreadsheet
for Proposal Note 534.
INSTRUCTIONS for using the calculator:
1 | Make sure the asphalt binder price indices are up to date on the "Data" tab, or download a new copy of the asphalt binder price adjustment calculator from the O drive under O:\Construction\Price Index Information.
2 | Enter the project number, the county, route, and section, and the PID
3 | Enter the date the project was bid. Make sure that this is a vaild date format in Excel, such as 1/15/2010.
4 | Enter the completion date for the project (use the postponed completion date if there is one.) Make sure that this is a valid date format in Excel. If the placing date is later than the completion date, the calculator will use the date that results in the lower placing index (PI) value.
5 | On each line, enter data in the cells shaded yellow. The data for percent virgin bitumen, date placed, and quantity placed are required. The reference number, part code, item number, and JMF are not required, but using these will help others who may review the price adjustment calculation.
6 | There are 22 lines available for data input. If you need more, use an additional copy of the worksheet, rather than trying to insert more lines.
7 | If the words "Error" show in the column for "Eligible for PA", then the Data tab is not up to date and does not include an index value for the date placed.
INSTRUCTIONS for modifying the spreadsheet:
1 | The price adjustment worksheets are protected. To edit these sheets, first unprotect the worksheet by clicking on "Review", then "Unprotect Sheet". There is no password.

## PN 534 Asphalt Price Adj. Calc
OHIO DEPARTMENT OF TRANSPORTATION
Asphalt Binder Price Adjustment Calculations
For Proposal Note 534
[11 empty] | Date calculated: | 2025-05-01
[11 empty] | Data entered by: | P.Engineer
Project number . . . . . . . . . . . . . . . |  |  |  |  | 0061-09 | C-R-S: | CNT-70-2.50 |  |  |  | PID: | 12345
Project letting (bid) date . . . . . . . . . . . |  |  |  |  | 2010-06-01 |  |  | BI | Bidding Index, $/ton
Current completion date . . . . . . . . . . . . . |  |  |  |  | 2011-09-30 |  |  | 481.67
Ref. No. | Part Code | Item No. | JMF | % virgin bitumen | Date placed | Quantity placed tons | C | Placing Index PI $/ton | PI BI | Eligible for PA | Notes | Price Adjustment (PA)
151 | 1 | 880 | W322432 | 2.5 | 2010-06-01 | 25066.56 | 12.0418 | 460.83 | 0.95673 | No | a | 0
151 | 1 | 880 | W322497 | 2 | 2010-06-02 | 209.2 | 9.6334 | 460.83 | 0.95673 | No | a | 0
653 | 8 | 880 | W322432 | 2.5 | 2010-06-08 | 15578.57 | 12.0418 | 460.83 | 0.95673 | No | a | 0
653 | 12 | 880 | W322432 | 2.5 | 2010-06-08 | 15578.57 | 12.0418 | 460.83 | 0.95673 | No | a | 0
1013 | 8 | 615 | B448378 | 4.8 | 2010-06-10 | 2 | 23.1202 | 460.83 | 0.95673 | No | a | 0
0
251 | 5 | 615 | W448377 | 3 | 2010-07-05 | 142.34 | 14.4501 | 452.5 | 0.93944 | No | a | 0
653 | 8 | 880 | W322432 | 2.5 | 2010-07-06 | 8000 | 12.0418 | 452.5 | 0.93944 | No | a | 0
653 | 12 | 880 | W322432 | 2.5 | 2010-07-06 | 8046.22 | 12.0418 | 452.5 | 0.93944 | No | a | 0
837 | 8 | 614 | W322432 | 2.5 | 2010-07-07 | 85.35 | 12.0418 | 452.5 | 0.93944 | No | a | 0
837 | 8 | 614 | W448377 | 3 | 2010-07-08 | 962.24 | 14.4501 | 452.5 | 0.93944 | No | a | 0
861 | 8 | 615 | W100020 | 3.2 | 2010-07-15 | 197.94 | 15.4134 | 452.5 | 0.93944 | No | a | 0
861 | 8 | 615 | W322432 | 2.5 | 2010-07-16 | 171.69 | 12.0418 | 452.5 | 0.93944 | No | a | 0
861 | 8 | 615 | W448378 | 4.8 | 2010-07-19 | 150.83 | 23.1202 | 452.5 | 0.93944 | No | a | 0
0
0
0
0
0
0
0
0
Notes: | [9 empty] | Total Asphalt Binder Price Adjustment |  | 0
a - Not eligible for PA because percent change in index was not greater than 10 percent.
b - Date placed was after the current completion date, so the date that results in the lower PI value was used.
Version 1.2
Enter data in cells shaded yellow. Make sure the asphalt binder price indices are up to date on the "Data" tab.
If "Error" shows in column for "Eligible for PA", then the Data tab does not include an index value for the date placed.

## Data
Asphalt Indexs
| Bidding Index (BI) | Placing Index (PI)
Month | $/ton | $/ton | Equation objects are included below so that the equations can be
2009-08-01 | 390 | 377.5 | changed in the future to reflect any future edits to the proposal note.
2009-09-01 | 377.5 | 368.33 | The equations on the calculator sheet were converted to images for compatibility
2009-10-01 | 368.33 | 388.33 | with older versions of Excel. To convert the equations, select all three, copy them,
2009-11-01 | 388.33 | 448.33 | and then "Paste, Special" as a picture (enhanced metafile).
2009-12-01 | 448.33 | 486.67
2010-01-01 | 486.67 | 492.5
2010-02-01 | 492.5 | 500.83
2010-03-01 | 500.83 | 498.33
2010-04-01 | 498.33 | 494.17
2010-05-01 | 494.17 | 481.67
2010-06-01 | 481.67 | 460.83
2010-07-01 | 460.83 | 452.5
2010-08-01 | 452.5 | 448.33
2010-09-01 | 448.33 | 448.33
2010-10-01 | 448.33 | 450.83
2010-11-01 | 450.83 | 455
2010-12-01 | 455 | 455
2011-01-01 | 455 | 471.67
2011-02-01 | 471.67 | 474.16
2011-03-01 | 474.16 | 495.83
2011-04-01 | 495.83 | 531.67
2011-05-01 | 531.67 | 533.33
2011-06-01 | 533.33 | 530.83
2011-07-01 | 530.83 | 519.16
2011-08-01 | 519.16 | 505
2011-09-01 | 505 | 489.16
2011-10-01 | 489.16 | 485
2011-11-01 | 485 | 485
2011-12-01 | 485 | 523.33
2012-01-01 | 523.33 | 548.33
2012-02-01 | 548.33 | 570
2012-03-01 | 570 | 570
2012-04-01 | 570 | 580.83
2012-05-01 | 580.83 | 581.67
2012-06-01 | 581.67 | 576.67
2012-07-01 | 576.67 | 566.67
2012-08-01 | 566.67 | 555
2012-09-01 | 555 | 552.5
2012-10-01 | 552.5 | 552.5
2012-11-01 | 552.5 | 552.5
2012-12-01 | 552.5 | 552.5
2013-01-01 | 552.5 | 533.33
2013-02-01 | 533.33 | 533.33
2013-03-01 | 533.33 | 532.5
2013-04-01 | 532.5 | 532.5
2013-05-01 | 532.5 | 534.17
2013-06-01 | 534.17 | 534.17
2013-07-01 | 534.17 | 535.83
2013-08-01 | 535.83 | 535.83
2013-09-01 | 535.83 | 535
2013-10-01 | 535 | 529.17
2013-11-01 | 529.17 | 529.17
2013-12-01 | 529.17 | 529.17
2014-01-01 | 529.17 | 529.17
2014-02-01 | 529.17 | 529.17
2014-03-01 | 529.17 | 529.17
2014-04-01 | 529.17 | 534.17
2014-05-01 | 534.17 | 538.33
2014-06-01 | 538.33 | 556.67
2014-07-01 | 556.67 | 570
2014-08-01 | 570 | 574.17
2014-09-01 | 574.17 | 578.33
2014-10-01 | 578.33 | 575.83
2014-11-01 | 575.83 | 559.17
2014-12-01 | 559.17 | 550.83
2015-01-01 | 550.83 | 502.5
2015-02-01 | 502.5 | 475.83
2015-03-01 | 475.83 | 455
2015-04-01 | 455 | 443.33
2015-05-01 | 443.33 | 442.5
2015-06-01 | 442.5 | 442.5
2015-07-01 | 442.5 | 442.5
2015-08-01 | 442.5 | 442.5
2015-09-01 | 442.5 | 435.83
2015-10-01 | 435.83 | 402.5
2015-11-01 | 402.5 | 383.33
2015-12-01 | 383.33 | 376.67
2016-01-01 | 376.67 | 360
2016-02-01 | 360 | 326.67
2016-03-01 | 326.67 | 320.83
2016-04-01 | 320.83 | 320.83
2016-05-01 | 320.83 | 308.33
2016-06-01 | 308.33 | 305.83
2016-07-01 | 305.83 | 303.33
2016-08-01 | 303.33 | 301.67
2016-09-01 | 301.67 | 297.5
2016-10-01 | 297.5 | 297.5
2016-11-01 | 297.5 | 297.5
2016-12-01 | 297.5 | 297.5
2017-01-01 | 297.5 | 299.17
2017-02-01 | 299.17 | 306.67
2017-03-01 | 306.67 | 330
2017-04-01 | 330 | 330
2017-05-01 | 330 | 330
2017-06-01 | 330 | 328.33
2017-07-01 | 328.33 | 328.33
2017-08-01 | 328.33 | 328.33
2017-09-01 | 328.33 | 328.33
2017-10-01 | 328.33 | 328.33
2017-11-01 | 328.33 | 328.33
2017-12-01 | 328.33 | 337.5
2018-01-01 | 337.5 | 345.83
2018-02-01 | 345.83 | 350.83
2018-03-01 | 350.83 | 369.17
2018-04-01 | 369.17 | 385.83
2018-05-01 | 385.83 | 409.17
2018-06-01 | 409.17 | 453.33
2018-07-01 | 453.33 | 487.5
2018-08-01 | 487.5 | 511.67
2018-09-01 | 511.67 | 516.67
2018-10-01 | 516.67 | 520
2018-11-01 | 520 | 513.33
2018-12-01 | 513.33 | 486.67
2019-01-01 | 486.67 | 475
2019-02-01 | 475 | 475
2019-03-01 | 475 | 475
2019-04-01 | 475 | 484.17
2019-05-01 | 484.17 | 493.33
2019-06-01 | 493.33 | 493.33
2019-07-01 | 493.33 | 493.33
2019-08-01 | 493.33 | 479.17
2019-09-01 | 479.17 | 469.17
2019-10-01 | 469.17 | 454.17
2019-11-01 | 454.17 | 442.5
2019-12-01 | 442.5 | 436.67
2020-01-01 | 436.67 | 436.67
2020-02-01 | 436.67 | 436.67
2020-03-01 | 436.67 | 420
2020-04-01 | 420 | 410.83
2020-05-01 | 410.83 | 396.67
2020-06-20 | 396.67 | 396.67
2020-07-01 | 396.67 | 396.67
2020-08-01 | 396.67 | 396.67
2020-09-01 | 396.67 | 393.33
2020-10-01 | 393.33 | 388.33
2020-11-01 | 388.33 | 388.33
2020-12-01 | 388.33 | 386.67
2021-01-01 | 386.67 | 393.33
2021-02-01 | 393.33 | 416.67
2021-03-01 | 416.67 | 426.67
2021-04-01 | 426.67 | 442.5
2021-05-01 | 442.5 | 449.17
2021-06-01 | 449.17 | 449.17
2021-07-01 | 449.17 | 455.83
2021-08-01 | 455.83 | 465.83
2021-09-01 | 465.83 | 465.83
2021-10-01 | 465.83 | 465.83
2021-11-01 | 465.83 | 483.33
2021-12-01 | 483.33 | 491.67
2022-01-01 | 491.67 | 493.33
2022-02-01 | 493.33 | 526.67
2022-03-01 | 526.67 | 584.17
2022-04-01 | 584.17 | 659.17
2022-05-01 | 659.17 | 698.33
2022-06-01 | 698.33 | 723.33
2022-07-01 | 723.33 | 741.67
2022-08-01 | 741.67 | 736.67
2022-09-01 | 736.67 | 692.5
2022-10-01 | 692.5 | 620.83
2022-11-01 | 620.83 | 600
2022-12-01 | 600 | 591.67
2023-01-01 | 591.67 | 591.67
2023-02-02 | 591.67 | 591.67
2023-03-01 | 591.67 | 592.5
2023-04-01 | 592.5 | 592.5
2023-05-01 | 592.5 | 592.5
2023-06-01 | 592.5 | 592.5
2023-07-01 | 592.5 | 592.5
2023-08-01 | 592.5 | 592.5
2023-09-01 | 592.5 | 584.17
2023-10-01 | 584.17 | 584.17
2023-11-01 | 584.17 | 584.17
2023-12-01 | 584.17 | 582.5
2024-01-01 | 582.5 | 582.5
2024-02-01 | 582.5 | 582.5
2024-03-01 | 582.5 | 579.17
2024-04-01 | 579.17 | 579.17
2024-05-01 | 579.17 | 579.17
2024-06-01 | 579.17 | 575.83
2024-07-01 | 575.83 | 574.17
2024-08-01 | 574.17 | 556.67
2024-09-01 | 556.67 | 526.67
2024-10-01 | 526.67 | 526.67
2024-11-01 | 526.67 | 526.67
2024-12-01 | 526.67 | 526.67
2025-01-01 | 526.67 | 529.1667
2025-02-01 | 529.1667 | 529.1667
2025-03-25 | 529.1667 | 529.1667
2025-04-25 | 529.1667 | 529.1667
2025-05-25 | 529.1667 | 529.1667
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
"If, " "PI" /"BI" "<0.9 then PA=" ["PI" /"BI" "−0.9" ]"×C×Q "
"If, 0.9≤" "PI" /"BI" "≤1.1 then no asphalt binder price adjustment"
"If, " "PI" /"BI" ">1.1 then PA=" ["PI" /"BI" "−1.1" ]"×C×Q "