## No Lanes Closed
Work Zone User Cost Calculations
No Lanes Closed
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Section:
Length of Work Zone (Miles):
Original Posted Speed (MPH):
Work Zone Posted Speed (MPH):
Duration of Work Zone (Days):
Calculated Values:
Cost per Hour:
Travel Time Pre-Work Zone (Secs):
Travel Time During Work Zone (Secs):
Delay (Secs):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Work Zone Duration:
Total Delay Cost for Work Zone Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Spreadsheet protection password: CONSTRUCTION
Date Calculated: | 2026-07-30

## Detour (Actual Drive Time)
Work Zone User Cost Calculations
Detour (Using Actual Drive Time)
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Detoured Section:
Time to Drive Normal Route (Min):
Time to Drive Detour Route (Min):
Duration of Closure (Days):
Calculated Values:
Cost per Hour:
Delay (Min):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Closure Duration:
Total Delay Cost for Closure Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Spreadsheet protection password: CONSTRUCTION
Date Calculated: | 2026-07-30

## Detour (Distance & Speed)
Work Zone User Cost Calculations
Detour (Using Distance & Speed)
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Detoured Section:
Length of Normal Route (Miles):
Length of Detour Route (Miles):
Avg Posted Speed on Normal Route (MPH):
Avg Posted Speed on Detour Route (MPH):
Duration of Closure (Days):
Calculated Values:
Cost per Hour:
Travel Time Along Normal Route (Secs):
Travel Time Along Detour Route (Secs):
Delay (Secs):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Closure Duration:
Total Delay Cost for Closure Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Spreadsheet protection password: CONSTRUCTION
Date Calculated: | 2026-07-30

## CPI Data
Table 24. Historical Consumer Price Index for All Urban Consumers (CPI-U): U. S. city average, all items-Continued
www.bls.gov/cpi
CPI Year | Semiannual Average |  | Annual Average | % change from 2008 Annual Average | User Cost/Hour |  | Project Year | Actual
| 1st half | 2nd half |  |  | Car | Truck
2008 | 214.429 | 216.177 | 215.303 |  | 19.22 | 51.88 | 2009
2009 | 213.139 | 215.935 | 214.537 | -0.3558% | 19.1516 | 51.6954 | 2010
2010 | 217.535 | 218.576 | 218.056 | 1.279% | 19.4658 | 52.5434 | 2011
2011 | 223.598 | 226.28 | 224.939 | 4.476% | 20.0802 | 54.2019 | 2012
2012 | 228.85 | 230.338 | 229.594 | 6.638% | 20.4958 | 55.3236 | 2013
2013 | 232.366 | 233.548 | 232.957 | 8.2% | 20.796 | 56.134 | 2014
2014 | 236.384 | 237.088 | 236.736 | 9.955% | 21.1333 | 57.0446 | 2015
2015 | 236.265 | 237.769 | 237.017 | 10.09% | 21.1584 | 57.1123 | 2016
2016 | 238.778 | 241.237 | 240.007 | 11.47% | 21.4253 | 57.8327 | 2017
2017 | 244.076 | 246.163 | 245.12 | 13.85% | 21.8817 | 59.0648 | 2018
2018 |  |  |  |  | 22.3194 | 60.2461 | 2019 | Estimated at 3% increase per year
2019 |  |  |  |  | 22.7658 | 61.451 | 2020
2020 |  |  |  |  | 23.2211 | 62.68 | 2021
2021 |  |  |  |  | 23.6855 | 63.9336 | 2022
2022 |  |  |  |  | 24.1592 | 65.2123 | 2023
2023 |  |  |  |  | 24.6424 | 66.5165 | 2024
2024 |  |  |  |  | 25.1353 | 67.8469 | 2025
2025 |  |  |  |  | 25.638 | 69.2038 | 2026
2026 |  |  |  |  | 26.1507 | 70.5879 | 2027
2027 |  |  |  |  | 26.6737 | 71.9996 | 2028
2028 |  |  |  |  | 27.2072 | 73.4396 | 2029
2029 |  |  |  |  | 27.7513 | 74.9084 | 2030
Information Last Updated: 1/31/18

## FAQ
1) What is the latest adjustment factor for car and truck road user costs for use with the road user cost spreadsheet?
The passenger car and truck costs shown in the Innovative Contracting Manual (ICM) are for 2008 values (provided to ODOT in early 2010 by FHWA Traffic Monitoring & Survey Division). To obtain the current year values, use the Consumer Price Index (CPI) and calculate a ratio to bring the values up to date. The CPI can be found here at:
www.bls.gov/cpi
(Bureau of Labor Statistics website has since been changed. As of 1/31/18, Table 24 can be found at the link below by clicking "Historical CPI-U" under the latest completed year.)
https://www.bls.gov/cpi/tables/supplemental-files/home.htm
Within the PDF report scroll to Table 24 ("Historical Consumer Price Index for All Urban Consumers (CPI-U): U.S. city average, all items - Continued"; the last page of Table 24). We use the annual average values rather than the monthly or semi-annual values to avoid potential volatility of the month-to-month factors.
Example: | What passenger car and truck costs are to be used for road user costs for 2018 (project calendar year 2018)?
The 2008 values given in the ICM are $19.22/hour for Passenger Cars and $51.88/hour for Trucks.
The annual average CPI for 2008, per Table 24 in the CPI, is $215.303.
The most recent annual average CPI published is for 2017 (as of 1/31/18). We use the 2017 annual average value for 2018.
The annual average CPI for 2017, per Table 24 in the CPI, is $245.120.
The 2017 to 2008 ratio ($245.120/$215.303) is 1.1385. (…or the 2017 value is 13.85% higher than the 2008 value.)
2018 Passenger Car Cost = (2008 Passenger Car Cost) x (2017 to 2008 Ratio) = $19.22/hour x 1.1385 = $21.88/hour
2018 Truck Cost = (2008 Truck Cost) x (2017 to 2008 Ratio) = $51.88/hour x 1.1385 = $59.06/hour
2) What if I am calculating road user costs for a future year? Do the passenger car and truck costs change? If so, how?
If calculating road user costs for a future year for a project, the values can be increased by an assumed percentage to obtain a projected future value. As a rule of thumb we use 2% per year based on the recent average over the past decade or so (based on the values shown on the last page of Table 24 under "Percent change from previous, Annual Avg").
Example: | What passenger car and truck costs are to be used for road user costs for project calendar year 2020 (as of 2018)?
Calculate or obtain the current year values (in this example, 2018; example is above under #1).
2018 Passenger Car Cost = $21.88/hour
2018 Truck Cost = $59.06/hour
Project the current year values (2018) two years forward to 2020 project year values, assuming an approximate 2% per year increase.
2020 Passenger Car Cost = (2018 Passenger Car Cost) x ((1+(2% per year))^2 years) = $21.88/hour x ((1+(0.02))^2) = $22.77/hour
2020 Truck Cost = (2018 Truck Cost) x ((1+(2% per year))^2 years) = $59.06/hour x ((1+(0.02))^2) = $61.45/hour
3) Who do I contact for more information or with questions?
| Contact: | Emily.Willis@dot.ohio.gov | or | Duane.Soisson@dot.ohio.gov
Information Last Updated: 1/31/18