## No Lanes Closed (hidden)
Work Zone User Cost Calculations
No Lanes Closed
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Section:
Length of Work Zone (Miles):
Original Posted Speed (MPH):
Work Zone Posted Speed (MPH):
Duration of Work Zone (Days):
Calculated Values:
Cost per Hour:
Travel Time Pre-Work Zone (Secs):
Travel Time During Work Zone (Secs):
Delay (Secs):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Work Zone Duration:
Total Delay Cost for Work Zone Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Date Calculated: | 2026-07-28
Spreadsheet protection password: CONSTRUCTION

## Lane(s) Closed on Mainline
Work Zone User Cost Calculations
Lane(s) Closed on Mainline (Based on Matching PLCS Segment)
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
AADT (Per the Matching PLCS Segment):
% Trucks (Per the Matching PLCS Segment):
Lanes per Direction (Per the Matching PLCS Segment):
Calculated Values:
|  | Car | B/C Truck
User Cost per Vehicle:
Vehicles per Day (Directionally):
User Cost per Day by Vehicle Type (Directionally):
User Cost per Day (Directionally):
User Cost per Day per Lane (Directionally):
User Cost per Hour per Lane (Directionally):
User Cost per Minute per Lane (Directionally):
Max Disincentive per Minute per Lane (Directionally): |  | (MISSING INPUT)
Notes (description, PLCS segment reference, project phase reference, etc, as applicable):
Fill in all highlighted cells per the Permitted Lane Closure Schedule (PLCS) segment(s) that apply to the Construction Limits of the project. If more than one PLCS segment applies to the Construction Limits, each User Cost per PLCS segment shall be calculated seperately.
The rounded User Cost per Minute per Lane is the MAXIMUM that may be used as a disincentive. The resulting value is to be applied to the area within the project that matches the PLCS segment used to calculate the value.
Date Calculated: | 2026-07-28
Spreadsheet protection password: CONSTRUCTION
WHERE TO FIND THE APPLICABLE VALUES TO ENTER:
- AADT is the total volume in both directions and can be found as circled below per the applicable PLCS.
NOTE: Segments using Calculation Method A will show 0 for AADT. Use AADT from MS2 instead for these segments.
- % Trucks is an overall value for the day and can be found as circled below per the applicable PLCS.
- Lanes per Direction is the number of lanes preconstruction per direction and can be found as circled below per the applicable PLCS.
- Direction on the PLCS (shown circled below) represents where the resulting user cost applies within the associated project segment. For some PLCS segments this is "BOTH" and will apply to both directions of the associated project segment. Some PLCS segments are directional (e.g. "EAST", "NORTH", etc) and the resulting user cost based upon those PLCS segment(s) will apply only to the same direction of the associated project segment.

## Lane(s) Closed Calc Method (hidden)
$RUCTOTAL = ($RUCCARS + $RUCTRUCKS)*(#Minutes Closed)*(#Lanes Closed)
$RUCCARS = (CARS/(Minute*Lane))*($/CAR)
$RUCCARS = (((60000/2)*0.90) cars/(24 hr*60 min*3 lanes))*($21.88/car)
$RUCCARS = (6.25 cars/minute-lane)*($21.88/car)
$RUCCARS = $136.75/minute-lane
NOTE: Round $/minute-lane down to the nearest $5; $136.75/minute-lane = $135/minute-lane
$RUCCARS = $135/minute-lane
$RUCTRUCKS = (TRUCKS/Minute*Lane)*($/TRUCK)
$RUCTRUCKS = (((60000/2)*0.10) trucks/(24 hr*60 min*3 lanes)*($59.06/truck)
$RUCTRUCKS = (0.69 trucks/minute-lane)*($59.06/truck)
$RUCTRUCKS = ($41.01/minute-lane)
NOTE: Round $/minute-lane down to the nearest $5; $41.01/minute-lane = $40/minute-lane
$RUCTRUCKS = ($40/minute-lane)
$RUCTOTAL = ($135/minute-lane + $40/minute-lane)*(30 minutes closed)*(1 lane closed)
$RUCTOTAL = ($175/minute-lane)*(30 minutes closed)*(1 lane closed)
$RUCTOTAL = $5250
Information Last Updated: 10/23/18
Spreadsheet protection password: CONSTRUCTION
*
* Based upon how many vehicles would have passed this point in a given timeframe.
Example:
-60,000 AADT, 10% Trucks
-3 total lanes, 1 lane closed (3:2) for 30 minutes beyond permitted
-2018 Construction
Lane(s) Closed on Mainline Road User Cost Calculation Method and Assumptions
Assumptions Made to Simplify the Calculation:
-AADT divided by 2 to obtain a directional AADT (rather than using specific directional percentages).
-Directional AADT divided by 24 gives hourly total volume (rather than using hourly percentages).
-Equal lane utilization.
-Vehicles impacted by the lane closure are only those that would have traveled in the closed lane(s) had they been open (rather than also assessing impacts on vehicles that would have traveled in lane(s) that remained open and had to accomodate the traffic from the closed lane(s)).
-Same % trucks applicable throughout the day.

## Lane(s) Closed Violation Calc (hidden)
Work Zone Disincentive Calculator (Per Violation)
Lane(s) Closed on Mainline (Based on Matching PLCS Segment)
Project ID:
County-Route-Section:
User Input:
Fill out the Lane(s) Closed worksheet first.
Next, fill in the following highlighted cells.
Non-Allowable Lane Closure Start Time (HH:MM AM/PM):
Non-Allowable Lane Closure End Time (HH:MM AM/PM):
Total Non-Allowable Lane Closure Time (in Minutes):
Number of Lanes Closed:
Disincentive to be Applied (Per Matching PLCS Segment):
Fill in all highlighted cells for Work Zone Disincentive Calculator, per violation. Highlighted cells in the Disincentive calculator are for use during construction when the need arrises calculate the disincentive to be applied due to a non-allowable closure. If a violation occured that extended into more than one contiguous PLCS Segments, the Lane(s) Closed worksheet shall be filled in using the PLCS segment resulting in the highest User Cost per Minute per Lane impacted by the violation.
Date Calculated: | 2026-07-28
Spreadsheet protection password: CONSTRUCTION

## Lane Closed on 2-Ln System Ramp (hidden)
Work Zone User Cost Calculations |  |  |  | WORKSHEET UNDER CONSTRUCTION; DO NOT USE YET
Lane Closed on 2-Lane System Ramp
Project ID:
System Ramp:
User Input:
Construction Calendar Year:
Directional AADT (On the Directional Ramp):
% Trucks (On the Directional Ramp):
Number of Lanes (On the Directional Ramp):
Calculated Values:
|  | Car | B/C Truck
User Cost per Vehicle:
Vehicles per Day (On the Directional Ramp):
User Cost per Day by Vehicle Type (On the Directional Ramp):
User Cost per Day (On the Directional Ramp):
User Cost per Day per Lane (On the Directional Ramp):
User Cost per Hour per Lane (On the Directional Ramp):
User Cost per Minute per Lane (On the Directional Ramp):
Max Disincentive per Minute per Lane (On the Directional Ramp): |  | (MISSING INPUT)
Fill in all highlighted cells. If there is more than one system ramp impacted within the Construction Limits, each User Cost per system ramp shall be calculated seperately. System Ramp AADT and % Trucks (BC) can be found in MS2.
The rounded User Cost per Minute per Lane is the MAXIMUM that may be used as a disincentive. The resulting value is to be applied to the area within the project that matches the system ramp inputs used to calculate the value.
NOTE: Although mainline ramps are treated as a mainline segment for Traffic Management in Work Zones Policy/Standard Procedure purposes, use this worksheet to calculate the maximum disincentive. The method is the same as the mainline worksheet; however, the AADT input is not divided by 2 to make the volumes directional on the system ramp worksheet.
Date Calculated: | 2026-07-28
Spreadsheet protection password: CONSTRUCTION
Note on B26: Emily Willis: If we publish this work sheet then duplicate this note on the mainline worksheet (with modifications to make it read properly). Also consider adding it to the FAQs.

## Detour (Actual Drive Time)
Work Zone User Cost Calculations
Detour (Using Actual Drive Time)
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Detoured Section:
Time to Drive Normal Route (Min):
Time to Drive Detour Route (Min):
Duration of Closure (Days):
Calculated Values:
User Cost per Vehicle per Hour:
Delay (Min):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Closure Duration:
Total Delay Cost for Closure Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Notes (description, detour route, project phase reference, etc, as applicable):
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Date Calculated: | 2026-07-28
Spreadsheet protection password: CONSTRUCTION

## Detour (Distance & Speed)
Work Zone User Cost Calculations
Detour (Using Distance & Speed)
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Detoured Section:
Length of Normal Route (Miles):
Length of Detour Route (Miles):
Avg Posted Speed on Normal Route (MPH):
Avg Posted Speed on Detour Route (MPH):
Duration of Closure (Days):
Calculated Values:
User Cost per Vehicle per Hour:
Travel Time Along Normal Route (Secs):
Travel Time Along Detour Route (Secs):
Delay (Secs):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Closure Duration:
Total Delay Cost for Closure Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Notes (description, detour route, project phase reference, etc, as applicable):
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Date Calculated: | 2026-07-28
Spreadsheet protection password: CONSTRUCTION

## CPI Data
Historical Consumer Price Index for All Urban Consumers (CPI-U): U. S. city average, all items, index averages - Continued
https://www.bls.gov/cpi/tables/supplemental-files/home.htm
(See file titled "Historical CPI-U, December 20xx" for the December prior to the current month.)
www.bls.gov/cpi
CPI Year | Semiannual Average |  | Annual Average | % change from 2008 Annual Average | User Cost/Hour |  | Project Year | Actual
| 1st half | 2nd half |  |  | Car | Truck
2008 | 214.429 | 216.177 | 215.303 |  | 19.22 | 51.88 | 2009
2009 | 213.139 | 215.935 | 214.537 | -0.3558% | 19.1516 | 51.6954 | 2010
2010 | 217.535 | 218.576 | 218.056 | 1.279% | 19.4658 | 52.5434 | 2011
2011 | 223.598 | 226.28 | 224.939 | 4.476% | 20.0802 | 54.2019 | 2012
2012 | 228.85 | 230.338 | 229.594 | 6.638% | 20.4958 | 55.3236 | 2013
2013 | 232.366 | 233.548 | 232.957 | 8.2% | 20.796 | 56.134 | 2014
2014 | 236.384 | 237.088 | 236.736 | 9.955% | 21.1333 | 57.0446 | 2015
2015 | 236.265 | 237.769 | 237.017 | 10.09% | 21.1584 | 57.1123 | 2016
2016 | 238.778 | 241.237 | 240.007 | 11.47% | 21.4253 | 57.8327 | 2017
2017 | 244.076 | 246.163 | 245.12 | 13.85% | 21.8817 | 59.0648 | 2018
2018 | 250.089 | 252.125 | 251.107 | 16.63% | 22.4162 | 60.5074 | 2019
2019 | 254.412 | 256.903 | 255.657 | 18.74% | 22.8224 | 61.6038 | 2020
2020 |  |  |  |  | 23.2788 | 62.8359 | 2021 | Estimated at 2% increase per year
2021 |  |  |  |  | 23.7444 | 64.0926 | 2022
2022 |  |  |  |  | 24.2193 | 65.3745 | 2023
2023 |  |  |  |  | 24.7037 | 66.6819 | 2024
2024 |  |  |  |  | 25.1978 | 68.0156 | 2025
2025 |  |  |  |  | 25.7017 | 69.3759 | 2026
2026 |  |  |  |  | 26.2157 | 70.7634 | 2027
2027 |  |  |  |  | 26.7401 | 72.1787 | 2028
2028 |  |  |  |  | 27.2749 | 73.6223 | 2029
2029 |  |  |  |  | 27.8204 | 75.0947 | 2030
Information Last Updated: 2/19/20

## FAQ
1) What is the latest adjustment factor for car and truck road user costs for use with the road user cost spreadsheet?
The passenger car and truck costs shown in the Innovative Contracting Manual (ICM) are for 2008 values (provided to ODOT in early 2010 by FHWA Traffic Monitoring & Survey Division). To obtain the current year values, use the Consumer Price Index (CPI) and calculate a ratio to bring the values up to date. The CPI can be found here at:
www.bls.gov/cpi
(Bureau of Labor Statistics website has since been changed. As of 1/31/18, Table 24 can be found at the link below by clicking "Historical CPI-U" under the latest completed year.)
https://www.bls.gov/cpi/tables/supplemental-files/home.htm
Within the PDF report scroll to Table 24 ("Historical Consumer Price Index for All Urban Consumers (CPI-U): U.S. city average, all items - Continued"; the last page of Table 24). We use the annual average values rather than the monthly or semi-annual values to avoid potential volatility of the month-to-month factors.
https://www.bls.gov/cpi/tables/supplemental-files/home.htm
As of 2/19/20, the table formerly refered to as Table 24 (for "Historical Consumer Price Index for All Urban Consumers (CPI-U): U.S. city average, all items - Continued") can be found by instead clicking the link above and then clicking on the link under December of the prior year titled "Historical CPI-U, December 20xx". Scroll to the end of the list for the most recent update. We use the annual values rather than the monthly or semi-annual values to avoid potential volatility of the month-to month factors.
Example: | What cost per passenger car and cost per truck are to be used for road user costs for 2018 (project calendar year 2018)?
The 2008 values given in the ICM are $19.22/Passenger Car and $51.88/Truck.
The annual average CPI for 2008, per the CPI, is $215.303.
The most recent annual average CPI published is for 2017 (as of 1/31/18). We use the 2017 annual average value for 2018.
The annual average CPI for 2017, per the CPI, is $245.120.
The 2017 to 2008 ratio ($245.120/$215.303) is 1.1385. (…or the 2017 value is 13.85% higher than the 2008 value.)
2018 Cost per Passenger Car = (2008 Cost per Passenger Car) x (2017 to 2008 Ratio) = $19.22/Passenger Car x 1.1385 = $21.88/Passenger Car
2018 Cost per Truck = (2008 Cost per Truck) x (2017 to 2008 Ratio) = $51.88/Truck x 1.1385 = $59.06/Truck
2) What if I am calculating road user costs for a future year? Do the cost per passenger car and cost per truck change? If so, how?
If calculating road user costs for a future year for a project, the values can be increased by an assumed percentage to obtain a projected future value. As a rule of thumb we use 2% per year based on the recent average over the past decade or so (based on the values shown on the Historical CPI-U under "Percent change from previous, Annual Avg" as of 1/31/18).
Example: | What cost per passenger car and cost per truck are to be used for road user costs for project calendar year 2020 (as of 2018)?
Calculate or obtain the current year values (in this example, 2018; example is above under #1).
2018 Cost per Passenger Car = $21.88/Passenger Car
2018 Cost per Truck = $59.06/Truck
Project the current year values (2018) two years forward to 2020 project year values, assuming an approximate 2% per year increase.
2020 Cost per Passenger Car = (2018 Cost per Passenger Car) x ((1+(2% per year))^2 years) = $21.88/Passenger Car x ((1+(0.02))^2) = $22.77/Passenger Car
2020 Cost per Truck = (2018 Cost per Truck) x ((1+(2% per year))^2 years) = $59.06/Truck x ((1+(0.02))^2) = $61.45/Truck
3) On the Lane(s) Closed on Mainline worksheet, the user is to enter a total AADT (bidirectional). How does the worksheet know what percentage is for each direction?
It is understood that the volumes may be directional on some facilities (something other than 50%/50%), but for simplicity the worksheet divides the total AADT by 2 (assumming 50% per direction).
4) On the Lane(s) Closed on Mainline worksheet, what do I enter for number of lanes per direction?
The value used should match the number of lanes used in the same respective segment on the Permitted Lane Closure Schedule (PLCS). If the PLCS segment represents one direction, rather than both directions, then the resulting user cost per minute per lane will be only applicable for the direction represented in the PLCS segment. If the PLCS segment represents both directions, the resulting user cost per minute per lane will be applicable in both directions represented in the PLCS segment. In both cases the number of lanes per direction shown on the PLCS segment is the same number that will be entered on the Lane(s) Closed on Mainline worksheet.
5) Why do I get a slightly different result when calculating the cost per minute per lane by hand rather than using the Lane(s) Closed on Mainline worksheet?
The Lane(s) Closed worksheet has the final user cost per minute per lane coded to always round down to the nearest $5. For example, if the resulting user cost per minute per lane calculates to $118.51 the resulting value is rounded down to $115 per minute per lane.
6) What happened to the No Lanes Closed worksheet?
The No Lanes Closed worksheet has been removed. Since work zone speed limits are now variable the applicability of the worksheet has declined. Additionally, disincentives for violations of the variable speed limits in work zones is now covered within SS 808. If you feel you have a need for this old worksheet please contact Emily or Chris (emails below).
7) Who do I contact for more information or with questions?
| Contact: | Emily.Willis@dot.ohio.gov | or | Christopher.Wilson@dot.ohio.gov
Information Last Updated: 2/19/20