## EW-2
CA-C-3 ADA Construction Check Points
ContID: |  |  |  | AltID:
PLN: |  | Co/Rt/Sec:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Inspector Name: |  |  |  |  | Date:
CONSTRUCTION CHECK POINTS |  |  |  |  | YES | NO | REVIEW NOTES - REQUIRED
1. Initial Review - Meet with contractor to review proposed layout
a. Review proposed curb ramp for constructability
i. Verify type of proposed curb ramp
ii. Verify all required excavation can be performed without conflicts or changed conditions.
iii. Verify proposed grades at existing walk or other items (i.e. foundations, etc.) will match all existing grades and meet plan intent/ADA compliance.
iv. Verify all dimensions.
v. Perform an initial review of estimated slope values (longitudinal and transverse slopes along the ramp and landing locations).
vi. Measure all removal items.
b. Verify approved producer/supplier of detectable warning devices and other materials.
c. Verify detectable warning locations
d. Verify curb work (if proposed)
e. Verify pavement repair (if proposed)
f. Discuss phasing of construction with contractor for separate operations (ex. removing/ replacing curb before/ after excavation/ installing ramp).
g. Verify that each phase of work will match each transition and all slopes meet plan intent/ADA compliance. NOTE - This might involve going through stop points 2. and 3. multiple times for each curb ramp item.
2. Approval of layout – Review at completion of excavation and placement of base material
a. Review and measure slope values including longitudinal and transverse grades along the ramp and landing locations as well as curb grades (if proposed).
b. Consult with District ADA Representative and Design Engineer to review changed conditions.
c. Record changed conditions and District ADA Representative concurrence, if any.
d. Do not proceed with concrete placement until all proposed deviations/changes from plan are approved.
3. Final inspection (after initial curing of concrete). Document the following for final acceptance and payment of the installed curb ramp.
a. Field measure all work items
i. Concrete area
ii. Detectable warning area
iii. Curb lengths
b. Verify the following
i. Ramp dimensions are 4 feet minimum length and width?
ii. Landing dimensions are 4 feet minimum length and width?
iii. Ramp type performed as per standard drawing?
iv. Ramp constructed as-per-plan details?
1.) Document any “as-per-plan” ramp features and construction conformance
2.) Document any changes and designer approval
v. Ramp grades in the longitudinal and transverse locations. (Use a Smart Level).
1). Do grades conform to the standard drawing per ramp type?
vi. Landing grades in the longitudinal and transverse locations. (Use a Smart Level.)
1.) Do grades conform to the standard drawing per ramp type?
vii. Grades grade along curb. (Use a Smart Level.)
1.) Do they meet the requirements set forth by the kind of ramp in the standard drawing?
c. Include a payment template based on field measurements.
d. Include all notes regarding non-conformance with ADA requirements.
e. Document communication with Contractor regarding non-conforming elements of as-built ramps.