Progress Meeting Agenda/Minutes

Project XXX(XX)

County-Route-Section

[Month Day, Year]

Attendees:  See sign-in sheet.

| Agenda Topic: | Action Items: |
| --- | --- |
| - Corrections to last Progress Meeting Minutes: | Description: Person Responsible: Deadline: |
| - Outstanding Issues from previous Progress Meeting: | Description: Person Responsible: Deadline: |
| - Safety: | Description: Person Responsible: Deadline: |
| - Work in Progress: - Prime - In progress - Look ahead (time period) - Subs - In progress - Look ahead (time period) | Description: Person Responsible: Deadline: |
| - Progress Schedule - Current Schedule Update - Critical Path Activities - Current Completion Date - Next Schedule Update | Description: Person Responsible: Deadline: |
| - Critical Delays (work on critical path): - Any delays since the last meeting? - Current - Excusable - Non-Excusable - Concurrent? - Potential - Excusable - Non-Excusable - Concurrent? | Description: Person Responsible: Deadline: |
| - Non-Critical Delays (work NOT on critical path): - Any delays since the last meeting? - Current - Potential | Description: Person Responsible: Deadline: |
| - Time Extensions - Requests by Contractor - Compensable - Granted - Pending - Non-Compensable - Granted - Pending - Non-Compensable | Description: Person Responsible: Deadline: |
| - R/W and Utilities: | Description: Person Responsible: Deadline: |
| - Environmental: - Regulated Materials - Stock Piles - Handling - MSDS/PPE - Regulated Wastes - Location - Handling - Documentation - Regulatory Permits - 404/401 - NPDES - FEMA - BUSTR | Description: Person Responsible: Deadline: |
| - Change Order Status: | Description: Person Responsible: Deadline: |
| - Maintenance of Traffic: - Upcoming Closures - Other | Description: Person Responsible: Deadline: |
| - Public Relations: - Complaints - Other | Description: Person Responsible: Deadline: |
| - Testing/Materials: | Description: Person Responsible: Deadline: |
| - Submittals: - Under Review - To Be Submitted | Description: Person Responsible: Deadline: |
| - Value Engineering Change Proposals (VECPs): | Description: Person Responsible: Deadline: |
| - Request For Information (RFIs): - Outstanding RFIs - Upcoming RFIs | Description: Person Responsible: Deadline: |
| - Completed Items & Agreement on Final Quantities: | Description: Person Responsible: Deadline: |
| - Dispute Resolution: - Disputes - Current - Potential - Claims - Current - Potential | Description: Person Responsible: Deadline: |
| - Estimates: | Description: Person Responsible: Deadline: |
| - EEO/Wages: | Description: Person Responsible: Deadline: |
| - Partnering: | Description: Person Responsible: Deadline: |
| - C95 Issues: | Description: Person Responsible: Deadline: |
| - Contractor Issues: | Description: Person Responsible: Deadline: |
| - ODOT Issues: | Description: Person Responsible: Deadline: |
| - Open Discussion: | Description: Person Responsible: Deadline: |
| - Next Meeting: - Date - Location | Description: Person Responsible: Deadline: |
| - Outstanding Issue for Next Meeting: | Description: Person Responsible: Deadline: |

Project: _______________		PID: ____________		    Date: __________

Progress Meeting Sign-In Sheet

Name			Company			Phone				Email

__________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________