## VECP
Conceptual VECP Approval | [12 empty] | Preliminary Submittal |  |  |  |  | Final submittals
District | Project Number | Spec Year | CRS | Prime Contractor | Description of VE Changes | PID | Conceptual VECP submittal for approval to District | Conceptual Estimated Savings | Conceptual VECP submission to Central Office | Date Review Comments sent to District/Contractor | Date Approved by CO | Comments | Date Prelimary Submittal Received in Central Office | Date Preliminary Approved by CO | Date Preliminary Returned to District | Preliminary Submittal Comments | First Change Order Approved | Final VECP submittal | Final VECP Comments sent to Dist | Change Order Two and Three Approved | Final Disposition | Comments2 | DD Approval | Final Cost Amount | CMS/SM Value | Change Order #'s | System | Additional Comments
2 | 110614 | 2010 | Wales Rd. | E.S. Wagner | 14" tube piling in the piers and abutments | 78877 |  | 199036 | 2012-06-07 | 2012-06-14 |  | Reviewed by Slomski/Narsavage/Sappington |  |  |  |  | 2012-09-28 |  |  | 9/28/12 & 8/12/13 & 8/8/13 | Approved | Reviewed by Structures/Estimating/Construction | Approved | 70947.42 | 70947.42 | 9,10,11,12,22,23 | SM
9 | 110628 | 2010 | SR-93-0.00 | Brayman Construction | VECP#3 - The proposed VECP will relocate the four galvanized conduits that are to be installed under the bridge deck, and route them into the barrier walls on the bridge deck. The conduit material will be changed from galvanized to Sch. 40 PVC. | 81595 | 2013-11-25 | 177584.39 | 2013-11-25 |  |  | 11/26/13: Discussion w/D9 - utility company impact: to be verified by District. Requested clarification on reduction of spare conduit 12/2/13.
9 | 110628 | 2010 | LAW-93C-0000 | Brayman Construction | Precast Floor Beams & SIP | 81595 |  | 249500 | 2012-03-09 | 2012-03-14 |  | Reviewed by Tim Keller Tom Sappington/FHWA |  |  |  |  | 2012-06-28 |  |  | 2012-09-26 | Approved | Reviewed by Structures/Estimating/Construction | Approved | 124750 | 124750 | 7,43,44 | SM
9 | 110628 | 2010 | LAW-93C-0000 | Brayman Construction | New Storm water layout | 81595 |  | 77111.85 | 2012-04-03 | 2012-04-06 |  | Reviewed by Steve Slomski, tom Sappington, Jeff Syar, Ron Trivissono, FHWA |  |  |  |  | 2012-09-05 |  |  | 2013-08-06 | Approved | Reviewed by Structures/Estimating/Construction | Approved | 38555.92 | 38555.92 | 3,9,10 | SM
1 | 120027 | 2010 | Reservoir road runaround | Eagle Bridge Co. | Cutting existing bridge deck into smaller single span beams | 87965 |  | 106029.82 | 2012-03-15 | 2012-03-23 |  | Reviewed by Jim Welter/Tom Sappington |  |  |  |  | 2012-06-19 |  |  | 2012-06-19 | Approved | Reviewed by Estimating/Construction | Approved | 60243.91 | 60243.91 | 3,4,5 | SM
3 | 120481 | 2010 | LOR 301 23.49 | Mosser Construction | Hybrid I-Beam | 80199 | 2012-10-08 | 300469 | 2012-10-10 | 2012-10-15 | Rejected | Conceptual Reviewed by Crace/Sappington/Merklin/Bline/Welter/FHWA. Denied at conceptual. | [8 empty] | Denied | Denied after review of Conceptual Submission |  | 0 | Denied
3 | 120481 | 2010 | LOR 301 23.49 | Mosser Construction | Hybrid I-Beam (REVISED) | 80199 | 2012-12-10 | 295399 | 2012-12-10 | Conceptual: 12/26/12 | Conceptual: 12/26/12 | Conceptual Reviewed by Crace/Sappington/Merklin/Bline/Welter/FHWA. | 2013-03-20 | 2013-04-15 | 2013-04-15 | Guaranteed Min should increase per estimating to $317,561.00. | 2013-05-01 | 41400 |  | 2013-06-19 | Approved |  |  | 377861 | 168780.5 | 4,6,7,8,9 | SM
7 | 120494 | 2010 | MOT 75 12.00 | Kokosing | Eliminate Wedge/Reduce Number of Piers #1 | 77247 | 2012-10-16 | 2800000 | 2012-10-17 | Conceptual: 11/16/12 | 2012-11-16 | Conceptual Reviewed by Crace/Sappington/Merklin/Bline/Welter/FHWA. Elimination of Wedge rejected - partial acceptance 11-16-12. Preliminary Submitted in 3 parts. | 2/1/12 (Part 1 for the 1227L&R Structures) 2/15/13 (Part 1 for the 1282L&R Interior Pier Piling) |  | 2/19/12 (Part 1 for the 1227L&R Structure) Sent by LeBlanc | Part 1 for the 1227L&R Structure Estimating – Tom Sappington, Office of Estimating (no Comments) Structures – Jeff Crace, Office of Structural Engineering (No Comments), Construction – Jim Welter Construction – Steve Slomski Geotechnical – Chris Merklin Roadway Engineering – Michael Bline (no Comments) FHWA – Andy Blalock Contractor sent responses to review 3-1-13. CO responded 3-12-13. Part 1 for the 1282L&R Interior Pier Tom Sappington, Office of Estimating (no Comments) Structures – Jeff Crace, Office of Structural Engineering (No Comments), Construction – Jim Welter Construction – Steve Slomski Geotechnical – Chris Merklin Roadway Engineering – Michael Bline (no Comments) FHWA – Andy Blalock | 2013-08-14 |  |  | 2013-08-14 |  |  |  | 1200000 | 1200000 | 23,24 | SM
7 | 120494 | 2010 | MOT 75 12.00 | Kokosing | Steel Beam to Prestressed Concrete Beam (VECP #2) | 77247 | 2012-12-06 | 683189.77 | 2012-12-06 | Conceptual: 12/27/12 | Conceptual: 12/27/12 | Conceptual Reviewed by Crace/Sappington/Merklin/Bline/Welter/FHWA. | 7/31/2013 (No $ submitted) 9/20/13 | 2013-10-18 | 8/19/13 (Partial - No $ submitted) | Disposition of Comments of preliminary design review sent in 8/21/13. Responded 8/29/13. Price submittal and revisions received 9/20/13. GMS Established 10/18/13 for $683,189.77. | 2013-12-11 |  |  | 2013-12-11 |  |  |  | 341594.88 | 341594.88 | 26,27 | SM | Not coded correctly in SiteManager
8 | 120579 | 2010 | Ham-74-05.53 | JR. Jurgenson (for sub Complete General) | VECP #1: modifying the bridge modification plan by installing a steel pedestal along with a new elastomeric bearings instead ofa concrete pedestal with new elastomeric bearings | 83011 | 2011-08-22 | 77258.77 | 2013-09-11 | 2013-09-13 | 2013-09-13
8 | 120599 | 2010 | HAM-75-2.30 | Kokosing | VECP#1 - revising the installation method prescribed (“pipe jacking”) to a 54” Jack and Bore installation. The installation would be a Steel Conduit with Bituminous coating. | 76257 | 2013-05-30 | 105037.01 | 2013-06-04 | 2013-06-13 | 2013-06-13 |  | 2013-10-21 | 2013-11-27 | 2013-11-27 | Preliminary Submittal received at D8 9/16/13. CO 10/21/13 after review by CSX. Estimating requested additional information 11/18/13 (received 11/21/13). Preliminary approved 11/27/13.
8 | 120599 | 2010 | Ham-75-2.30 | Kokosing | VECP#2 - Revising the drainage and redesigning Soldier Pile Lagging walls #27 & 28 | 76257 | 2013-10-09 | 400000 | 10/9/2013 10/15/13 (resubmission) | 2013-10-10 | 2013-10-18 | Initially rejected - Insufficient information for conceptual 10/8/13. DDD Concurrence 10/18/13.
11 | 120656 | 2010 | BEL-70-17.73 | Beaver Excavating Company | Revised Bridge Design - Multiple Span to Single Span on MSE Walls | 25510 | 2013-01-30 | 120000 | 2013-02-08 | 2013-02-14 | Rejected | Conceptual Reviewed by Crace/Sappington/Merklin/Bline (no comments)/Welter/FHWA. VECP Rejected by District and CO. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | No info found
11 | 120656 | 2010 | BEL-70-17.73 | Beaver Excavating Company | Revised Bridge Design - Precast Arch on Spread footings to Precast Arch on Drilled shaft foundation (Str 1783) | 25510 | 2013-02-27 | 150000 | 2013-03-01 | 2013-03-04 | 2013-03-18 | Conceptual Reviewed by Crace/Sappington/Merklin/Bline (no comments)/Welter/FHWA. Restriction: no auger shafts allowed. | 2013-04-19 |  | 2013-05-02 | Contractor sent additional clarifications to review comments on 5/10/13. |  | 2013-05-28 | 2013-06-11 |  | approved |  |  | 75000 | 75000 | 5,7,8 | SM
11 | 120656 | 2010 | BEL-70-17.73 | Beaver Excavating Company | Revised Bridge Design - Multiple Span to Single Span on Drilled Shaft supported Walls (Str 1817) | 25510 | 2013-03-04 | 140000 | 2013-03-08 | 2013-03-08 | 2013-04-03 | Revised from MSE Walls - Incorrectly sent out for review by District to Geotech and Structures. Requested clarifications from the Districts on 3-8-13. | 2013-04-16 | 2013-05-22 | 2013-05-22 | Received Preliminary Drawing 4/12/13 - Structures performed expedited review - comments for reference sent 4/18/13. Costing sent for CO review on 5/10. |  | 2013-06-26 | 40741 |  | Approved |  |  | 112865.94 | 112865.94 | 6,21,22 | SM
3 | 120675 | 2010 | HUR-99-13.77 | Mosser Construction | Revised Retaining Wall - Vertical Tie Downs: Revised Savings #2 | 76959 | 2012-01-28 | 70000 | 2012-02-11 | 2013-03-18 | 2013-03-26 | Sappington, Crace, Slomski (Possible), Merklin (Possible with Modifications), FHWA (Blalock/Dar - Recommended Not to approve) Requested additional info 2-22-13. Response received 3-13-12. Requested comments from DD's 3-18-13. | 2013-05-02 |  | 2013-05-20 | Preliminary Submittal also includes a Time Savings of 29 days. |  | 2013-06-25 | 2013-07-17 |  | Approved
3 | 120675 | 2010 | HUR-99-13.77 | Mosser Construction | Revised Retaining Wall - Vertical Tie Downs #1 | 76959 | 2012-01-28 | 45000 | 2013-01-29 | 2013-01-31 | Rejected | Rejected at District Level. - Revised and resubmitted. | NA | NA | NA | NA | 2013-06-05 | NA | NA | 8/23/13 & 8/26/13 | NA | NA | NA | 42371 | 56871 | 2,3,4,5,6 | SM
3 | 130001 | 2010 | LOR-58-7.36 | Beaver Excavating Company | VECP #1: Redesign for the retaining walls 1, 2, and 3 and a Pump Station | 23104 | 2012-03-13 | 300000 (Conceptual revision: $157k) | 2013-03-13 | 2013-03-28 | 2013-03-30 | Requested meeting for 3/26/13 - held. | 2013-08-13 |  | 2013-09-12 |  |  | 2013-11-20 | 2013-11-27 |  |  |  |  | 78718.5 | 78718.5 | 20,29,30 | SM
3 | 130001 | 2010 | LOR-58-7.36 | Beaver Excavating Company | VECP #2: Replace CIP Reinforced Concrete Abutment with Top Down Construction Type - Cantilevered Tangent Drilled Shaft Wall Wall with | 23104 | 2013-03-18 | 300000 | 2013-03-19 | 2013-03-28 | 2013-03-30 | Conceptual Reviewed by Crace/Sappington/Merklin/Bline/Welter/FHWA Dropped by Contractor - verified by phone call w/Beaver 11/5/13. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Could not find change orders that match the description
3 | 130001 | 2010 | LOR-58-7.36 | Beaver Excavating Company | VECP#3: Lowering the Pump Station floor elevation | 23104 | 2013-03-22 | 50000 | 2013-03-26 | 2013-05-06 | 2013-05-06 | Multiple issues needed addressed prior to approval. Original designer recommended rejection due to specific design issues - ultimately addressed. Portion of drilled shaft temp retaining wall not a VECP but allowed temp shoring means and methods. depends upon the approval of VECP #1. | 6/3/2013 9/16/13 (resubmittal) |  | 6/19/2013 9/27/13 | GMS: $51,810.66.00 . Multiple issues with the design - modified drawings created by the original designer, Burgess and Niple modifies an original structural design item. The changes do not indicate what was revised from the original design. The conceptual VECP named the VECP Designer to be E.L. Robison. The revisions are not be performed by the named VECP designer. (REJECTED) 2nd submittal received 9/16/13. Minor CO Comments. Being reviewed by original Designer. Original Designer response - 10-15-13. District formal response 10-17-13. |  | 41591 | [5 empty] | 25905.33 | 25905.33 | 25,33,34 | SM
3 | 130001 | 2010 | LOR-58-7.36 | Beaver Excavating Company | VECP#4: Reducing the deep of underdrain by reducing Type C granular embankment and replacing with Geogrid. | 23104 | 2013-04-01 | 110000 | 2013-04-03 | 2013-04-17 | 2013-04-17 | none | 6/12/2013 10/16/2013(resubmission) |  | 7/16/2013 10/24/13 (resubmission) | GMS Incorrectly calculated per Estimating. Submitted 158,383.64. The Guaranteed Minimum Savings (GMS) should be $229,448.32. Revised Submission received at CO 10-16-13. Requested GMS clarification 10/18/13. CO Revised Prelim Review sent 10/24/13 |  | 41591 | 41605 |  | Approved | In preliminary review - requested change to VECP (removal of Mirafi on top of Type C. Removed the request and requested to proceed as originally proposed. This change will reduce GMS.
1 | 130002 | 2010 | ALL-75-5.53 | Beaver Excavating Company | #1: Revised Bridge Design - Multiple Span Concrete Beams to Single Span Concrete Beam on MSE Walls (Str 0703) | 76691 | 2013-03-11 | 250000 | 2013-03-11 | Conceptual: | 2013-03-26 | Reviewed by Slomski(approve)/Sappington/Crace(approve w/comments)/Tariq/Bline/Welter/Merklin(approve) | 2013-05-21 |  | 2013-06-05 |  | 2013-08-01 | 2013-07-02 | 2013-07-11 | 2013-09-24 |  |  |  | 133874.15 | 133874.15 | 7,15,16 | SM
1 | 130002 | 2010 | ALL-75-5.53 | Beaver Excavating Company | #2: Revised Bridge Design - Multiple Span Concrete Slab to Single Span Concrete I on Semi-Integral Abutments eliminating piers (Str 0832) | 76691 | 2013-03-11 | 120000 | 2013-03-11 | Conceptual: | 2013-03-26 | Reviewed by Slomski(approve)/Sappington/Crace(approve)/Tariq/Bline/Welter/Merklin(approve) | 2013-05-22 |  | 2013-06-06 |  | 2013-08-01 | 2013-07-02 | 2013-07-11 | 2013-10-02 |  |  |  | 182941.5 | 182941.5 | 8,17,18 | SM
1 | 130002 | 2010 | ALL-75-5.53 | Beaver Excavating Company | #3 change portions of the proposed Retaining Walls 9, 10 & 11 from MSE walls to Geogrid Reinforced Slopes | 76691 | 2013-04-03 | 500000 | 2013-04-03 | 2013-04-11 | 2013-04-11 | NA | 2013-07-09 |  | 2013-08-01 | Conceptual Savings reduced to $446,108.71. Response required the GMS to be $500k as in the conceptual Submittal. Contractor requested a reconsiderations due to changes - requested itemized ODOT required changes. | 2013-09-24 | 2013-08-12 |  | 2013-10-02 |  |  |  | 224445.21 | 224445.21 | 23,30,31 | SM
1 | 130002 | 2010 | ALL-75-5.53 | Beaver Excavating Company | #4 Geogrid Subgrade Stabilization: replace the subgrade improvement method in the plans on SR- 309 and Service Road 3 & Neubrecht Road using 12" of Granular Material, Type 8 and Item 861 Geogrid with 8" of Granular Material, Type 8 and a layer of TX 5 Geogrid by Tensar. | 76691 | 2013-05-22 | 26581.1 | 2013-05-22 | n/a | n/a | Approved by District | NA | NA | NA | NA | 2013-06-12 | NA | NA | 2013-08-01 | Approved | NA | NA | 13290.55 | 13290.55 | 2,5,6 | SM
5 | 130026 | 2010 | LIC-70-13.00 | Double Z | Constructing MSE Wall 1 phase - Coring through existing abutment to install MSE Wall straps | 85540 | 2013-02-26 | 48000 | 2013-03-01 | 2013-03-01 | N/A | Reviewed by CO (Slomski, Siddiqi) - Viable. Less the $50k - approved by District. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | 130027 | 2010 | OTT-2-25.05 | Beaver Excavating Company | VECP#1: MOT Revisions - Allowance of Daytime work and Crossover requirement barrier changes | 78572 | 2013-04-15 | 115000 | 2013-04-16 | 2013-04-29 | 2013-04-29 | MOT Submittal - allowed abbreviated Preliminary review as VECP Straight forward |  |  | 2013-08-08 |  |  |  |  | 2013-09-25 | Approved |  |  | 69921 | 69921 | 3 & 4 | SM
2 | 130027 | 2010 | OTT-2-25.05 | Beaver Excavating Company | VECP#3: Grout Mix Revisions | 78572 | 2013-05-28 | 240000 | 2013-07-01 | 2013-08-28 | Rejected | Initially rejected by District. Sent to CO for review 7/18/13. Meeting held 8/19/13. DD concurrence on rejection sent 8/28/13 | [8 empty] | Denied |  |  | 0 | Denied
2 | 130027 | 2010 | OTT-2-25.05 | Beaver Excavating Company | VECP#4: PCB Non-Performance | 78572 | 2013-08-30 | 177922 | 2013-09-04 | 2013-09-10 | Rejected | Recommended rejection 9/10/13. Rejection Concurrence by DDs 9/12/13. | [8 empty] | Denied |  |  | 0
8 | 130032 | 2010 | CLI-71/380-4.26/3.99 | Barrett Paving | VECP#1: MOT Revision Proposing MOT pattern changes | 87061 | 2013-05-09 | 114693 | 2013-05-10 | N/A | N/A | Requested clarification 5/10/13. Dropped by Contractor 5/16/13. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | 130184 | 2010 | CUY-77-9.50 | Ruhlin Company | VECP#1 - Revising MOT phasing and procedure. Cost savings (400K) and time savings (117days @ $2600/day). Total savings $745k. | 77419 | 2013-07-18 | 745000 | 2013-08-30 | 2013-09-27 | 2013-09-25 | Recommended calling a conference call (9/10/13). DDD request 9/25/13 - received 9/27/13.
5 | 130321 | 2010 | FAI-158-3.75 | IGEL | VECP1 - Removing Rock Blasting and using equipment for removal | 87344 | 2013-07-09 | 57115 | 2013-07-09 | 2013-07-19 | NA | Geotech OK with scaling. Simple VECP with only 1 submittal needed.
6 | 130402 | 2010 | FRA-23-22.23 | Ruhlin Company | VECP#2 - redesign of the built up solder piles specified in the tie-back wall for the project. The redesign will utilize a wide flange beam and stiffener for the tie-back installation in lieu of the built up soldier pile | 81746 | 2011-10-25 | 182892.3 | 2013-11-06 | 2013-11-19 | 2013-11-19 | Spoke to Contractor (Kahlig) - 11/26/13. Design changes must be done by consulting firm. Initial calculations on the Conceptual not sufficient.
6 | 130402 | 2010 | FRA-23-22.23 | Ruhlin Company | VECP#3 - Proposal to redesign the CIP Facing on the MSE Wire wall to Precast Panels | 81746 | 2013-09-24 | 100000 | 2013-10-09 | 2013-10-09 | Rejected | Rejected due to environmental commitments for aesthetics. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  | CO #5 for $14500 for time savings
6 | 130402 | 2010 | FRA-23-22.23 | Ruhlin Company | VECP#4 - Proposes to redesign/eliminate approach slabs on FRA-23-2330 and FRA-23-2363. Proposes to redesign Moment Slab & Barrier on tieback retaining walls allowing asphalt pavement. MOT scheme not constructible, and elimination slab with redesign eliminates MOT conflict. | 81746 | 2014-07-24 | 350000 | 7/24/2014 8/20/14 (Revision) | 2014-07-29 | 2014-08-26 | 7/29/14: Requested additional information - location of new joint and deck edge in relation to wheel path. Infor received 8/8/14. Conf call with Ruhlin - will require approach to be tied. Engineer to discuss with Ruhlin for resubmission. Resubmission 8/20/14 - requested DD concurrence 8/25/14. |  | 1900-01-01 | [5 empty] | Change Order 2 -3/13/2015 Change Order 3 - 3/13/2015 |  |  |  | 702332.72 | 702332.72 | 45,46,47 | SM | N/A
6 | 130402 | 2010 | FRA-23-22.23 | Ruhlin Company | VECP#1 - Revising abutment types (Str 2330 & 2363) | 81746 | 9/4/2013 10/12/2013 | 350000 | 9/4/2013 10/17/2013 | 9/16/13 (initial meeting) | 2013-10-18 | Recommended calling a conference call (9/5/13). Conceptual meeting held 9/16/13. Revisions to the Conceptual submittal received 9/27/13. 2nd Conf call 10/9/13. ODOT requirements reduced savings from $600k to $350k. Revised Conceptual received at CO 10-17-2013. DD Approval 10/18/13
11 | 130535 | 2010 | BEL-70-0.05 | Shelly and Sand | VECP#1 - Proposed VECP for Time and Cost to redesign the MOT and Structures by constructing the bridges part width, minimally closing CR-114 for 60days, and increase the elevation of I-71 to gain the increase CR-114 clearance instead of lowering CR-114 and build temp MOT ramps. Preliminary Profile received 1/24/14 (Feasible) | 87886 | 2014-01-08 | 372000 | 2014-01-08 | 2014-01-31 | 2014-01-31 | Requested the proposal to be "overbuilt" by 12 ft to allow future permanent width. | 3/26/2014 5/21/2014 | 2014-06-30 | 4/11/2014 6/13/2014 | Required contractor to resubmit cost per proper format (4/4/14). Preliminary Review without estimating comments sent 4/11/14. 2nd set of review comments on resubmission of plans received on 5/21/14 - Comments sent 6/13/14. No Cost submitted. 3rd submission received 6/9/14. Sent to Estimating. |  |  |  | Change Order 2 -10/9/2014 Change Order 3 - 10/9/2014 |  |  |  | 152579 | 152579 | 1,2,3 | SM | N/A
1 | 130568 | 2010 | ALL-75-0.21 | Beaver Excavating Company | VECP#1 - This VECP will change the cast-in-place piling layout on the rear and forward abutments for both structures. The VECP proposes to eliminate approximately 3400ft of piling. It appears that the abutment piling on these two bridges was designed on a per foot width basis with no transverse distribution of superstructure dead loads and live loads (i.e., the loads at beam seat level are applied only to the piles located directly under the bridge superstructure). | 89029 | 2014-02-10 | 178500 | 2014-02-18 | 2/10/14 2/21/14 2/24/14 3/7/14 3/13/14 3/18/14 3/27/14 | 2014-04-01 | Information sent to Contractor-Issues with overstressing per original design assumptions per original designer (2-24-13). Decision made to allow as a VECP as redesign includes recalculations and new layout of piling. VECP Designer changed from URS to EL Robinson at the Contractor's request. | 1A - 4/7/2014 1B - 5/21/14 | 1A - 4/29/14 1B - 6/19/14 | 1A - 4/29/14 1B - 6/4/14 | 1A -Submittal broken into two submittals. Breese Rd submitted 4/7/14. 1B - Hanthorn submitted | 1A - 4/25/2014 1B - 6/17/2014 |  |  | 1A - 5/8/2014 1B - 7/2/2014 |  |  |  | 1A - $76,160.00 1B - $80,278.00 | 156438 | 1A - 5,6,7 1B - 14, 15, 16 | SM | N/A
1 | 130568 | 2010 | ALL-75-0.21 | Beaver Excavating Company | VECP#2 - Proposes to replace an open cut 54" storm and replace with a Jack-and-Bore. Savings less then $50k, so district approval only. | 89029 | 2014-02-24 | 29400 | na | na | na | Under 50k threshold. Approved by District 3/7/14. | na | na | 2014-04-11 | GMS 29,600 | 2014-04-16 |  |  | 2014-04-18 |  |  |  | 27493.37 | 27493.37 | 1,2,3 | SM | N/A
1 | 130568 | 2010 | ALL-75-0.21 | Beaver Excavating Company | VECP#3 - This VECP replaces retaining walls (CIP & MSE) to Geogrid Reinforced Slopes. The proposed Geogrid Reinforced Slope will vary from a 1.4:1 to a 2:1 slope and will remain inside the current construction limits. | 89029 | 2014-02-27 | 200000 | 2014-02-27 | 2014-03-06 | 2014-03-06 | none | [7 empty] | Change Order 2 -5/8/2014 Change Order 3 - 5/8/2014 |  |  |  | 91617.4 | 91617.4 | 8,9,10 | SM | N/A
1 | 130568 | 2010 | ALL-75-0.21 | Beaver Excavating Company | VECP#4 - Proposes to change the typical section buildup for SR65 in locations where the plans originally called out Geoweb installation. The VECP changes the Geoweb to TX-160 Geogrid. | 89029 | 2014-03-18 | 20000 | na | na | na | Under 50k threshold. Approved by District. | 2014-04-11 | 2014-04-16 | 2014-04-16 | Preliminary Estimate increased above 50k, therefore required. | 2014-05-08 |  |  | 2014-05-08 |  |  |  | 45808.7 | 45808.7 | 8,9,10 | SM | N/A
1 | 130568 | 2010 | ALL-75-0.21 | BEAVER EXCAVATING COMPANY | VECP#5 - This VECP will change portions of the proposed Retaining Walls from MSE walls to Reinforced Slopes, total impacted length of 1136ft. | 89029 | 2014-06-28 | 150000 | 2014-06-30 | 2014-07-03 | 2014-08-05 | 7/3/14 Comments: OGE concerns with proximity to adjacent Gasline. Requiring Dominion Gas to approve prior to proceeding. 7/31/14: Dominion OK with concept. Sent out for DDD approval 8/1/14. | 2014-08-12 | 2014-08-20 | 2014-08-20 | Minor Comments: Minor error in cost estimates. Minor note revisions required. |  | 2014-08-29 | 2014-09-08 | Change Order 2 -9/8/2014 Change Order 3 - 9/8/2014 | Approved |  |  | 128826.54 | 128826.54 | 17,18,19 | SM | N/A
6 | 138046 | 2010 | Del-23-0372 | Shelly and Sand | VECP#1 - Redesign of foundation - drilled shaft to spread footing and redesign of straight foundation to turnback abutment foundation | 90821 | 2013-11-20 | 130000 | 11/20/2013 (1st submission) 11/25/13 | 11/20/2013 (1st submission) | n/a (1st submission) Rejected (11/27/13) | Initial 11/20/13 submission returned to contractor. Insufficient information to judge concept feasibility. Rejected due to concerns with long term settlement (verified with OGE). | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  | CO #8 for $20150 for time savings.
3 | 140002 | 2013 | LOR-2-10.46 | JD Williamson | VECP#1 - Proposes modifying MOT phasing by constructing the project using Contra-Flow vs "over-building" structures in Ph1 & Ph2 to accommodate 4 lanes of traffic. VECP savings is through reduced temp structure widening, reduced permanent deck width, and reduced MOT installations. | 25732 | 2014-02-27 | 1000000 | 2014-02-27 | 3/3/14 - asked for additional information concerning temporary parapet detail connections. | 2014-03-07 | Requested additional info 3/3/14 - concerns with feasibility of temp barrier details. | 2014-06-02 |  | 2014-06-17 | First submission needing items addressed. Resubmittal required. Estimated Savings $1,064,537 |  | 2014-07-30 | 2014-08-07 | Change Order 2 - 9/11/2014 Change Order 3 - 8/29/2014 | Approved |  |  | 1103483.7 | 1103483.7 | 1,2,3 | SM | N/A
11 | 140098 | 2013 | BEL-70-4.41/4.71 | Shelly and Sand | VECP proposes revising construction sequence and closure. Eliminates engineered fill and cross-over by filling completely under structure, working from 1 side across. | 86871 | 2014-04-11 | 250000 | 2014-04-11 | 2014-04-16 | 2014-05-07 | Rejected time component of VECP - project maintains 2 lanes therefore minimal impact to traveling public. District concurrence depending upon constructability. | 8/11/14 - Complete Package 8/7/14 - Incomplete 8/18/14 - Revisions 8/21/14 - Revisions | 2014-08-26 | 2014-08-26 | Comments provided on an incomplete submission. Phasing for traffic 2/3/4 forthcoming. |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | 140170 | 2013 | WOO-75-10.61 | Kokosing | VECP#1: MOT Revisions - The contractor is proposing an MOT scheme which will allow the NB full-depth reconstruction to be built full-width. Original phasing - part-width with PCB entire length NB&SB. Proposed: SB part-width in two phases with PCB, contra-flow upon SB reconstruction with crossovers. Full width reconstruction NB. | 95435 | 2014-06-23 | 620000 | 2014-06-26 | 2014-06-30 | 2014-07-22 | 6/30/14 comments: Concerns with system to ensure no encroachment to clear zone. Required to address issues. Resubmitted on 7/15/14. Sent for DDD Concurrence: 7/16/14 | 2015-04-23 | 2015-06-02 | 2015-05-11 | 5/6/14: Comments requesting breakdown of items and correction. Received 5/7/15. 5/11/15: Sent technical Review comments to District. 6/2/15: Approval with assumption that taper lengths in phase 3 will be corrected. |  |  |  | Change Order 2 -3/31/2015 Change Order 3 - 9/15/2015 | 340468 | 340468 | 10,26,27 | 340468 | 340468 | 10,26,27
2 | 140170 | 2013 | WOO-75-10.61 | Kokosing | VECP#2: Profile Revisions - is to adjust the project profile grades for approximately 6.5 miles of the 8.82 mile project. The grade adjustment will raise the planned profile reducing the excavation and raising the embankment quantities for the complete reconstruction portions of the project. | 95435 | 2014-07-01 | 374000 | 2014-07-03 | 2014-07-14 | 2014-07-12 | 7/3/14 - Sent to DDDs for Concurrence. Last concurrence received 7/12/14. | 2014-08-21 | 2014-10-01 | 2014-08-27 | 8/27/14: Bridge adjustment, but no cost impacts. Requested this be re-evaluated. 9/4/14: Sent ODOT estimated Bridgte savings. |  | 2015-03-05 |  | Change Order 2 -1/21/2016 Change Order 3 - 1/21/2016 |  |  |  | 340468 | 311747.16 | 311747.16 | SM | N/A
2 | 140170 | 2013 | WOO-75-10.61 | Kokosing | VECP#3: Noisewall Redesign - Proposal to is replacing the planned concrete noisebarrier with a earthen mound constructed at the same length and final top height as the proposed noisebarrier | 95435 | 2014-07-14 | 612000 | 2014-07-17 | 2014-07-31 | 2014-07-31 | Required: • They will need to address any permit issues with the impacted waterway as the proposed earthen mound will be filling in the proposed ditch line. • Participate with the District in the required outreach necessary with the revision. • Additional landscaping. Trees will need to be planted. • The earthen mound needs to be of natural material conducive to vegetation. Expect savings to be reduced. | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 140180 | 2013 | FRA-23-0.00 | Kokosing | VECP#1 - MOT revisions: closing one lane, removing the bolt on barrier on the bridge, replacing it and then reopening the lane. Plan requires 2 lane shift with PCB to perform the work. The closed lane would be protected with a crash truck and equipment during the work period. They would only remove what they could replace in a night. | 80108 | 2014-07-02 | 108810 | 2014-07-02 | 7/3/2014 7/16/14 (Rejection) | Rejected | 7/11/14 - Sent recommendation for rejection. Proposal is to use equipment to protect zone. Unacceptable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 140180 | 2013 | FRA-23-0.00 | Kokosing | VECP#1 RESUBMISSION - MOT Revision: Resubmission proposing to replace a single post so no drop off occurring. Will install bottom rail and all post replaced by morning. Closure to occur at night. | 80108 | 2014-07-22 | 108810 | 2014-07-25 | 2014-08-05 | 2014-08-05 | 7/31/2014 - Spoke with OSE and ORE. Conceptual idea acceptable. 7/31/14 - Sent DDDs request for approval. | [7 empty] | Change Order 2 -3/9/2015 Change Order 3 - 3/9/2015 |  |  |  | 126619.16 | 126619.16 | 5,6 | SM | N/A
7 | 140202 | 2013 | CLA SR 41/235 30.79/8.65 | Double Z | Complete closure of 235/41 interchange for 30days to complete roundabout. Plans allowed SR 41 closure for 80days and maintain 235. | 94639 | 2014-08-23 | 110000 | 2014-05-05 | 2014-05-08 | Rejected | Rejected - Early planning stages determined closure of SR235 not feasible. Acceptance would conflict with initial outreach in planning. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | N/A | N/A | N/A | N/A
11 | 140212 | 2013 | Has-250-23.23 | TRUCCO | VECP#1 - Proposed VECP for Time and Cost to revise MOT closure period. VECP proposes to increase closure duration from 7days to 11days and reduce MOT installations. Proposing 24days savings on the completion date. | 83382 | 2014-05-08 | 170488 | 2014-05-23 | 2014-05-27 | Rejected | Rejected as preliminary planning identified 7days as the longest closure allowable due to heavy gas/oil development traffic. | NA | NA | NA | NA | NA | NA | NA | N/A | NA | NA | NA | N/A | N/A | N/A | N/A | N/A
2 | 140235 | 2013 | LUC-475-4.33/5.22/5.47 | Miller Brothers Construction | VECP#1 - Proposes to redesign the MOT for the WB SR2 entrance to NB475. Instead of 120day closure of the ramp, the proposal constructs a left turn from WB SR2 to the ramp from EB SR2 to NB475. | 80694 | 2015-02-23 | N/A | N/A | 2015-02-25 | N/A | 2/25/15: Issues with feasibility - issues sent. Resubmittal Rejected. Determined that proposed scheme would cause undue backup into adjacent zone. Unacceptable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | 140235 | 2013 | LUC-475-4.33/5.22/5.47 | Miller Brothers Construction | VECP#2 - Proposed to redesign slope drains in benching widening from following the side slope to a vertical trenching construction. | 80694 | N/A | 38911.8 | N/A | N/A | N/A | Less then $50k - approved by the District. | 2015-06-10 |  |  | 6/10/15: Requested additional information on costs. 6/23/15: Received response.
2 | 140236 | 2013 | LUC-CR-73-1.42 | Beaver Excavating Company | VECP#1 - Proposes to redesign the Pump Station from a multi-side structure to a circular structure with auger cast piles as shoring/support | 75107 | 2014-10-03 | 54000 | 2014-10-07 | 10/10/14 10/16/2014 | 2014-11-24 | Sent comments - received response 11/6/14. | 2015-03-19 | 2015-05-21 | 2015-04-06 | 4/6/15 - Initial Submittal review comments. 4/28/15 - Resubmittal by contractor 5/6/15 - Additional requested information. |  |  |  | Change Order 2 -10/19/2015 Change Order 3 - 10/19/2015 |  |  |  | 52445 | 52445 | 4,5,6 | SM | N/A
8 | 140267 | 2013 | HAM-75-6.78 | Jurgensen | VECP#1 - Proposes to change the location of a planned underground detention system at the interchange of I-75 and SR562. Plan location on the infield of the onramp from 562 to SB75. Proposed location to exit infield of NB75 to SR562. Proposing a pre-cast system. | 82286 | 2014-08-15 | 250000 | 2014-08-26 | 2014-08-29 | 2014-08-29 | Proposed location would be in an field which would include a future location. Per District, VECP will require additional redesign of adjacent project. Cost of redesign will be evaluated in ultimate acceptance. | 2014-11-05 | 2015-12-18 | 2015-12-18 | 11/6/15: Requested additional cost breakdowns. 11/26/15: Received additional cost breakdowns. 12/09/15: Requested additional cost breakdowns. 12/17/15: Additional info received. |  | 2015-01-12 | 2015-01-21 | Change Order 2 -3/16/2015 Change Order 3 - 3/16/2015 | Approved |  |  | 256818.23 | 256818.23 | 1,2,3 | SM | N/A
8 | 140267 | 2013 | HAM-75-6.78 | Jurgensen | VECP#2-Proposes to change Wall G from an MSE wall to a Geofoam wall. Proposes to redesign the existing F2 geofoam wall to utilize lighter weight geofoam and eliminate the existing CIP wall. | 82286 | 2014-10-03 | 200000 | 2014-10-10 | 2014-10-24 | 2014-10-24 | Wall F2 currently a geofoam wall. | 2015-03-12 | 2015-05-01 | 2015-03-16 | 3/16/15: Requested further breakdown of submitted LS items. 3/23/15: Requested further breakdown of distribution slab and temp shoring. 3/25/15: Requested further breakdown of items. 4/7/15: Submitted comments - estimated determined VECP actually increases the cost of Wall G. 4/27/15: Contractor Resubmitted by removing the Wall G redesign. |  |  |  | Change Order 2 -9/29/2015 Change Order 3 - 9/29/2015 |  |  |  | 283954.58 | 283954.58 | 6,7,8 | SM | N/A
2 | 140485 | 2013 | LUC-75-4.52 PH 2 | Kokosing | VECP#1 - changing the beams from structural steel (as bid) to precast concrete I-beams as well as revisions to the pier and abutment locations and designs. | 77254 | 2015-01-05 | 1500000 | 2015-01-05 | 2015-01-09 | 2015-01-09 | Meeting held 1/5/15 - Conceptual discussion. Included several requirements for contingent approval sent 1/9/15. Additional Meeting held 01/29/15 - discussing superstructure issues. 1/28/15 - Partial (Framing Plan/ I-Beam X-Sections). CO Meeting on 1/29/15. 2/11/15 CO Meeting with OGE to discuss geotechnical concerns with VECP#1. | 2015-05-08 |  |  | VECP savings submitted at $1,603,473.99. Calculations exceeds 5000pages. District submitted plans to Norfolk Southern. 5/7/15: Initial Preliminary Submittals. 5/20/15: Preliminary Comments Sent 6/3/15: Initial Preliminary Review comment resolution meeting. Re-submission required. |  |  |  | Change Order 2 -9/3/2015 Change Order 3 - 9/3/2015 |  |  |  | 1123105.89 | 1123509.89 | 20,24,25 | SM | N/A
2 | 140485 | 2013 | LUC-75-4.52 PH 2 | Kokosing | VECP#2 - Proposed changing MOT Slotted Drain to Trench Drain. Drainage need for MOT only | 77254 | 2015-03-13 | 87387 | 2015-03-13 | 2015-03-19 | 2015-03-19 | VECP designer through additional evaluation found the concept not feasible. Dropped prior to preliminary submittal. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | 140535 | 2013 | FA-33-5.60 | Shelly and Sand | VECP#1 - Utilize a Geosynthetic Reinforced Soil Foundation (GRSFS) as a shallow foundation system to be installed beneath the proposed MSE wall and embankment at the "Special Consideration Areas." | 76938 | 2015-01-23 | 300000 | 2015-01-26 | 2015-02-03 | NA | Review of VECP cost and time by contractor has caused this VECP to be withdrawn (2/27/15). | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | 150057 | 2013 | CUY-6-12.20 | Great Lakes | VECP#1 - Revising the Soldier Pile/Tie Back wall with a GeoFoam retaining wall | 86482 | 2015-06-01 | 700000 | 2015-06-04 | 2015-06-10 | N/A | 6/10/15: Requested additional information. 6/23/15: Rejected. Schedule risk and unknown risks. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | 150085 | 2013 | HAM - 71 - 1.34 Lytle Tunnel | Great Lakes | VECP #1 - Change the plan quantity of 2,457 Schreder Luminaires to 1,420 Holophane Tunnel Pass Luminaires | 87268 | 2016-01-21 | 200000 | 2016-01-26 | 2016-02-29 | N/A | Rejected - The Department did not view the submittal as a viable option because of increased yearly energy costs for maintaining lighting in the tunnel after construction. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | 150085 | 2013 | HAM - 71 - 1.34 Lytle Tunnel | Great Lakes | VECP #2: Option for redesign of Holophane Luminaire fixtures or install of Kenall Luxtran Luminaire fixtures. Additional details involve reducing the number of junction boxes and modifying the required spray-on fireproofing. | 87268 | 2016-06-02 | 829678.68 | 2016-06-03 | 2016-06-13 | 2016-06-13 | - Conceptual VECP #1 was rejected because the Department did not view the submittal as a viable option due to increased yearly energy costs. - Contractor will provide further information on both options during the Preliminary Phase to assist in deterring which is the most viable. | 2016-09-01 | [6 empty] | Change Order 2 - 10/5/2016 Change Order 3 - 10/5/2016 |  | Original Preliminary VECP and proposed GMS was rejected for using estimated quantities as opposed to original bid quantities due to a known plan error (CMS 105.19.B) |  | 465451.6 | 465451.6 | 26,27,28 | SM | N/A
12 | 150135 | 2013 | CUY - East 79th Street | Great Lakes | VECP #1 - Revises the plan drilled shafts at the Pier 1 foundation to driven pile. | 93460 | 2016-01-12 | 54631 | 2016-01-12 | 2016-01-20 | 2016-01-20 | Preliminary VECP acceptance is contingent on Norfolk Southern Railroad and Cleveland Regional Transit Authority. | 2016-02-17 | 2016-02-29 | 2016-02-29 | Approval contingent on Norfolk Southern Railroad, Greater Cleveland Rail Transit Authority and Sewer Utilities Office of Estimating GMS: 56,212.60 | 2016-03-17 |  |  | Change Order 2 - 6/1/2016 Change Order 3 - 4/4/2016 |  |  |  | 41394.8 | 41394.8 | 1,2,3 | SM | N/A
9 | 150136 | 2013 | HIG-225-1.26/2.84 | Complete General | VECP #1 - Proposed change from the three sided steel arch 1.26 structure to a single span prestressed concrete box beam supported on integral abutments with a composite, reinforced deck | 89233 | 2015-05-07 | 167045 | 2015-05-15 | 2015-05-27 | 2015-05-27 | Reviewed by Tim Keller/ Jeff Crace from the Office of Structural Engineering. Due to the low ADT, the proposed prestressed concrete box beam will not be required to be post tensioned traversely. | 2015-10-05 | 2016-10-22 | 2016-10-22 | Office of Estimating GMS: $157,533.72 | 2015-10-30 | N/A | N/A | Change Order 2 -12/18/2015 Change Order 3 - 12/18/2015 | N/A | N/A | N/A | 157533.72 | 157533.72 | 1,2,3 | SM | N/A
3 | 150188 | 2013 | MED - 42 - 18.98 | Fechko Excavating | VECP #1 - Change subgrade stabilization from granular embankment type b to cement stabilization | 86893 | 2016-03-14 | 193610 | 2016-03-14 | 2016-03-21 | 2016-03-21 | Add geotextile fabric in areas being undercut not included with the areas of cement stabilization. | 2016-03-22 | 2016-03-22 | 2016-03-22 | Office of Estimating GMS: $193,610.65 | 2016-03-24 | 2016-03-23 | N/A | 2016-03-25 | N/A | N/A | N/A | 193610.66 | 193610.66 | 6,7,8 | SM | N/A
9 | 150305 | 2013 | PIK - TR 224 - 0.18 | BUDS Inc. | VECP #1 - Widening the MOT route to complete Construction in one phase as opposed to two. | 93982 | 2015-07-27 | 35902.85 | N/A | N/A | N/A | Less then $50k - approved by the District. | N/A | N/A | N/A | Office of Estimating GMS: $36,005.25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 36005.25 | 36005.25 | 1,2,3 | SM | N/A
9 | 150308 | 2013 | SCI - 139 - 0.69 | The Shelly Company | VECP #1 - Change pavement buildup for the two foot widening based on CMS 615.05. | 93982 | 2015-07-07 | 57656 | 2015-07-08 | 2015-07-15 | N/A | Rejected for failing to meet the requirements of CMS 105.19.F. in regards to pavement buildup. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | 150331 | 2013 | BEL - IR - 70 - 5.92 | Triton Construction Inc. | VECP #1 - Installation of Reinforced Soil Slopes (RSS) at the rear/forward abutments of Bridge BEL-70-0592 | 91866 | 2015-08-21 | 550000 | 2015-08-31 | 2015-09-02 | N/A | Rejected for overall concern about long term soil stability on a high ADT route. High probability of surface erosion. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 150395 | 2013 | FRA - 71 - 5.29 | Shelly and Sand | VECP #1 - Change Phase 1 Maintenance of Traffic scheme by eliminating PCB and constructing temporary pavement for outside shoulders at night utilizing the appropriate lane closures. | 84868 | 2015-08-27 | 270000 | 2015-08-27 | 2015-09-14 | 2015-09-14 | Shelly and Sands rescinded ramp portions of the VECP. Ramps will follow plan notes. VECP will impact mainline. | 2015-09-29 | 2016-10-07 | 2016-10-07 | Office of Estimating GMS: $328,657.18. | 2015-11-02 |  |  | 2015-12-07 | - | - |  |  | 318662.68 | 1,2 | SM | -
6 | 150396 | 2013 | FRA - 70 - 3.41 | Complete General | VECP #1 - Latex Modified Concrete bridge deck overlay to Superplasticized Dense Concrete | 25594 | 2016-02-22 | 82389.48 | 2016-02-23 | 2016-02-24 | 2016-02-24 | The Dept. believes the durability of SDC and LMC are fairly equal and there is no known evidence showing one treatment is better than the other. The Dept. will experiment with optional bidding as a result of this VECP. (Two locations) | 2016-03-25 | 2016-05-20 | 2016-05-20 | 4/1/2016 - Preliminary VECP returned to Contractor for needed revisions to cost breakdown. 4/13/206 - Requested further explanation needed on labor/materials to establish GMS. 5/5/2016 - Meeting at project Field Office to discuss GMS discrepancy. 5/20/2016 - Contractor informed GMS revised to $69,800 after discovering an overestimate of plan quantity. (GMS accepted by Contractor) | 2016-08-03 | - | - | Change Order 2 -8/5/2016 Change Order 3 - 8/5/2016 | N/A | N/A | N/A | 69800 | 69800 | 5,6,7 | SM | N/A
5 | 150455 | 2013 | GUE - CR347 - 0.92 | Shelly and Sands | VECP #1 - Change drilled shafts to point-bearing H-piles, along w/ appropriate foundation & abutment wall redesigns. | 94658 | 2016-01-29 | 308288.8 | 2016-01-29 | 2016-02-26 | 2016-02-26 | VECP #1 - Foundation redesign VECP #2 - Rescinded VECP #3 - Sheet Pile redesign | 2016-03-04 | 2016-03-29 | 2016-03-29 | 3/21/16 - Multiple review iterations between Department and Contractor regarding plan clarification and constructability. Office of Estimating GMS: $308,288.80. | - | - | - | Change Order 2 -4/27/2016 Change Order 3 - 4/27/2016 | N/A | N/A | N/A | 308288.8 | 308288.8 | 2,3 | SM | N/A
5 | 150455 | 2013 | GUE - CR347 - 0.92 | Shelly and Sands | VECP #3 - Shortened the amount of stay-in-place sheet pile while increasing the length of walers and the number of tie-backs. | 94658 | 2016-03-01 | 150000 | 2016-03-03 | 2016-03-10 | 2016-03-10 | The Department noted section loss of sheet pile should be addressed at Preliminary Phase. | 2016-03-21 | 2016-04-18 | 2016-04-20 | - Required Contractor VECP Design firm to have 2nd prequalified check for approval since transition from Level 2 to Level 1 - 3/23/2016 - Multiple review iterations - Coating to prevent section loss addressed outside VECP - Office of Estimating GMS:$194,014.25 | 2016-06-08 | 2016-04-27 | - | Change Order 2 -6/21/16 Change Order 3 - 6/21/2016 | N/A | N/A | N/A | 194014.25 | 194014.25 | 4,5,6 | SM | N/A
9 | 150559 | 2013 | BRO - SR125 - 0.00 | John R. Jurgensen | VECP #1 - • Change 881 Microsurfacing to 0.75” Fine Graded Polymer Asphalt, Type B Smoot Seal | 88978 | 2016-03-03 | 21500 | 2016-03-04 | 2016-03-09 | 2016-03-09 | Rejected - CMS 105.19.F "Changes the type of buildup of permanent pavement.” - Will optional bid selected projects. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | 158003 | 2013 | Hobart/Carl Smith Drive | John R. Jurgensen | VECP#1 - Proposed to change MOT phasing to eliminate the need to reconstruct base asphalt on access road. | 83987 | 2015-04-22 | 95000 | 2015-04-28 | 2015-05-01 | NA | Rejects as not viable as a VECP. Accepting it as a VECP does not meet the intent of the VECP requirements. non-performing a work item to generate the savings and not a technical equal. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | 158011 | 2013 | JAC - 93 - 0.15 | Allard Excavation, LLC | VECP #1 - Proposed a shotcrete lining in lieu of SS 833 material. | 86588 | 2015-07-06 | 10510 | 2015-07-07 | 2015-07-14 | N/A | Rejected because the proposed shotcrete material did not meet the performance requirements set forth by SS 833 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 158035 | 2013 | FRA-270-40.45 | Shelly Company | VECP #1 - Latex Modified Concrete bridge deck overlay to Superplasticized Dense Concrete | 76352 | 2016-02-24 | 223619.92 | 2016-03-16 | 2016-03-25 | 2016-03-25 | The Dept. believes the durability of SDC and LMC are fairly equal and there is no known evidence showing one treatment is better than the other. The Dept. will experiment with optional bidding as a result of this VECP. (Six locations) | N/A | N/A | N/A | N/A | 2016-07-20 | N/A | N/A | 2016-08-02 | N/A | N/A | N/A | N/A | 221786.98 | 3,5,6 | SM | N/A
9 | 160020 | 2013 | LAW - 7 - 0.27 | Capitol Tunneling | VECP #1 - Change the steel casing liner to a Contech segmental liner plate structure. | 86702 | 3/1/2016 | 200000 | 2016-03-02 | 2016-03-07 | 2016-03-03 | Contractor provided two VECP options: GMS with either a 13' or 13.5' option | 2016-04-11 |  |  | - Contractor provided two VECP options: GMS with and without concrete field paving. The Department elected to go with the field paving option | 2016-06-28 |  | N/A | 2016-07-29 | N/A | N/A | N/A | N/A | 153590 | 1,2,3 | SM | N/A
10 | 160028 | 2013 | NOB - 77 - 1.36 | Panther Industrial | VECP #1 - Utilize a combination of MOT schemes between stationary lane closures on a divided highway and temporary road closures. | 84452 | 2016-04-13 | 40800 | 2016-04-15 | 2016-04-15 | N/A | Less then $50k Rejected by the District. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | 160041 | 2013 | BEL - 70 - 19.17 | Lash Paving | VECP #1 - Modify Phase 4A MOT from contraflow to one lane of EB traffic that will be closed per allowable times and SCD MT 95.30 | 95600 | 2016-05-13 | 228000 | 2016-05-18 | 2016-05-26 | 2016-05-26 | Exact lane spacing and drop-off depths will need detailed in Preliminary Design | 2016-07-13 | 2016-07-26 | 2016-07-26 | - | 2016-08-22 | - | - | Change Order 2 -8/22/2016 Change Order 3 - 8/22/2016 | N/A | N/A | N/A | 259868.06 | 259868.06 | 7,8,9 | SM | N/A
3 | 160080 | 2013 | ERI - 6 - 22.15 | Mosser Construction | VECP #1 - Change from proposed three sided precast concrete arch on pedestal walls supported on spread footings to a single span composite steel I-beam bridge supported on integral abutments with HP 10X42 piles driven to rock. | 90905 | 2016-03-24 | 165000 | 2016-03-29 | 2016-04-05 | N/A | Rejected - Additional maintenance requirements and not deemed hydraulically equivalent | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | 160080 | 2013 | ERI - 6 - 22.15 | Mosser Construction | VECP #1 (resubmission)- Change from proposed three sided precast concrete arch on pedestal walls supported on spread footings to single span composite spread concrete box beam bridge supported on integral abutments with HP 10X42 piles driven to rock | 90905 | 2016-04-25 | 290000 | 2016-04-25 | 2016-05-10 | N/A | Rejected - The proposed structure will have a shorter service life and higher maintenance costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | 160218 | 2013 | CUY/SUM - 271 - 0.00/14.87 | Kokosing | VECP #1 - Change the spacing and depths of the Noise Barrier drilled shafts. | 80418 | 2016-06-13 | 202740 | 2016-06-23 | 2016-06-30 | 2016-06-30 | Office of Environmental Services supports 24' spacing. | 2016-08-18 | 2016-08-24 | 2016-08-29 | Official GMS - $213,165.80 | N/A | - | - | Change Order 2 -11/28/2016 Change Order 3 - 11/28/2016 | N/A | N/A | N/A | 213165.8 | 213165.8 | 9,10 | SM | N/A
12 | 160218 | 2013 | CUY/SUM - 271 - 0.00/14.87 | Kokosing | VECP #2: MOT: Propose to have Phase 2 MOT for the two I-271 N lanes on proposed Phase 1 pavement while the two lanes of I-480 W utilize temporary pavement to cross from the existing pavement over to proposed pavement | 80418 | 2016-08-12 | 800000 | 2016-08-15 | 2016-08-29 | 2016-08-23 | The Department will require the contractor to improve roadway geometrics, ensure drainage can be maintained and exact merge locations. | 2018-12-13 | 2017-02-02 | 2017-02-02 | Temporary geometrics needed detailed on the south end of the project as 271 and 480 merged headed NB (Phase 2 Step 1), construction access points, and horizontal alignments of Ramp L-3 | 2017-03-07 |  |  | Change Order 2 - 2/15/2017 Change Order 3 - 2/15/2017 | - | - | - | 802451.1 | 802451.1 | 18,19,20 | SM | N/A
12 | 160218 | 2016 | CUY/SUM - 271 - 0.00/14.87 | Kokosing | VECP #4: Modifies the MOT plan for 271 SB and 480 EB during Phase 2 construction at the north end of the project leaving traffic in its current alignment from SB 271 by converting the existing lane of 271 (near the merge of I-480) into a yellow edge line for the length of the contraflow. The VECP results in reduced temporary pavement, striping, and avoids hydroblasting | 80418 | 2018-02-06 | 300000 | 2018-02-08 | 2018-02-14 | 2018-02-13 | VECP change order language will need to equally share shoulder repair risk if encountered. The Contractor was asked to provide all curve and tangenet information during preliminary submittals that deviate from the original plans | 2018-05-22 | 2018-05-29 | 2018-07-17 | The District's design consultant requsted additional data from the Prime Contractor regarding design speed assumptions and K values for the merge area at 271 and 480. | 2018-08-30 | 2018-07-27 | - | Change Order 2 - 8/30/2018 Change Order 3 - 8/30/2018 | - | - | - | 367790.17 | 367790.17 | 113114 | SM | N/A
12 | 160218 | 2016 | CUY/SUM - 271 - 0.00/14.87 | Kokosing | VECP #5: Phase 1-A: Shift traffic to the outside to run approximately 4’ on the shoulder to reduce temporary median pavement and slot drains and build permanent pavement to the inside. Phase 2-A: Shift traffic inside on 11’ lanes with a 2’ offset from the PCB and 2’ offset from the edge of pavement. | 80418 | 2018-02-16 | 1000000 | 2018-02-16 | 2018-03-02 | 2018-03-02 | • Add a 2’ aggregate shoulder to help stability and assist traffic running close to the edge of pavement • Depict wheel track locations to ensure traffic is not running on old/new joints • Managing shoulder repairs if needed through VECP savings | 2018-04-04 | 2018-04-16 | 2018-04-16 | VECP change order language needed to equally share shoulder repair risk if encountered | 2018-06-05 | 2018-06-01 | - | Change Order 2 - 6/13/2018 Change Order 3 - 6/13/2018 | - | - | - | 1091543.72 | 1091543.72 | 96,98,99 | SM | N/A
3 | 164002 | 2013 | ERI - 4 - 8.60 | Eclipse Construction | VECP #1 - Change the 12" undercut with 12" of cement stabilization with the option of temporary asphalt or concrete pavement | 92647 | 2016-04-18 | 49125.1 | 2016-04-21 | 2016-04-21 | N/A | Initial submission rejected - did not provide a greater or equal product or conform to SCD MT-101.90 "Drop Offs" - Conceptual Savings for Asphalt/Concrete were $49,125.10 and $32,645.60 respectively | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | 164002 | 2013 | ERI - 4 - 8.60 | Eclipse Construction | VECP #1 (resubmission) - Change the 12" undercut with 14" of cement stabilization. | 92647 | 2016-04-25 | 27464.6 | 2016-04-25 | 2016-05-06 | 2016-04-27 | VECP is under $50,000 threshold but District is requesting assistance from Central Office. | 2016-06-02 | N/A | N/A | - 7/1 Rejected - The Department was unable to establish a GMS based on original contract prices - 6/29 Teleconference between CO, D3, and Contractor to discuss GMS -6/10 Contractor resubmits new GMS based on reject of original Preliminary submittal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | 167000 | 2013 | MRG - 266 - 7.70 | Kokosing | VECP #1 - Non-perform proposed retaining wall and continue the emabankment slope down to the proposed ditchline next to R/W limits. | 89418 | 2016-05-17 | 205976.34 | 2016-07-20 | 2016-07-26 | 2016-07-26 | Contractor made the Department aware of Conceptual VECP in May but did not submit a formal proposal until July. | - | - | - | - | 2016-12-05 | 2016-11-01 | - | Change Order 2 -12/5/2016 Change Order 3 - 12/5/2016 | - | - | - | 205976.34 | 205976.34 | 12,13,14 | SM | N/A
10 | 167000 | 2013 | MRG - 266 - 7.70 | Kokosing | VECP #2 - Modify the plan 706 feet of 54” Type A conduit at 18.17% grade to 442 feet of 48” conduit at 2.5% grade in combination with rip rap and grout with PVC liner for slope erosion protection. | 89418 | 2016-08-05 | 89590 | 2016-08-18 | 2016-08-29 | 2016-08-23 | Rejected - The Department was not in favor of discharging water onto a 2:1 slope at the proposed height. In addition, the grouted rock was not believed to be a vialbe option for the site conditions. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1 | 170001 | 2016 | HAN - 75 - 14.39 | Beaver Excavating Company | Redesign of the project MOT phasing. The proposed conceptual design reduces the number of phase shifts and maximizes work areas. | 87005 | 2017-08-25 | 100000 | 2017-08-25 | 2017-08-31 | 2017-08-31 | The Department required clouded plan sheets given the fact the Contractor provided VECP drawings, provide spread calculations, list shoulder strengths, snow and ice removal, and detailed winter work approaches to insuffient weather | 10/12/2017 11/12/2017 (resubmission) 11/28/2017 (resubmission) | 2017-12-12 | 2017-12-12 | The Department had concerns about signing and the transition approaches between Phase 4 and 5 regarding barrier wall construction and the potential for exposed ends with the traveling public | 2017-12-27 | 2018-01-18 | The final VECP plans lacked detail on the construction of the barrier wall transitioning from Phase 4 to Phase 5 | Change Order 2 - 3/16/2018 Change Order 3 - 3/16/2018 | - | - | - | 130242 | 130242 | 13,27,28 | SM | N/A
6 | 170004 | 2016 | FRA - 270 - 9.15 | Kokosing | Reconstruct the outside shoulders full width from the south end to Cemetery Road to the north end of the project. North of Cemetery Rd, the VECP proposes to defer construction of the 3 foot outside shoulder widening until Phase 2 and use 11’ lanes in Phase 1. The number of lane closures on I-270 will be reduced and should improve the quality of the 3 foot outside shoulder pavement north of Cemetery Road. | 76469 | 2017-03-22 | 250000 | 2017-03-22 | 2017-03-29 | 2017-03-28 | 1. The Safety Edge and 6:1 foreslope safety grading abutting the edge of pavement (whether it is temporary edge of pavement or existing edge of pavement) is still required. 2. Show proposed new lane shifts not shown in the VECP sheets 3. Pre-phase work to install signs, sign supports, guardrail extensions, etc will still be required | 2017-05-11 | 2017-05-23 | 2017-05-23 | - | 2017-06-13 | 2017-06-19 | N/A | Change Order 2 - 8/23/2017 Change Order 3 - 8/23/2017 | - | - | 2017-06-13 | 310673.99 | 310673.99 | 1,2,3 | SM | N/A
6 | 170268 | 2016 | FRA - 70 - 14.56 | Kokosing | Replace the plan Retaining Wall 7W5 with a precast engineered wall system (Techwall) that will will include a full height precast wall with aesthetics | 103487 | 2017-06-22 | 400000 | 2017-06-22 | 2017-07-05 | N/A | Rejected - OSE stated wall thickness would have to be substantially increased for consideration by the Department because the VECP retaining wall 5 ¾" design was calculated based off of MSE wall designs. Department felt VECP was not an equal product to the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 170268 | 2016 | FRA - 70 - 14.56 | Kokosing | Modification to the design of the debris containment netting which eliminates the requirement to remove the existing vandal protection fence and install a new vandal protection fence (VPF). | 103487 | 2018-04-11 | 80000 | 2018-04-11 | 2018-04-17 | 2018-04-17 | Office of Structural Engineering approved of VECP details | 2018-05-02 | 2018-05-10 | 2018-05-10 | Teleconference call with Kokosing to discuss extra work unit costs and ownership details of existing debris netting | 2018-08-27 |  |  | Change Order 2 - 8/27/2018 Change Order 3 - 8/27/2018 | - | - | - | 87469.46 | 87469.46 | 13,14 | SM | N/A
12 | 173002 | 2016 | CUY - 480 - 18.42 | Walsh Design Built Team | VECP #1: Reduce the number of cross-frames for the new Valley View bridge structure by modifying ODOT's BDM requirement of 25' max cross-frame spacing in girder positve moment regions and 15' max in negative moment regions | 90591 | 2018-03-21 | 272206.18 | 2018-03-21 | 2018-04-06 | 2018-04-06 | During the Project pursuit, the Walsh Design Build Team proposed Alternate Technical Concept (ATC) #4: Intermediate Cross Frame Spacing but did not incorportate into bid price. ATC#4 was conditionally approved by the Department on 8/4/2017 | 2018-03-21 | 2018-04-06 | 2018-04-06 | - | 2018-04-09 | - | - | - | - | - | - | 272206.18 | 272206.18 | 1 | SM | N/A
12 | 173002 | 2016 | CUY - 480 - 18.42 | Walsh Design Built Team | VECP #2: Change of handrail/grab bars of the new Valley View bridge structure from galvanized steel to ASTM A709 weathering steel | 90591 | 2018-05-24 | 268000 | 2018-05-29 | 2018-06-14 | 2018-06-14 | Climbing rods will be galvanized in the painted zones (within 20-ft of abutments, joints, and piers). This VECP deviates from the requirements of specification section 16.5.1 Miscellaneous Materials, Item 4: Inspection platforms, catwalks, handrails, climbing rods, grating, safety bars, and supports shall be ASTM A709 steel galvanized in accordance with CMS 711.02 (ASTM A123) | 2018-05-29 | 2018-06-14 | 2018-06-14 | - | 2018-06-20 | - | - | - | - | - | - | 268000 | 268000 | 3 | SM | N/A
5 | 180001 | 2016 | COS - SR 16 /541 - 8.99/19.10 | Beaver Excavating Company | Three-part VECP to detour WB SR 16 traffic along the same detour route utilized during the SR 541 detour shown in the plans and providing a temporary signal at the on and off ramp for eastbound SR16 to allow through traffic around the work area under the SR 541 overpass | 93263 | 2018-04-05 | 450000 | 2018-04-05 | 2018-04-10 | N/A | Rejected - the Department did not view the additional detour time and potential of local roads receiving heavy traffic as a betterment to the project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | 180089 | 2016 | CUY - 480 - 22.41 | Kokosing | Eliminate the temporary tape work zone markings with Work Zone Markings Class 1 paint | 89168 | 2018-03-26 | 180000 | 2018-03-26 | 2018-03-30 | 2018-03-29 | Assumed Contractor will place Work Zone Markings at below 50°F b/c of project schedule. In such situations, the Contractor shall place Type 1A paint (Cold Weather). Class III Work Zone Marking will have to be used on the surface course since Class I Work Zone Markings are prohibited in situations of either epoxy, thermoplastic, or spray thermoplastic markings | 2018-04-04 | 2018-04-18 | 2018-04-18 | A meeting between the Office of Alternative Project Delivery, Office of Estimating, D12 Construction, and the Contractor was held on 4/17/2018 to disucss and come to agreement on extra work unit prices | 2018-06-14 | 2018-04-18 | - | Change Order 2 - 8/17/2018 Change Order 3 - 8/17/2018 | - | - | - | 254227.57 | 254227.57 | 1,4,5 | SM | N/A
2 | 180277 | 2016 | LUC - 75 - 1.10 | E.S. Wagner | Replace steel pile for drilled shafts in the median of IR-75 for cap and column piers. | 93594 | 2018-07-25 | 191889.83 | 2018-07-26 | 2018-08-01 | 2018-07-31 | Office of Geotechnical Engineering approved of VECP details | 2018-10-03 | 2018-12-18 | 2018-12-21 | Further lump sum cost breakdown of cofferdams, unclassified excavation, and pile driving mobilization was requested by the Office of Estimating. Meeting occurred on 12/4/2018. Deputy Directors of Construction, Engineering, and the District approved a GMS of $224,305.26.
5 | 184009 | 2016 | D05 - CUL - FY2018 | Eclipse Construction | Exchange the plan spray applied liner for field paving of the inverts on conduit sizes of 36", 42", 48", and 60" | 98201 | 2018-05-04 | 501125.94 | 2018-05-04 | 2018-05-09 | N/A | Rejected - The VECP was viewed as a complete change in scope of work, field paving limits future liner size, and overall is not viewed as an equal or betterment to the project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 190037 | 2016 | FRA - IR70-14.54 (Project 2E) | Kokosing | VECP #1: Leave existing Manhole #28 in place and not reconstruct to grade. The manhole sits behind the curb of Mooberry St. in front of Nationwide Children’s Hospital and is located 32’ deep. Additionally, the VECP proposes to leave in place 55’ of the existing 42” conduit feeding into the manhole to stay away from Mooberry Street to avoid further cofferdams and excavation bracing. | 105322 | 2019-04-12 | 105000 | 2019-04-18 | 2019-04-25 | N/A | Rejected - Non-performance based VECP submittal but the Department would entertain plan revisions if the impact to Mooberry Street and Nationwide Children's Hospital could be reduced from the plan allowances | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | 190037 | 2016 | FRA - IR70-14.54 (Project 2E) | Kokosing | VECP #2: Leave the large 33’ deep existing junction chamber in place on the west side of the 70/71 split carrying both a 54” and a 72” conduit. Contractor proposes to change the alignment of proposed Manhole #32 and 60” conduit to avoid the existing 54” conduit at the junction chamber tie-in. | 105322 | 2019-04-12 | 200000 | 2019-04-18 | 2019-04-25 | N/A | Rejected - the Department believes its in the best interest to replace the junction chamber and views the VECP submital as not being equal to the original plans | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | 190108 | 2016 | WOO/LUC-IR75-30.70 | Kokosing | VECP #1 Eliminates Ramp 1-D and Structure 0029N and replaces such with a configuration that mimics existing conditions (half trumpet concept) for traffic headed NB on IR-75 from Miami St. | 93592 | 2019-08-14 | 1500000 | 2019-08-22 | 2019-09-11 | 2019-09-09 | Accepted - Technically accpetable
5 | 180082 | 2016 | MUS-CR 32-0.00 | Complete General | VECP #1 The original plans required recessed lighting to be installed within the inner side of the left parapet, and on both sides of the right barrier. he contractor is proposing to utilize the same style of roadway lighting; 15ft decorative light poles (with “acorn” top luminaires) installed on the left and right barrier walls. | 97346 | 2019-09-20 | 60100 | 2019-10-08 | 2019-10-17 | 2019-10-17 | Recessed lighting was at the request of the then County Engineer. Discussion with light engr l - good with change. Would require some minor evaluation of lighting. Could allow reduction of walkway if 5ft passing zones occur every 200 ft on bridge. (Not an issue) | 2019-11-07
4 | 190328 | 2016 | STA-IR 77-08.40/VAR (PART 1 AND PART 2) | Beaver Excavating Company | VECP #1 Change the lightweight embankment proposed in the plans (EPS Geofoam Fill) with another lightweight fill material Elastizell EF-Class II Low Density Concrete Fill (LDCF). This lightweight roadway fill is required behind bridge abutments and must be placed in phases due to MOT restrictions. | 90973 | 2019-08-15 | 400000 | 2019-10-10 | 2019-10-18 | 2019-10-18 | Accepted - Beaver was made aware global stability will need verified during preliminary phase so the Department and original designer can review for accpetance.
6 | 170393 | 2016 | FRA-IR 71-9.62/9.71 (PART 1) | Shelly and Sands | VECP#1 Non-performs or skips the plan temporary 615 Class A, APP pavement in the median of IR-71 SB designed to handle traffic loads between Frank Road and Greenlawn Avenue (MOT Phase 1). With MOT revisions and additional PCB, moves directly to placing temporary pavement for MOT Phase 3B at final pavement elevations | 104799 | 2019-09-13 | 335395 | 2019-09-17 | 2019-09-18 | 2019-09-20 | Simplified VECP - Bypassed Preliminary Submission and went straight to Final. | N/A | N/A | N/A | N/A |  |  | 2019-09-20 |  | Approved | Combined Preliminary and Final Submission - reviewed by Estimating |  | 297266.65 | 297266.65 | 43,44,45 | SM | N/A
2 | 190108 | 2016 | WOO/LUC-IR75-30.70 | Kokosing | VECP #2 Relocating 72" water main from design location to avoid the required capped pile foundations and casing pipe and allow improved maintenance access for the City of Toledo. | 93592 | 2019-06-28 | 500000 | - | - | - | Central Office was made aware of the VECP after District approval was granted to Kokosing. Central Office agreed with the details and approval by the District to proceed with the VECP. | 2019-11-21 | 2019-12-06 | 2019-12-06 | The District has coordinated with CSX and the City of Toledo. The initial discussion were started in June 2019. All concerns have been addressed and the plans have been completed. | [10 empty] | SM | N/A