## Slide 2
Southern Ohio Veterans Memorial Highway
State Route 823
Notes: ----- Meeting Notes (3/3/16 09:40) -----
chancge PGG logo to SR823 version

## Slide 3: PRESENTATION OVERVIEW
Project Overview
Public Private Partnerships (P3)
Why P3 for SCI-823?
Project Update
Questions and Answers

## Slide 4: Project ROUTE
Project Location
  Rural community in Scioto County
  90 miles south of Columbus, OH
  100 miles east of Cincinnati, OH

## Slide 5: Appalachian Mountain Range

## Slide 6
The Appalachian Highway system is designed to:
    Generate economic development;
    Connect Appalachia highways to interstate system;
    Improve Regional & National market access.
Completes Appalachian Highway in Ohio
Reduces current 26 mile travel time by avoiding:
    30 traffic signals, 80 intersections, 500 driveways
Improves safety and congestion
Project Purpose and Need

## Slide 7: ORGANIZATION
Public Private Agreement
Financing Agreements
Developer
Lenders
TIFIA
Quality Oversight

## Slide 8: HOW IT ALL GOT STARTED AS A P3
HB 114 (March 2011) allowed ODOT to use P3 delivery models
ODOT conducted statewide review of potential P3 projects
SCI-823 was already well developed and “ready to go”
    Originally Design-Bid-Build in 3 Phases
    Scope Defined and Design >50% complete
    Environmental Documents complete
    ROW purchase underway
Value for Money study conducted – identified single phase Design-Build-Finance-Operate-Maintain (DBFOM) approach
ODOT submitted application for Rural TIFIA loan early

## Slide 9
Accelerate delivery of the project by 17 years
Delivers the complete project rather than in phases
Allow ODOT to pay for the project over longer period
Achieve competitive, firm fixed price
Substantial risk transfer to private sector
        Geotechnical Risk
        Design and Construction Risk
        Schedule Risk
        Finance Risk
Generates economies of scale related to construction
Effective long-term warranty through performance specifications and 35 year O&M contract
WHY P3 FOR SCI 823?

## Slide 10: PROCUREMENT TIMEFRAME
Total Duration – 3 years

## Slide 11: ORGANIZATION
Operations & Maintenance
(Developer Self-Performance)
Public Private Agreement
Financing Agreements
Developer
Equity Members
40%
20%
40%
Lenders
TIFIA
PAB’s
Quality Oversight

## Slide 12
INFRASTRUCTURE PROCUREMENT IN THE US
Traditionally:
Design-Bid-Build (DBB)
“Alternative Delivery”:
Design-Build (DB)
Public Private
Partnership (P3)
Fully Designed
Construction
Public
Private
Outline Specifications
Design and Construction
Performance Specifications
Design, Construction, Operate, and Maintain
Contract Length
1-5 years
1-5 years
20-30 years
Notes: In the traditional public-sector procurement (aka DBB):
  the public authority

## Slide 13: Risk Sharing: DBB (Traditional)
PUBLIC
PRIVATE
SHARED
Project interfaces
Right of Entry
Environmental & Historical Artefacts
Geotechnical (site)
Technical (constr.)
Contractor Failures
Cost overrun
Quality
Site Construction
Contractor Failures

## Slide 14: RISK SHARING: DBFOM (P3)
PUBLIC
PRIVATE
SHARED
Right of Entry
Environmental & Historical Artifacts
Project interfaces
Geotechnical (site)
Site Construction
Technical (construction)
Cost overrun
Quality
Contractor Failures
Notes: ----- Meeting Notes (3/3/16 09:40) -----
add other venn diagram that contrasts other project delivery methods

## Slide 15: P3 Delivery Option
Projects Sponsors
Government Subsidy
P3 Special Purpose Vehicle
Private bank loan
Operations & Maintenance
Local subcontractors
Detailed Design & Construction
Local subcontractors
Equity Investors
Notes: DBF and DBFOM
Key take-away: Financiers are exposed to the long-term project performance.
1. Analysis considered 3 delivery options:
  DBB – traditional, the benchmark for comparison
  DBF – private design, build and finance
  DBFOM – private design, build, finance, operation & maintenance
2. DBFOM process is:
  Create an SPV whose sole purpose is to build, operate and maintain the project.
  Sponsors define the project scope and the minimum performance.
  Sponsors set performance standards, and make payments to the SPV.
  SPV’s financers seek to pass down risk to Design-Build and O&M contractors.
3. Risk transfer is achieved with:
  Efficient procurement and implementation
  A bankable SPV risk profile being established
  Sponsors enforcing satisfaction of the project scope and performance

## Slide 16: P3 – HOW IT WORKS ON SCI-823
Developer prepares own design and construction specs – no ODOT design or specs
Developer builds DMF according to those criteria – performs own QA/QC
Developer gets 3 milestone payments during construction
After construction, Developer earns fixed price Availability Payment for 35 years
  Facility must perform to pre-established performance specifications
  Monthly payment subject to Unavailability Deductions
  Monthly payments subject to Non-Compliance Events deductions
Developer will “own” what they build for 35 years; any cost overruns or defects in the project are the responsibility of the Developer
  Developer will perform routine maintenance (e.g. roadside sweeping, mowing, etc)
  Developer performs major rehab (e.g. pavement resurfacing, bridge repair, etc)
After 35 years of operations, developer hands back roadway to ODOT in a good condition or suffers deductions
ODOT will perform Snow Plowing, Emergency Incident Response

## Slide 17: ORGANIZATION
DB Joint Venture
50%
30%
20%
Operations & Maintenance
(Developer Self-Performance)
Public Private Agreement
DB Agreement
Financing Agreements
Developer
Equity Members
40%
20%
40%
Lenders
TIFIA
PAB’s
Quality Oversight

## Slide 18: PROJECT SCOPE
Largest single project ODOT has ever done ($429M) – First P3
16-mile, 4-lane, limited access highway through mountainous terrain of SE Ohio
Bypasses 26 miles of US 23 and US 52, crossing NS and CSX Railroads
High fill embankments (> 180’) and deep culverts (> 170’)
Originally 3 phase construction – now one phase
Developer Maintained Facilities and Locally Maintained Facilities
Performance Based Specifications for DMF

## Slide 19: Major Project Components
GENERAL
Greenfield project
820,000 SY/340,000 TN of pavement
5 interchanges
80+ Major Culverts
  Significant Expected Settlement
20M CY Excavation, 95% rock
+300,000 SF MSE Wall
21 Structures (Steel and Concrete)
ODOT Preconstruction Activities
  Acquisition of ROW
  Tree clearing for Phase 1 of Project
  Removal of all structures and gas station at SR 140
  Relocation of AEP transmission lines

## Slide 20
Final Acceptance Date
Financial Close
April 2015
End of Term
Dec. 2053
NTP: Design Work start
Commencement of Construction
June 2015
OPERATING PERIOD: 35 years
CONSTRUCTION PERIOD: 3 years – 8 months
Substantial Completion
Date
120 days
Funding of Handback Reserve
2 years
Dec. 2018
Project timeline

## Slide 21: CONSTRUCTION SCHEDULE
Financial Close
Commencement of Construction
Culverts
Excavation – Segment 1
Finishes
Substantial Completion
Final Acceptance
Design
Utilities
Structures
Wick Drains
Excavation – Segment 2
Excavation – Segment 3
Excavation – Segment 4
Pavement
April 2015
2016
2017
2018
Dec 2018
April 2019
June 2015

## Slide 22: ORGANIZATION
DB Joint Venture
50%
30%
20%
Operations & Maintenance
(Developer Self-Performance)
Public Private Agreement
DB Agreement
Financing Agreements
Developer
Equity Members
40%
20%
40%
Designer
Lenders
TIFIA
PAB’s
Design Subconsultant
Quality Oversight

## Slide 23: Design PHASING
  Phase 1 = Segment 2B/3A
  Phase 2 = Segment 3B/4
  Phase 3 = Segment 1/2A
    Each individual bridge a separate buildable unit
    Separate culverts buildable unit for each segment
    Separate grading buildable unit for each segment
    Finish grade / drainage package separate

## Slide 24: ORGANIZATION
DB Joint Venture
50%
30%
20%
Operations & Maintenance
(Developer Self-Performance)
Public Private Agreement
DB Agreement
Financing Agreements
Developer
Independent Quality Firm
Equity Members
40%
20%
40%
Designer
Lenders
TIFIA
PAB’s
Design Subconsultant
Quality Oversight

## Slide 25: Independent Quality Firm Major Responsibilities
Accept all design and construction work
  Design reviews
  Construction inspection QA
  Testing
Create, operate, maintain an electronic document management system for the project
  Web based EADOC for final documents
  Web based SharePoint for design review
  Web based “DEMAR” database for test results
Provide Duty of Care to ODOT and the Developer
Be and remain completely independent

## Slide 26
QUESTIONS?
www.PGG823.com
Southern Ohio Veterans Memorial Highway
SR-823/SOVHM

## Slide 27
Excavation for culvert pipe – August 2015

## Slide 28
Embankment placement – August 2015

## Slide 29
Connection of wick drain and strip drains – August 2015

## Slide 30
Hitachi 1200 excavator loading CAT 773 with shot rock – September 2015

## Slide 31
Backfill placement over culvert – September 2015

## Slide 32
Wick Drain Installation – September 2015

## Slide 33
Shot rock placement for embankment – October 2015

## Slide 34
Mass rock fill along the mainline – night work – October 2015

## Slide 35
Clearing and grubbing – October 2015

## Slide 36
Embankment placement – October 2015

## Slide 37
Rock fill along the mainline – November 2015

## Slide 38
Drilling rig drilling pre-split holes – November 2015

## Slide 39
Clearing and grubbing – November 2015

## Slide 40
Jack and bore operation – December 2015

## Slide 41
Rock fill placement – night work – December 2015

## Slide 42
Scalping ravine slope and removing mulch – December 2015

## Slide 43
Shot rock placement along the mainline – January 2016

## Slide 44
Wick drain installation – January 2016

## Slide 45
Hitachi 1200 excavating shot rock beside drilling rig drilling production blast holes, CAT 773 dumping shot rock while dozer grades material – January 2016

## Slide 46
Shot rock placement for embankment while hoe ram breaks up oversized boulder – February 2016

## Slide 47
Placement of backfill over culvert – February 2016

## Slide 48
Pile driving for bridge foundation – February 2016

## Slide 49
Future Lucasville-Minford interchange – January 2016
Project Offices