**Ohio Department of Transportation**

**Scope of Services**

**Project Designation: xxx**  **Route xx** **Section xxxxx**

**Table of Contents**

 Project Designation

1. General Information 8. Variations from the Scope of Services
2. PDP Phases included in this Agreement 9. Existing Documents

and who holds Agreement 10. PDP Process

1. Project Description 11. Exceptions or Clarifications
2. Project Location / Project Limits 12. Price Proposal Due Date
3. Communication / Contacts 13. Subsequent Steps to the Agreement
4. Schedule & Review by the Department 14. On-going Services
5. Distribution of Design Information 15. Attachments

**1. General Information**

**District/Central Office:** x

**PID#:** xxxxx

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Prime Agreement | Modification No, x | Modification No. x | Modification No. x |
|  | Phase x thru x | Phase x thru x | Phase x thru x | Phase x thru x |
| Scope of Services Meeting Date |  |  |  |  |
| Approved Final Scope of Services |  |  |  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | **XXXX** |  |  |  |  |
|  |  |  |  |  |  |  |
| Functional Classification |  |  |  |  |  |  |
| Design Functional Classification |  |  |  |  |  |  |
| Posted Speed (mph) |  |  |  |  |  |  |
| Design Speed (mph) |  |  |  |  |  |  |

**2. PDP Phases Included in this Agreement**: Phase XX through Phase XX

 **Agreement between Consultant and:** Ohio Department of Transportation

This scope approval is the initial scope for development of the agreement. As the project moves through additional project development Phases, the project specific scopes of services for these additional Phases shall be developed and incorporated herein.

This Agreement will be implemented in Parts appropriate to the PDP Phases. The initial price proposal and authorization will include:

**Phase PL thru the Phase PE - Feasibility Study**

The specific scope of work and cost proposal for succeeding PDP Phase(s) will be developed as the current Phase(s) is completed.

**3. Project Description:**

|  |
| --- |
|  |

**4. Project Location/Project Limits:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | **Unit of Measure** |  | **Unit** |
|  |  |  |  |  |
| To: |  | SLM |  |  |
| From: |  | SLM |  |  |
| Project Length: |  | Miles +/- |  |  |
| Work Length: |  | Miles +/- |  |  |
| Lateral Limits: |  | Feet +/- |  |  |

Provide additional description below for defining project location/project limits.

|  |
| --- |
|  |

1. **Communication/Contacts:**

The respective project managers (ODOT and Consultant) will be the primary points of communication. Rules for communication between project staff listed below will be discussed at the Scope of Services Meeting and further described herein. Technical issues may be discussed directly (between project staff) below the project manager level, but the respective project managers must be informed of such discussions and any decisions resulting there from. Contractual issues should always be communicated at the project manager level.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Name** |  | **Phone #** |  | **E-Mail Address** |
| **ODOT** |  |  |  |  |  |
| Project Manager |  |  |  |  |  |
| Contract Manager |  |  |  |  |  |
| ODOT Staff  |  |  |  |  |  |
|  |  |  |  |  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Consultant:** |  |  |  |  |  |
| Project Manager |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

1. **Schedule & Review by the Department:**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Completion Time For Phases** | x | ***Into thru*** | PE | **:** |  | x | Months |
|  |  |  |  |  |  |  |  |
| **Completion Time for all Phases:** | x |  |  |  |  | x | Months |

The following commitment dates are derived from the Ellis events as developed:

| **Milestone** | **SFY** | **Compl.** | **Current** | **Approved** | **Lockdown (2011)** | **Lockdown (2012)** |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

The Consultant will prepare a detailed Master Schedule Gantt Chart (from initial authorization of the agreement thru completion (sale) utilizing Microsoft Project. This schedule is to be included with the price proposal. The Schedule will include beginning and ending dates as well as key milestones on the critical path (Ellis milestones) for the project. Based on the type of Consultant Agreement, the Schedule shall also accommodate appropriate time frames for scoping, negotiation and authorization for the additional Phases. If applicable to the project, the schedule will also include, at a minimum, all milestones as per the Department’s approved Enhanced Tracking Milestone Listings. The overall schedule past those phases contracted for may be general in nature meeting the dates as established within this scope. The Consultant will be responsible for timelines of Phases as authorized within this agreement. The Consultant is responsible for updating the schedule as needed throughout the PDP (or as requested by ODOT) and providing these schedules monthly or as mutually agreed at the time of scope meeting (typically with Consultant Invoices). Monthly project updates are required to be submitted to the Departments Project Manager at a minimum indicating or identifying work completed this month, expected work next month and identifying any critical items needing action from both the Consultant and Departments personnel. These updates are typically provided with monthly invoicing and should be coordinated with the Department’s Project Manager for an approved format and schedule.

**7. Electronic Distribution of Design Information**

The development of this project shall be performed in accordance with the Department’s design manuals and documents. The consultant shall perform all work required by the design manuals unless a specific exception is included herein. Absence of a specific reference to required elements of the work either in this Scope of Services or the consultant’s price proposal shall not relieve the consultant of responsibility to perform the work or justify additional compensation. The consultant’s price proposal shall be based on the most current revision of each manual at the date of the Scope of Services Meeting.

The consultant shall also be responsible to revise the plans to conform to the most recent revision of the design manuals and documents. The Department maintains current documents and a summary of the latest revisions through the Design Reference Resource Center (DRRC) (http://www.dot.state.oh.us/drrc/) (the DRRC page of the Department’s Website). This site will release all new and revised design information quarterly, on four specific dates. The most significant recent changes made to this page are reflected under the heading “Latest Revision/Revision History."

Minor changes should be routinely incorporated in the work. The consultant shall notify the Department (District Office or other office charged with administration of the agreement) in writing of any subsequent changes in design manuals or other documents that would substantially impact work already performed or change the overall impacts of the project including construction costs, right of way impacts or environmental impacts. The Department will respond in writing concerning the disposition of any such changes. The Department agrees that a substantial change in design policy or plan preparation requirements may constitute a valid request for additional compensation.

The letter transmitting final tracings shall note the last revision date of the Design Reference Resource Centerupon which the plans were based.

**8. Variations from the Scope of Service**

This Scope of Services document is based on the Department’s knowledge of project requirements at the time when the document was prepared, and serves as the basis for the price proposal and agreed fee. However, changes in the work may be required as the project develops and more complete information becomes available. Such changes also may be dictated by written procedures included in manuals or decisions made by the Department. As the project develops, it is the Consultant’s responsibility to advise the Department of significant changes in the work that may require modification of the agreement, and to maintain separate cost accounting for each specific issue. The Department’s written comments and other technical decisions concerning development of the project shall not be construed as authorization for extra work for which additional compensation may be claimed. Modification of the agreement or written authorization to proceed is required prior to the performance of additional work. In short, at all times the Consultant remains responsible to advise the Department of work that exceeds the scope of services.

Requests for modification will be evaluated from the standpoint of the scope of services in its entirety and not in terms of a single issue. Additions to the scope of services may be offset by reductions in other areas of the work.

**9. Existing Documents**

|  |
| --- |
|  |

**10. PDP Process**

The Ohio Department of Transportation (ODOT) has developed and implemented a Project Development Process (PDP) that includes regular communication among technical disciplines, results in quality plans and minimizes cost overruns during right-of-way acquisition and project construction. Depending on their size, complexity, and/or potential impact to the environment, ODOT transportation projects are categorized as one of five paths (Path 1– 5). The PDP consists of five phases that projects must advance through prior to construction. These phases include Planning, Preliminary Engineering, Environmental Engineering, Final Engineering and Construction. While all projects advance through these phases, project managers have the flexibility to adjust scope activities within the phases to better support decision-making.

The PDP is a project management and transportation decision-making procedure that outlines project development from concept through completion. Each PDP activity is timed to facilitate informed decision making based on an appropriate level of project development and risk management. The PDP encourages communication among disciplines, requires documentation of the reasoning behind project related decisions, eliminates duplicated effort among disciplines and provides for early identification of potential issues. Involvement of all disciplines during the early stages of project development ensures that issues affecting project type, scope, development schedule and costs can be correctly evaluated and anticipated.

The manual and associated tools provide guidelines to identify activities required during each phase of project development. The project scope determines the amount of work performed within the phases. Although the manual and web-based tool identifies work tasks, deliverables and potential stakeholders for each phase in the process, the process requires coordination of people and tasks between phases to ensure continued review and study of the best possible options.

Communication and transition among disciplines are critical to a project’s success. By establishing communication opportunities and responsibilities throughout the PDP, the project manager ensures that those involved in the project fulfill their project commitments. The project manager for each step is responsible for ensuring appropriate coordination and involvement of other disciplines throughout the process.

**11. Exceptions and or Clarification from Manuals**

District Preferences exceptions or manual Clarifications:

|  |
| --- |
|  |

**12. Price Proposal Due Date:** XXXX, 2012

Price proposal shall comply with the requirements for Consultant Price Proposal as posted on ODOT’s Consultant Services website:

[http://www.dot.state.oh.us/Divisions/Engineering/Consultant/ConsultDocs/ReqPriceProposal.pdf](https://www.dot.state.oh.us/Divisions/Engineering/Consultant/ConsultDocs/ReqPriceProposal.pdf)

**13. Subsequent Phases to the Agreement**

Subsequent Phases to the Agreement will be added through contract modification.

**14. On-Going Consultant Involvement during the Construction Phase**

The Consultant shall provide construction phase services as requested by the Department, for the purpose of advising the Department concerning interpretations of the plans and specifications prepared by the consultant, advising the Department of any changed or unanticipated field conditions that will impact the work, and participating in a formal Partnering process if applicable. The consultant will not have any formal ongoing duties in administration of the construction contract or inspection and testing of the project. The Consultant’s personnel assigned to this phase of the work shall be the same personnel that designed the project and prepared the plans (generally the personnel whose initials appear on the drawings).

The Consultant shall provide the following construction phase services as requested by the Department:

 Attend meetings including the preconstruction meeting, job progress meetings, partnering meetings if applicable, and other meetings as requested.

* + 1. In conjunction with job progress meetings or as requested, visit the job site at appropriate intervals to monitor critical areas of the work and advise the Department of any conditions that would affect the work.
		2. If authorized, provide on-site geotechnical support for construction of geotechnical complex systems.
		3. Respond to questions and visit the job site on an as needed basis.
		4. Assist the Department in evaluation of change orders or claims.
		5. If directed by the Department, replace right of way monumentation destroyed by the Contractor’s construction operations. Monuments shall be ¾ inch diameter steel rod, 30 inches long, with an aluminum cap having a minimum diameter of 1 ½ inch, stamped ODOT R/W and bearing the surveyor’s Ohio Registration Number and name, and/or company name. In order to support the Department’s efforts in recovering costs from the Contractor, **maintain separate cost accounting records** for this work.

 Centerline Adjustable Monument Assemblies shown on the Recorded Centerline Plat shall be set by the consultant at an appropriate stage of construction, as directed by the Department. After construction of the Centerline Adjustable Monument Assemblies by the contractor, the Consultant shall set the iron pin and cap in the Centerline Adjustable Monument Assembly Box. All centerline monuments, reference monuments and right of way monuments shall conform to Standard Construction Drawing RM-1.1 (pages 1 and 2)

* + 1. Attend the post construction meeting and prepare minutes of the meeting including a discussion of preventable change orders.

**Compliance with Health and Safety Requirements**

For Consultant personnel visiting the site, the Consultant shall be responsible for compliance with applicable health and safety requirements including OSHA requirements (CFR 29-1926), and medical testing required by OSHA and ODOT rules and regulations.

The Consultant shall provide, as a minimum, the same level of safety equipment as required for ODOT inspectors. Consultant personnel shall be subject to compliance inspections by ODOT personnel.

**Responsibilities of the Department**

* + - 1. The District Project Manager for the design agreement will remain as the point of contact for the consultant during the construction phase
			2. District construction personnel may contact the consultant directly regarding any plan questions or interpretations, but the District Project Manager for the design agreement will be notified of all such communications.
			3. The Department will advise the consultant in writing of any potential errors or omissions which must be corrected without undue delay and without additional costs to the State
			4. The Department will direct the consultant to set the iron pin and cap in the Adjustable Monument Assembly Boxes at an appropriate stage of construction.

**15. Attachments**

|  |  |
| --- | --- |
|  | Attachment Identified |
|  |  |
| Location Map | A |
|  |  |
| Scope of Services Insert for Task list with NarrativeScope of Services insert for Fee Proposal Task List | BC |
|  |  |