## Sheet1
Work Zone Constraints
Work Zone Constraints
Constraint | Work Zone Alternatives
| Part-Width | Crossover | Contraflow | Hybrid
Ability to meet Work Zone Policy | Indicate areas where the policy (# lanes, widths of lanes/shoulders, etc) can and cannot be maintained. Include information on what is needed to meet the policy and associated costs.
Ability to Maintain All Accessess | Include a Ramp Table. This table shall include ramp designation, number of lanes, ramp volume, ramp truck volume, decision sight distance, whether the ramp will be closed or open for each phase of construction, duration of closure, and detour for closure. If the ramp operates with more than one lane and this will be reduced in any phases of MOT, include this information as well. If a detour is noted - can ramps being used handle additional traffic or will modifications be needed such as widening on the ramp and/or signal work at ramp termini.
Ability to Provide Required On-Ramp Merge Decision Sight Distance | Provide the proposed decision sight distance at each entrance ramp for each phase in the ramp table. If it does not meet the required DSD in the TEM, how much does it not meet by or what will it take to meet it? This information should be included in the ramp table described above.
Right-of-Way Impacts | Explain the project ramifications of overcoming this constraint (e.g. cost of additional ROW, cost of retaining walls used). Include associated impacts to the schedule.
Environmental Impacts | Indicate areas where additional widening, bridge widening, etc. would cause impacts to streams, rivers, etc. Cost impacts and schedule impacts shall be included.
Bridge Widths | Include a Bridge Table. This table shall include extent of work being completed, length of bridge, type of bridge, existing pier spacing, existing bridge width, bridge width needed for each phase of MOT, future bridge width, and additional cost of width needed for each MOT scheme.
Significant Impacts for Construction Duration and/or Construction Costs | Include an estimated time of construction for each alternative. Describe additional costs for each alternative.
Significant impacts to earthwork, retaining walls, shoulder buildup, pier clearances, profile differences, etc. | Include information such as amount of retaining wall needed, cost of retaining wall, significant fills or cuts and associated costs, etc. Indicate if the existing shoulders are strong enough to maintain traffic based on analysis results. If they are not adequate, provide proposed improvements.
Ability to Maintain Existing Drainage and Lighting Systems | Include information such as removal of median lighting, temporary wedging to allow for drainage, etc. Include any adiditional costs associated with concerns.
Constructability; and Construction Equipment Access | Discuss issues and costs associated with contractor access and ability to construct the project. If alternatives vary greatly in cost or time describe why.
Location of Crossovers (e.g., Can crossovers be located near the project?) | How do the locations of the crossovers on each end of the project affect existing ramps? Are bridge structures going to be constraints in areas of crossovers?
What are the Access Impacts to Important Traffic Generators such as Hospitals, Fire Departments, Industries, Sports Arenas, etc. | Indicate if any ramp closures impact major traffic generators or emergency services in the area. If so, how may this be handled during closure.
For Concrete Pavements, the Longitudinal Joints must be Located at the Lane Lines.
For Asphalt Pavements, Longitudinal Phase Joints require space for proper stepping. | Include width in the work area for each lift of asphalt, base and intermediate courses, to be stepped back six inches from the previous lift, up to 18" total. (Reference TEM Figure 698-14)
Exit Ramps - Can the existing number of ramp lanes be maintained? | Include a Cost Comparison Table with the major costs differences between the alternatives analyzed. A total cost for each alternative shall also be included.
* All constraints that require any additions need to have a cost estimate associated with the alternative.