## Inspection Checklist
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
204 Subgrade Compaction and Proof Rolling
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Subgrade Compaction | [6 empty] | 0
| Unsuitable Soils Where shown in the plans or discovered in the field, were Unsuitable Soils (see 203.03.A & 703.16.A) excavated from the subgrade ? | 204.01 / 204.02 |  |  |  |  | 0
| Rock, Shale, Coal Where shown in the plans or discovered in the field, was rock, shale, or coal excavated to 2 feet below the bottom of the pavement? | 204.05 |  |  |  |  | 0
| Were the excavations for the removal of unsuitable soil, rock, shale, or coal backfilled with compacted suitable materials? | 204.07 |  |  |  |  | 0
| Is the subgrade (top 12 inches) being constructed with suitable materials that have a maximum dry density of at least 100 lbs./cubic foot? | 204.02 |  |  |  |  | 0
| Prior to compaction, is the subgrade moisture content near optimum moisture and not showing instability? | 204.03 |  |  |  |  | 0
| Has the nuclear density gauge compaction form, CA-EW-5 or CA-EW-6, been completed to determine compaction acceptance? | 204.03 |  | Never |  |  | 0
| Are compaction tests being performed at the correct frequency - one per at most 3000 SY? | 1015.07 |  | Never |  |  | 0
| Are compaction tests showing that the dry density of the subgrade is at least: 102% for max. dry density = 100 to 105 pcf; 100% for max. dry density = over 105 pcf; or 98% of a test section maximum dry density? | 204.03 |  | Never |  |  | 0
| Has the area of a failed compaction test been corrected (adjust moisture, more rolling)? | 204.03 |  |  |  |  | 0
| Did the final shaped subgrade, including under cut areas, conform to the plans and the tolerances of 203.08.D? | 204.06.B |  |  |  |  | 0
| Is the compacted subgrade being maintained and drained in accordance with 203.04.A? | 204.03 |  | Required if Non Conform |  |  | 0
| If moisture controls and compaction were not able to obtain subgrade stability, was the material removed, replaced with suitable material, and constructed to finished grade? | 204.04 |  |  |  |  | 0
| If unstable areas were discovered during subgrade compaction, were the deficiencies corrected prior proof rolling? | 204.04 |  |  |  |  | 0
Proof Rolling | [6 empty] | 0
| Is the correct weight proof roller being used? 35 tons for Clay/Silt 50 tons for Granular | 204.06.A |  | Never |  |  | 0
| Was the total weight of roller and ballast verified? Document how verified. | 204.06.A |  | Never | Required |  | 0
| Is the correct tire pressure being used - 120 psi? | 204.06.A |  | Never |  |  | 0
| At time of proof rolling, is the moisture content within 2 percent of optimum moisture, or if applicable the test section moisture? | 204.06.B |  |  |  |  | 0
| Plan underdrains installed before proof roll: Was the proof roller being kept 1.5 feet away from installed plan underdrains? | 204.06.B |  |  |  |  | 0
| Has the proof rolling form, CA-EW-2, been used to document proof rolling observations and measurements? Complete CA-EW-2. | 204.06 / MOP 204 |  |  | Required |  | 0
| If necessary, were deficient areas investigated with test pits and logged on form CA-EW-3? | MOP 204 |  |  | Required |  | 0
| Were rut depths, boring logs, or test pits used to determine depth of undercuts? | MOP 204 |  |  |  |  | 0
| Was the depth of undercut determined using MOP Figure 204.G? | MOP 204 |  |  |  |  | 0
| Was form CA-EW-8 completed to document the undercuts? | MOP 204 |  | Never |  |  | 0
| If chemical stabilization was used rather than undercutting, was the CA-Q-0206 inspection form completed? | MOP 204 |  | Never |  |  | 0
Excavation of Subgrade; Embankment and Granular Materials | [6 empty] | 0
| Were the excavations made at the correct locations and depths shown on the plans, or as directed by the Engineer? | 204.06 |  |  |  |  | 0
| What was the backfill material for the undercuts? • Embankment • Granular Embankment • Granular Material Type__ | 204.02 |  | Never | Required |  | 0
| Was the material being spread in either 8-inch thick loose lifts, or an increased lift thickness authorized by the Engineer? Document thickness | 204.07 |  |  | Required |  | 0
| Has the nuclear density gauge compaction form, CA-EW-5 or CA-EW-6, been completed to determine compaction acceptance? | 204.03 |  | Never |  |  | 0
| Are compaction tests showing that the dry density of the subgrade is at least: 102% for max. dry density = 100 to 105 pcf; 100% for max. dry density = over 105 pcf; or 98% of a test section maximum dry density? | 204.03 |  | Never |  |  | 0
Geotextile, Geogrid, Drainage | [6 empty] | 0
| If geotextile was required: Was the geotextile fabric placed properly (smooth, not tensioned, unwrinkled, 18-inch overlap, pinned/stapled)? | 204.07 |  |  |  |  | 0
| If geogrid was used: Was a CA-Q-0861 inspection form completed? | MOP 204 & SS 861 |  | Never |  |  | 0
| Was drainage provided for the undercuts (for example connect to underdrain, outlet to ditch, pipe, or catch basin/manhole)? | MOP 204 |  |  | Required |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.