## Inspection Checklist
Ohio Department of Transportation, Division of Construction Management | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
421 Microsurfacing
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| Did the contractor submit a copy of their approved QCP and approval letter? | 421.04 |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Equipment | [6 empty] | 0
| Was the equipment calibration performed in the presence of the inspector according to S1040? | 421.07 / S1040 |  |  |  |  | 0
| Was all documentation per S1040 provided to the Engineer and reviewed for compliance? | 421.07 / S1040 |  |  |  |  | 0
| Does the contractor have the appropriate size spreader box? | 421.08 |  |  |  |  | 0
| Does the contractor have a rut fill box if specified? | 421.08 |  |  |  |  | 0
| Does the equipment have a secondary strike off for surface courses? | 421.08 |  |  |  |  | 0
Temperature and Weather Limitation | [6 empty] | 0
| Is the pavement free of any standing water? | 421.05 |  |  |  |  | 0
| Is the pavement and atmospheric temperature ≥ 45° F and rising? Document Temperature. | 421.05 |  |  | Required |  | 0
| If between Sept. 30 & May 1 is the pavement temperature ≥ 50° F? Document Temperature. | 421.05 |  |  | Required |  | 0
| Temperatures are forecasted ≥ 32° F within 24 hours from the time of work? | 421.05 |  |  |  |  | 0
Test Strip and Surface Prep | [6 empty] | 0
| Pavement is cleaned and is free of any material accumulations that might hinder the bond of the binder to the pavement? Engineer has approved surface? | 421.09 |  |  |  |  | 0
| RPMs removed and holes filled with HMA? | 421.09 |  |  |  |  | 0
| Pavement markings removed, if specified, per Item 641.10? | 421.09 |  |  |  |  | 0
| Visible joints and cracks > 2ft in length or 1/4in in width are sealed per Item 423? | 421.09 |  |  |  |  | 0
| Diluted tack coat (15% residual ~ 3:1) applied per Item 407 at 0.06 to 0.12 gal/SY? | 421.09 |  |  |  |  | 0
| Existing features such as manholes, valve boxes, monuments, etc. protected? | 421.09 |  |  |  |  | 0
| A test strip 1000-foot long by lane width is constructed, reviewed after 12hrs, and approved for the JMF? Document any defects and test strip approval. | 421.10 |  | Required | Required |  | 0
Operations | [6 empty] | 0
| Verify that an approved JMF is being used. Document JMF Number. | 421.11 |  |  | Required |  | 0
| Is the rut fill placed with 1/8" or less excess crown after 24hrs of traffic? | 421.11 |  |  |  |  | 0
| Is the rut fill feathered neatly? | 421.11 |  |  |  |  | 0
| Does the course meet the application tolerances? Document Rate. Double Micro: Leveling 14+lb./sy, Surface 18 ±1 lb./sy Total must be 32 lb./sy minimum. Single Micro: Surface 21.5-22.5 lb./sy | 421.11 |  |  | Required |  | 0
| Is the micro uniform with complete coverage that fills cracks, potholes, and surface irregularities and no skips, lumps, or tears or unmixed aggregate? | 421.11 |  | Required if No |  |  | 0
| Is the surface courses wide enough to cover rut fill and leveling courses? | 421.11 |  |  |  |  | 0
| Has the microsurface restored the design profile of the pavement cross-section? | 421.11 |  |  |  |  | 0
| Straight lines maintained along curbs, shoulders, and intersections and no material runoff in these areas? | 421.11 |  |  |  |  | 0
| Are seams in the material smooth and neat with 1-3 inches of overlap where the two passes meet? | 421.11 |  |  |  |  | 0
| Does all handwork provide the same uniform appearance of the surface? | 421.11 |  |  |  |  | 0
| Is the final pavement surface uniform in texture, free of streaks, drag marks, lumps or tears? Longitudinal joints and transverse joints must be neat and straight. | 421.11 |  | Required if Non Conform |  |  | 0
| Was the Daily QC report submitted acceptable? (Meets all requirements of 421.12) | 421.12 |  |  |  |  | 0
| Were daily binder and tack samples received? | 421.12 |  |  |  |  | 0
| Was the Engineer’s summary of quantities for each day provided and the proportion of binder to dry aggregate is maintained within 1.5 gallons per ton? | 421.13 |  |  |  |  | 0
Comments Section
Provide comments for non-compliant work.
Inspection Guidance / Instruction Section