## Inspection Checklist
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
422 Chip Seal
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Equipment | [6 empty] | 0
| Binder distributor has computerized rate control that automatically adjusts the binder pump to the unit ground speed? Document Make/Model. | 422.03 |  |  | Required |  | 0
| Appropriate spray nozzles are used for the material and rate specified? | 422.03 |  |  |  |  | 0
| Minimum of three pneumatic tire rollers Type II conforming to 401.13 are used? (Max capacity does not apply.) Document Make/Model. | 422.03 |  |  | Required |  | 0
| Self-propelled aggregate spreaders: -variable width aggregate hopper 8’ to 16’? -computerized rate control automatically adjusts the aggregate output to the unit ground speed? Document Make/Model. | 422.03 |  |  | Required |  | 0
| Power sweeper, pickup sweeper or rotary broom provided? (pickup sweepers are required for curb areas and areas with no aggregate shoulder, especially lawns). Document Make/Model. | 422.03 |  |  | Required |  | 0
| Equipment was checked and approved before starting the project? | 422.03 |  |  |  |  | 0
| Are accurate thermometers provided? | 422.03 |  |  |  |  | 0
Material | [6 empty] | 0
| Polymer emulsified binder 702.16 Type A? | 422.02 / 702.04 / 702.16A |  |  |  |  | 0
| Cover material is washed limestone or dolomite meeting gradation requirements?* | 422.02 |  |  |  |  | 0
| JMF gradation is submitted to the Engineer and DET? | 422.02 |  |  |  |  | 0
Temperature and Weather Limitation | [6 empty] | 0
| Is the work performed before September 1st and after April 30th? | 422.04 |  |  |  |  | 0
| Is the pavement temperature ≥ 60° F and < 140° F? Document temperature. | 422.04 |  |  | Required |  | 0
| Is the atmospheric temperature ( ≥ 70° F)? Document temperature. | 422.04 |  |  | Required |  | 0
| Are temperatures forecasted ≥ 50° F within 24 hours from the time of work? | 422.04 |  |  |  |  | 0
Test Strip | [6 empty] | 0
| A test strip 1000-foot long by lane width is constructed? Document test strip results/location. | 422.05 | Document location |  | Required |  | 0
| Pavement is cleaned and is free of any material accumulations that might hinder the bond of the binder to the pavement? Engineer has approved surface? | 407.05 / 422.06 |  |  |  |  | 0
| The aggregate spreader was calibrated? Document target rate and actual rate. | 422.05 |  |  | Required |  | 0
| Binder and aggregate application rate determined from the test strip for 2/3 chip embedment? Document binder and aggregate rates. | 422.05 |  |  | Required |  | 0
| Aggregate sampled and gradation is confirmed from material used for test strip? | 422.05 |  |  |  |  | 0
| The test strip is reviewed the next day and approved by the Engineer? Document results. | 422.05 |  |  | Required |  | 0
Surface Prep | [6 empty] | 0
| Are all existing longitudinal pavement markings except 740.02 traffic paint removed? | 422.06 |  |  |  |  | 0
| Existing RPMs removed? | 422.06 |  |  |  |  | 0
| Is the pavement clean? | 422.06 |  |  |  |  | 0
Binder Application | [6 empty] | 0
| Binder temperature between 150°F and 180°F? | 422.07 / 422.10B |  |  |  |  | 0
| Binder is reheated at a rate of no more than 25° F per hour when cooled below 150° F (65 °C)? | 422.07 |  |  |  |  | 0
| Binder application rate is at the established target rate ±0.02 gallon/sy? Document daily yields. | 422.07 / 422.10B |  |  | Required |  | 0
| Binder is uniformly applied without streaking, triple lap coverage on spray fans? | 422.07 |  |  |  |  | 0
| Binder application starts and stops on a removable protective cover? (Paper, metal sheets, or other suitable material.) | 422.07 |  |  |  |  | 0
| Transverse and longitudinal laps are uniform and continuous in texture? | 422.07 |  |  |  |  | 0
| Proper stone embedment of 2/3 of stone height obtained? If not, is a new application rate established? | 422.07 |  |  |  |  | 0
Cover Aggregate Application | [6 empty] | 0
| Aggregate application rate is checked? Document results. | 422.08 |  |  | Required |  | 0
| Cover aggregate over applied creating nuisance? New application rate established? | 422.08 |  |  |  |  | 0
| Cover aggregate is immediately and uniformly applied without ridges or laps? | 422.08 |  |  |  |  | 0
| Tires of the trucks or aggregate spreader at no time contact the uncovered and newly applied binder? | 422.08 |  |  |  |  | 0
| Surface is protected while under cure to prevent dislodging of the aggregate particles by normal traffic? | 422.08 |  |  |  |  | 0
Operations | [6 empty] | 0
| The contractor establishes and maintains 1000-foot station intervals on the entire project before placing materials? | 422.09 |  |  |  |  | 0
| Binder distributor kept within 150 feet of the aggregate spreader at all times? | 422.09 |  |  |  |  | 0
| Rolling is performed immediately after placing the aggregate and within 5 minutes? A minimum of 3 rollers used? | 422.09 |  |  |  |  | 0
| Rollers are kept as close to each other as possible, rolling longitudinally? | 422.09 |  |  |  |  | 0
| Roller speed within 5 miles/hr without pick-up or dislodging of particles? | 422.09 |  |  |  |  | 0
| A minimum of two complete passes performed? (A complete pass is forward and backward over the same area.) | 422.09 |  |  |  |  | 0
| Was the pavement swept after binder set and within 4 hrs. of placement? | 422.09 |  |  |  |  | 0
| Sweeping is extended 1 foot beyond the edge of pavement? | 422.09 |  |  |  |  | 0
| Intersections or lawn/curb areas are free of any loose aggregate from sweeping? | 422.09 |  |  |  |  | 0
| Aggregate swept from operation is not to be re-used. | 422.09 |  |  |  |  | 0
| Double chip seal: 24 hours elapsed between 1st course and 2nd course? | 422.09 |  |  |  |  | 0
| Double chip seal: damage in the first course is fixed before placing the final chip seal? | 422.09 |  |  |  |  | 0
| Double chip seal: the joint is placed for the first course 6 inches off the centerline? | 422.09 |  |  |  |  | 0
| The longitudinal construction joint in the final course is placed at the centerline? | 422.09 |  |  |  |  | 0
Maintenance of Traffic | [6 empty] | 0
| “Loose Stone” signs and a “35 mph” speed plaque mounted below the sign at proper intervals? | 422.09 / 614 |  |  |  |  | 0
| A pilot vehicle is used on two-lane roads or pavements where traffic is maintained? | 422.09 |  |  |  |  | 0
| All utility castings, monument boxes, etc., are protected using tarpaper or other approved material? | 422.09 |  |  |  |  | 0
| One binder sample collected each day? | 422.10 |  |  |  |  | 0
| Random aggregate samples collected and sampled each day from the spreader box? Moisture Content (by dry weight) = 4% Max for adsorption >2%, 3% Max for adsorption ≤2% | 422.1 |  |  |  |  | 0
| Do gradations meet daily acceptance requirements? Moisture Content (by dry weight) = 4% Max for adsorption >2%, 3% Max for adsorption ≤2% | 422.1
| Aggregate trucks are rejected when water is seen coming from the truck bed? | 422.10 |  |  |  |  | 0
| A dust problem is not created from Aggregate? | 422.10 |  |  |  |  | 0
| Finished surface has less than four tears or untreated areas greater than 1” x 4” in any 120-square yard area? | 422.11 |  |  |  |  | 0
| Joints are neat and uniform without buildup, uncovered areas, or unsightly appearance? | 422.11 |  |  |  |  | 0
| Longitudinal joints have less than a 2-inch overlap on the adjacent passes? | 422.11 |  |  |  |  | 0
| Transverse joints have less than 1/4-inch difference in elevation across the joint as measured with a 6-foot straightedge? | 422.11 |  |  |  |  | 0
| Chip seal edge is neat and uniform along lane, shoulder, and curb lines? | 422.11 |  |  |  |  | 0
| Chip seal edge has no more than 2-inch variance in any 100 feet, along the roadway edge or shoulder? | 422.11 |  |  |  |  | 0
| Typical stone embedment is 2/3 of stone height? | 422.11 |  |  |  |  | 0
| The Contractor and Engineer reviewed the completed work 25 to 35 days after placement? | 422.11 |  |  |  |  | 0
Contractor Provided Documentation | [6 empty] | 0
| Contractor provided Engineer with daily report documenting: • Control section, project number, county, route, and Engineer • Date, air and pavement temperature, and humidity • Binder temperature • Beginning and ending stations • Yield checks on binder (3 per day, minimum) • Yield checks on aggregate (3 per day, minimum) • Gradation, moisture content, and station • Length, width, and total area • Condition of “Loose Stone” signs with “35 MPH” plaques • Contractor signature | 422.10 |  |  |  |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.