## Inspection Checklist
Ohio Department of Transportation, Division of Construction Management | [6 empty] | Y
Inspection Quality Checklist | [6 empty] | N
Item 610 Cellular Retaining Walls
Header Section
Alt ID |  | Co/Rt/Sec |  | Cont ID
Name |  | Date Inspected |  | PLN
Checklist Section
Check if Inspected | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
Construction
| Did the Contractor submit drawings to the Department for acceptance of the units to be furnished 30 days prior to construction? | 610.02
| Did the Contractor submit drawings for walls produced by manufacturers whose wall design has been in successful commercial use for a period of at least 3 years? | 610.02
| For concrete wall units, did the Contractor provide concrete conforming to Item 499, Class QC 1 and reinforcing steel conforming to 509.02? | 610.03
| For galvanized metal walls, did the Contractor furnish base metal galvanized conforming to AASHTO M 218 with a minimum thickness of 0.057 inches? | 610.03
| For galvanized metal walls, did the Contractor furnish 3 copies of the Manufacturer's, “Analysis and Coating Test Certificate”? | 610.03
| Were the precast concrete units produced by a certified precast concrete producer and shipped with a TE-24? | 610.03
| Were the precast concrete units free of exposed reinforcing steel, honeycombs and cracks? | 610.04
| Were the precast concrete units installed with Interlock headers perpendicular to sills at proper grade and alignment and not shimmed? | 610.07 |  | Required
| Were the galvanized metal walls placed in proper position and batter by the use of templates? | 610.07 |  | Required
| Was the bearing for the foundation excavated according to 203 with a firm base at the proper elevation? | 610.05
| Below the elevation of the proposed ground line at the face of the wall, were the cells filled with soil as defined in 203.02.R? | 610.06
| Above the elevation of the proposed ground line at the face of the wall, were the cells filled with material conforming to 203 Granular Material Type B, except that the percent passing the No. 200 sieve shall not exceed 5 percent? | 610.06
| Was the material placed in layers that compact to a depth not to exceed 6 inches using approved tampers or compactors? | 610.06
| Was the space behind the wall filled according to 503.08? Document type of backfill used and how compacted. | 610.06 |  | Required | Required
Comments Section
Inspection Guidance / Instruction Section
This Checklist should be filled out for each cellular retaining wall on the project.
Provide comments for non-compliant work.
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check
Check