## Inspection Checklist
Form: | CA-Q-000_NewHeaderTemplate
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
622 Concrete Barrier
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Permanent Barrier | [6 empty] | 0
| How is the barrier wall being constructed? Document cast-in-place, precast, or slip-form. | 622.03 |  |  | Required |  | 0
| Are joints constructed for cast-in-place or slip-formed barrier of the type and dimensions and at the locations specified? Document joint spacing and thickness of expansion material used. | 622.05 |  |  | Required |  | 0
| Immediately following removal of fixed forms or slip-form construction, was the surface of the barrier checked with a straightedge and all irregularities of more than 1/4 inch in 10 feet corrected? | 622.06 |  |  |  |  | 0
| Was concrete cured according to 511.14, Method B using an approved mechanical sprayer equipped with a shield to protect the spray from wind? Document the amount of curing compound used. | 622.07 |  |  | Required |  | 0
Portable Barrier | [6 empty] | 0
| Are individual sections of portable barrier wall greater than 10 feet long? | 622.04 |  |  |  |  | 0
| Are portable barrier sections damaged during handling or by traffic being replaced or repaired for the life of the project? Document the quantity of barrier replaced. | 622.04 |  |  | Required |  | 0
| If the contractor is using steel barrier: Document the brand name of steel barrier. | 622.04 |  | Required | Required |  | 0
| If the contractor is using steel barrier: Is the contractor installing the steel barrier in accordance with the manufacturer's recommendations? | 622.04 |  |  |  |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.